State of California

Annual Performance Report

for

Federal Fiscal Year 2006

(2006-2007)

Individuals With Disabilities Education Act of 2004

Due:  February 1, 2008

| ##### Table of Content |  |
| --- | --- |
| ##### Overview of Annual Performance Report Development | 1 |
| ##### Improvement Activities Across Multiple Indicators | 3 |
| ##### Indicator #1 - Graduation | 8 |
| Indicator #2 - Dropout | 13 |
| Indicator #3 – Statewide Assessment | 16 |
| Table 6 – Report of the Participation of Students with Disabilities On State Assessment | 23 |
| Indicator #4 - Suspension and Expulsion | 39 |
| Indicator #5 - Least Restrictive Environment | 59 |
| Indicator #8 - Parent Involvement | 63 |
| Indicator #9 - Disproportionality Overall | 71 |
| Indicator #10 - Disproportionality Disability | 85 |
| Indicator #11 - Eligibility Evaluation | 110 |
| Indicator #12 - Part C to Part B Transition | 114 |
| Indicator #13 - Secondary Transition Goals and Services | 119 |
| Indicator #15 - General Supervision | 123 |
| Indicator #16 - Complaints | 130 |
| Indicator #17 - Due Process | 136 |
| Indicator #18 - Hearing Requests | 139 |
| Indicator #19- Mediation | 141 |
| Indicator #20 - State-reported Data | 143 |
| Attachment 1 - Table 7, Report of Dispute Resolution under Part B of the Individuals with Disabilities Education Act | 147 |

Overview of the Annual Performance Report Development

The Annual Performance Report is prepared using instructions forwarded to the California Department of Education (CDE), Special Education Division (SED) by the U.S. Department of Education, Office of Special Education Programs (OSEP). For 2006-07, instructions were drawn from several documents:

•	California’s 2005-06 Compliance Determination letter and table (June 2007

•	General Instructions for the State Performance Plan (SPP) and Annual Performance Report (APR)

•	State Performance Plan (SPP) and Annual Performance Report (APR) Part B Indicator Measurement Table

•	State Performance Plan (SPP) and Annual Performance Report (APR) Part B Indicator Support Grid

CDE staff and contractors collected data and made calculations for each of the indicators. Technical assistance was provided by several federal contractors – most notably the Western Regional Resource Center. SED management discussed each of the requirements, reviewed calculations and discussed improvement activities.

In January 2007, based on the advice of stakeholders, SED managers undertook an overhaul of the improvement activities. Many of the improvement plans were seen as repetitive and redundant. Many were also seen as only marginally associated with true progress toward the targets and benchmarks. As a result, this document includes a section on improvement activities that address a variety of indicators. It includes descriptive material about the activities and a matrix of indicators affected by the major activity. This allows for including more pertinent improvement activities in each indicator section.

During 2006-07 CDE disseminated information and solicited input from a wide variety of groups:

•	Beginning in January 2007, the CDE, SED implemented a united stakeholder group, named Improving Special Education Services (ISES). This group was established to combine various existing stakeholder groups into one larger stakeholder constituency. Members include parents, teachers, administrators, professors in higher education, SELPA Directors, agencies, CDE special contracted staff for improvement activities, CDE staff across various divisions, and outside experts as needed. Three meetings have been held to discuss SPP and APR calculations and improvement activities – January 2007, May 2007, and December 2007. Drafts of the APR and SPP sections were disseminated in late November 2007 for comments.

•	The SPP and APR requirements and results were presented at two separate California Special Education Management Information System (CASEMIS) training sessions with the Special Education Local Plan Areas (SELPA) administrators and local educational agencies (LEA)/districts during the fall of 2006 and the spring of 2007.

•	The SPP and APR requirements were presented at regular meetings of the California Advisory Commission on Special Education. Drafts of the APR and SPP sections were disseminated in late November 2007 for comments.

•	SPP requirements and APR data related to Preschool Assessment, Preschool Least Restrictive Environment, and Transition from Part B to Part C were reviewed twice (spring 2006 and fall 2006) with a special stakeholder group of program administrators, staff, and parents.

•	Selected SPP revisions and APR data have been reviewed at the regular monthly meetings of the Directors of the SELPAs and at the quarterly meetings of the Special Education Administrators of County Offices (SEACO). Drafts of SPP and APR were disseminated in late November 2007 for comments

•	The SPP and APR were presented to the California State Board of Education (SBE) as information items in October and November 2007. SED staff met several times during the year with SBE staff and members to coordinate planning efforts and ensure a more timely submission of information. The SPP and APR were approved at its January 2008 meeting.

•	The revised SPP and APR will be posted on the CDE website once they have been approved by the OSEP. The 2007 SPP and APR may be found at http://www.cde.ca.gov/sp/se/qa/.

•	LEA level postings for 2005-06 may be found at (http://www.cde.ca.gov/sp/se/ds/sppaprrpts.asp). Posting for 2006-07 values will be made in May 2007.

General Notes:

Monitoring Data Indicators 1, 2, 3, 4 ,5 ,9, and 10 are derived from 618 data collected December 1, 2006 and/or June 30, 2007.

Determination and Correction of Noncompliance As noted in Indicator 15 in the SPP, the CDE has used multiple methods to carry out its monitoring responsibilities. These monitoring activities are part of an overall Quality Assurance Process (QAP) designed to ensure that procedural guarantees of the law are followed and that programs and services result in educational benefits. The CDE uses all of its QAP activities to monitor for procedural compliance and educational benefit. Formal noncompliance may be identified and corrective action plans develop through a wide variety of means including, data collection and analysis, investigation of compliance complaints and due process hearings, and reviewing policies and procedures in local plans. For example, the CDE uses data collected through the California Special Education Management Information System (CASEMIS) to identify districts that are not completing annual reviews of individualized educational programs (IEPs) in a timely way. These result in formal findings of noncompliance citing specific state and federal regulations and require that a corrective action plan be completed.

In addition to these components of the QAP, there are four types of traditional monitoring review processes: Facilitated Reviews, Verification Reviews, Special Education Self Reviews, and Nonpublic School Reviews (both onsite and self reviews). Each of the formal review processes results in findings of noncompliance at the student and district level. All findings require correction. At the student level the district must provide specified evidence of correction within a 45-day time period. At the district level, the district must provide updated policies and procedures, evidence that the new policies and procedures have been disseminated and, in a six-month follow-up review, the district must demonstrate that no new instances of noncompliance in that area have occurred. CDE has a variety of sanctions available to use in situations in which noncompliance goes uncorrected (e.g., special grant conditions, withholding of funds, and court action).

Compliance and Non-Compliance CDE has adjusted all of its monitoring data from an initiation year basis (e.g., Verification Reviews initiated in 2006-07) to a reporting year basis (e.g., the ABC school district review findings were reported in 2005-06). For the purpose of this and other indicators, compliance findings are reported in the year in which they were reported to the district. “On time” calculations are based on a span of one year from the date that the noncompliance finding was reported. As a result, noncompliance findings made in 2005-06 should be corrected within one year in 2006-07. For this reason, some of the finding totals cited in prior APRs may not match with this APR because they were reported by initiation date rather than reporting date.

### Improvement Activities across Multiple Indicators

In our work in California many of the Improvement activities in the SPP address multiple indicators. Instead of listing a multitude of repetitive activities in each indicator, we have chosen to highlight those large scale activities that cut across indicators and provide a brief description of what is begin done and include web links as appropriate.

Improvement Planning

Analysis and thoughtful planning of improvement activities for each of the indicators takes place in a variety of ways. Beginning in January 2007, the CDE, SED implemented a united stakeholder group, named Improving Special Education Services (ISES). This group was established to combine various existing stakeholder groups into one larger stakeholder constituency. Members include parents, teachers, administrators, professors in higher education, Special Education Local Plan Area (SELPA) Directors, agencies, CDE special contracted staff for improvement activities, CDE staff across various divisions, and outside experts as needed. ISES’s purpose is to provide CDE feedback and recommendations for improvement activities based on data in the State Performance Plan and Annual Performance Report. In addition to the ISES work SED staff has worked hard at identifying improvement activities for each indicator and have contributed to the analysis of effectiveness. http://www.calstat.org/sigPcse.html

In 2007-08, CDE will begin the development of improvement planning modules to become a part of the Verification and Special Education Self Review software.  Currently, CDE software customizes a district’s review based on a monitoring plan that, when entered into the software, generates student record review forms, policy and procedure review forms, and parent and staff interview protocols. In the current software, all of the items are related to compliance requirements of state and federal law. Existing software draws on the compliance elements of all SPP indicators, whether they are compliance indicators or not. Over the next year, CDE will incorporate programmatic self review items related to the performance based indicators. These items will generate required, self study instruments for those districts that fall below the benchmark on performance based indicators such as Indicator 3 Assessment or Indicator 5 Least Restrictive Environment. Items for these self study instruments will be drawn from a variety of sources, but starting with those instruments prepared by the CDE and OSEP technical assistance contractors. Results of the self study will be entered into the software and, based on the results; the district will develop and enter an improvement plan that can be tracked as a part of the follow-up to the monitoring review.

Communication/Information and Dissemination

Communication and dissemination of information for the SED is dispersed and present in a variety of formats. A quarterly newsletter, the Special Edge, is published and sent out free of charge to special education personnel, parents and the public. The Special Edge covers current topics in special education in California and nationally. The Division also takes the advantage of technology by providing information and training through the Web site and Webcast. Training on Transition at 16 and Student Participation in Statewide Assessments: Guidelines for Individualized Education Program (IEP) Team Decision-Making are being conducted in face to face training state wide. Our consultants are available to the field by phone or email to offer technical assistance and provide information.

Assessment

Assessment activities cross over to several indicators in the State Performance Plan. CDE has developed statewide assessments for all students. They are apart of the STAR program and include the California Standards Test (CST), California Modified Assessment, California Alternate Performance Assessment (CAPA). In addition to these three the STAR program also includes Spanish assessment for students who speak Spanish. Data is gathered from these assessments to inform Indicator 3.

In addition CDE has developed a statewide assessment for preschoolers called the Desired Results Developmental Profile Revised (DRDP-R). To provide an instrument to capture developmental progress on children with disabilities the SED has developed the DRDP access. These preschool assessments inform Indicator 7 for child outcomes. How well students do on assessments also has an impact on graduation rate, dropout rate, least restrictive environment for school age and preschool, and eligibility evaluation. Through the development of a tool kit, Student Participation in Statewide Assessments: Guidelines for IEP Team Decision-Making, IEP teams will have extensive training on how students participate in statewide assessments to maximize student success.

Closing the Achievement Gap

In December 2004, State Superintendent of Public Instruction Jack O’Connell announced he was establishing a statewide California P-16 Council to examine ways to improve student achievement at all levels and to create an integrated, seamless system of student learning from preschool through the senior year of college.

The goals of the Superintendent's California P-16 Council are to:

- Improve student achievement at all levels and eliminate the achievement gap.

- Link all education levels, preschool, elementary, middle, high school, and higher education, to create a comprehensive, seamless system of student learning.

- Ensure that all students have access to caring and qualified teachers.

- Increase public awareness of the link between an educated citizenry and a healthy economy

The Superintendent's California P-16 Council will be charged with examining ways to improve student achievement at all levels and link preschool, elementary, middle, high school, and higher education to create a comprehensive, integrated system of student learning.

It is the role of the P-16 Council to develop, implement, and sustain a specific ambitious plan that holds the State of California accountable for creating the conditions necessary for closing the achievement gap. The Council’s four subcommittees are:

- Access Subcommittee

- Culture/Climate Subcommittee

- Expectations Subcommittee

- Strategies Subcommittee

We know all children can learn to the same high levels, so we must confront and change those things that are holding back groups of students. At the Achievement Gap Summit held November 2007, stakeholders identified ways the state can better assist counties, districts, and schools in their ongoing efforts to close gaps by learning best practices from each other, sharing information and insight, and helping guide recommendations for next year.

Response to Intervention (RtI)

There are two perspectives on Response to Intervention (RtI) – the Macro view and the Micro view. The Macro view looks at RtI as a general education process that addresses the needs of all children. It involves providing high quality instruction matched to students’ needs and using rate of learning over time to make important instructional decisions about student learning. The goal is to provide for the needs of most students in the general education classroom. The Micro view looks at RtI as one component in the assessment process for the identification of a student under the Individuals with Disabilities Education Act (IDEA) as a student with a Specific Learning Disability (SLD). When effectively implemented, RtI can be seen as a process that brings together research-based curriculum and instruction, formative and summative assessments including: screening, diagnostic and progress monitoring and STAR assessments that inform instruction and employ learning supports that enhance the learning environment for all students. This is clearly a general education process that must grow and flourish within general education.

CDE, SED have formed an internal CDE RtI Partnership Group including representatives from School Improvement Division, Learning Support & Partnerships Division, Child Development Division, Secondary, Postsecondary, & Adult Leadership Division, Curriculum Framework/Instructional Resources Division and Special Education Division.

Eight expert teams of educators have been selected and each team will select 3 sites to implement RtI models in the first year. Over the next 2 years data will be collected at these implementation sites on student outcomes such as proficiency on the CSTs (API & AYP data for all groups) and other outcomes such as High School Graduation rate, dropout rate, LRE and disproportionality. These teams are also addressing RtI's relationship to the indicators on graduation rate, dropout rate, statewide assessment data, least restrictive environment and parent involvement.

NIMAS/NIMAC

The National Instructional Materials Accessibility Standard (NIMAS) and the National Instructional Materials Accessibility Center (NIMAC) were mandated for the first time in the reauthorization of IDEA in 2004. As a result, states are mandated to adopt a standard electronic file format for instructional materials. The creation of a standard electronic file format will help to ensure that students with print disabilities will have timely access to print materials. This will allow for expanded learning opportunities for all students in the Least Restrictive Environment (LRE). This will lead a greater number of students with print disabilities to be better prepared to participate in the state assessments. Additionally, a greater number of students with print disabilities can be expected to graduate with a regular diploma.

The National Instructional NIMAC serves as a national repository for NIMAS files. It is also the conduit through which the NIMAS files are made available to authorized users so that the files can converted into accessible textbooks. California will opt in to NIMAC. Therefore, California will require publishers to send NIMAS files to the Center after December, 2006. The SED will work closely with the Clearinghouse for Specialized Media and Translations (CSMT) in ensuring that all LEAs become familiar with NIMAS and NIMAC.

NIMAS and NIMAC contribute to Improvement activities several indicators; graduation, dropout, assessments, least restrictive environment and post secondary. Providing students with visual impairments with access to the core curriculum with supports greatly enhances there success.

Highly Qualified Teacher and Personnel Development

California’s teacher workforce is the largest in the country with more that 300,000 teachers serving a student population of over six million. The CDE serves more than 9,223 schools under the local control of more than 1,059 school districts.

Over the past decade California’s public education system has undergone unprecedented change. The state’s standards-based reform movement has transformed the focus and goals of public education, challenged schools to set higher expectations for all students, and hold everyone from superintendent to students responsible for academic performance. Policymakers have focused on improving California’s educational system by lowering class sizes in the primary grades, establishing standards across the curriculum, and initiating a standards-based assessment and accountability system. The state’s accountability system includes the California Standards Tests (CST), the new California Modified Assessment (CMA), the California Alternate Performance Assessment and the California High School Exit Examination (CAHSEE).

Ensuring that there is an adequate supply of highly qualified and effective teachers and administrators, in general education and special education, which are prepared to meet the challenges of teaching California’s growing and diverse student population has been a priority. The state must also ensure the equitable distribution of the most well-prepared teachers and administrators throughout the state, particularly in low-performing schools that serve a disproportionate number of poor and minority students, English learners, and special education students. Recruiting preparing and retaining highly qualified teachers and administrators is the most important investment of resources that local, state, business, and community leaders can make in education.

SED has spent time and effort on the development of highly qualified special education teachers’ guidance on NCLB/IDEA, and related state regulations. The California Commission on Teacher (CTC) Credentialing convened a task force to make recommendations for the revision of the special education credentials eliminating redundancy, increasing program access, expanding multiple entry points for special education teacher candidates and streamling the credential process. This effort will increase the number of special education teachers that meet the NCLB teacher requirements. CTC approved the task force recommendations at their December 2007 meeting. Many activities will take place over the next few years to change the special education credentials.

Professional development activities have been carried out state and district wide through out the state to address highly qualified teacher requirements and training. These activities impact student performance and many of the SPP indicators.

The first statewide action plan: The Strategic Plan for Recruiting, Preparing, and Retaining Special Education Personnel, was issued in 1997 in anticipation of a predicted shortage in the years to come. Many robust activities were successful with current focus areas as: a) school climate, b) administrative support and c) working conditions. In September 2007, it was decided to pursue investigation and fact finding for an online School-Site Teaching and Learning Conditions Survey that could yield useful data related to teaching and learning conditions as perceived by a range of school personnel. Many stakeholders including state and national technical assistance centers are assisting in this effort.

Subject Matter Verification for Secondary Teachers in Special Settings - an advanced certification option:

California’s Revised State Plan of Action for No Child Left Behind: Highly Qualified Teacher was approved by the SBE on November 2006, and by the United states Department of Education on December 2006. In that plan, a commitment is made to develop a new subject matter verification process for secondary alternative education and secondary special education teachers as a means to provide an opportunity for them to meet No Child Left Behind (NCLB) Highly Qualified Teacher (HQT) requirements. These implementing regulations were deemed permanent by the Office of Administrative Law December 2007.

The chart below provides a “crosswalk” of some of the major improvement projects and indicates with an “X” what may be considered tangential to that particular indicator.

| INDICATORS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Improvement Planning | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Communication | X | X | X |  | X |  |  |  | X | X |  |  | X | X | X |  |  |  |  |  |
| Assessment | X | X | X |  | X | X | X |  |  | X | X |  |  |  |  |  |  |  |  |  |
| Achievement Gap | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| RtI | X | X | X | X | X |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| NIMAS/NIMAC | X | X | X |  | X |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |
| HQT/Prof HQT/Prof. Development | X | X | X | X | X |  |  | X | X | X | X |  | X | X | X |  |  |  |  | X |

Monitoring Priority: FAPE in the LRE

Indicator 1:  Percent of youth with IEPs graduating from high school with a regular diploma compared to percent of all youth in the State graduating with a regular diploma.

(20 U.S.C. 1416 (a)(3)(A))

Measurement: Through the CASEMIS, the SED collects information about individual students receiving special education services. This allows SED to calculate the proportion of exiting students who graduate. The requirements to graduate with a regular diploma in California are the same for all students. In addition to meeting the district's requirements for graduation, all students are required to pass the California High School Exit Exam (CAHSEE) in order to earn a public high school diploma. California state law, however, does permit a waiver of the CAHSEE requirement for a student with an IEP who has otherwise met all other state and district graduation requirements. A local school board may grant a waiver of the CAHSEE requirement for a student with an IEP if the student has taken the CAHSEE on multiple occasions and has participated in CAHSEE preparation opportunities. In addition, students with disabilities on an IEP were exempt from the requirement to pass the CAHSEE in the 2006-07 school year. These students may have been awarded a regular high school diploma, but are not included in this calculation of the graduation rate.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | Ninety percent of districts will meet or exceed established annual benchmarks |

Actual Target Data for 2006:

In 2006-07, seventy percent of districts statewide met or exceeded the established annual benchmarks. Of the 417 LEAs with high school graduates who received special education services, 251 had sufficient numbers of students exiting (N>19)  to calculate a percentage of graduates. Table 1a depicts the number of districts having sufficient exiters that meet the benchmark by type of district.

Table 1a

California’s District-level Graduation By District Type

2006-07

| District Type | Total N | N Over Benchmark | % over Benchmark |
| --- | --- | --- | --- |
| High School Districts: Grades 9-12 | 46 | 18 | 39% |
| Unified and High School Districts Grades 7-12 | 205 | 158 | 77% |
| Total | 251 | 176 | 70% |

This compares to 90% of districts in 2005-06. It should be noted that there was a change in the method of calculating graduates in 2006-07. As required by the Office of Special Education Programs, CDE removed students who earned diplomas under a CAHSEE exemption and students who earned a diploma using a CAHSEE waiver from the data in 2006-07. These students were included in the calculation of graduates in 2005-06. Table 1b shows how the 2006-07 data would appear if the 2005-06 methodology had been used.

Table 1b

California’s State-level Graduation By Diploma Type

2005-06 and 2006-07

| Type of Diploma | 2005-06 Methodology | 2006-07 Methodology |
| --- | --- | --- |
| Regular Diploma | 16,289 | 16,289 |
| Regular Diploma awarded through CAHSEE exemption | 3,657 | - |
| Regular Diploma awarded through CAHSEE waiver | 889 | - |
| Total Graduates | 20,935 | 16,289 |
| Total Exiters | 35,149 | 35,149 |
| Percent of Exiters Graduating with a Diploma | 59.56% | 46.34% |

Table 1c shows that 34 additional districts would have been considered to meet the benchmarks had the 2005-06 methodology been used. However, the overall percentage of districts would have been 84% (210 districts meeting the benchmark divided by 251 total districts times 100) - still below the benchmark for 2006-07.

Table 1c

Number of Districts Meeting Benchmark

by 2005-06 Calculation and 2006-07 Calculation

|  | 2006-07 Met | 2006-07 Not Met | Total |
| --- | --- | --- | --- |
| 2005-06 Met | 176 | 34 | 210 |
| 2005-06 Not Met | 0 | 41 | 41 |

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

As noted above, a portion of the slippage in graduation rates is due to a change in the population included in the calculation. The drop in the statewide student percentage due to the change in methodology is approximately 13% (from 59% to 46%); as is the drop in the number of districts making the 2006-07 benchmark (83% using the 2005-06 methodology and 70% using the 2006-07 methodology).

As for the remainder of the slippage, there has been no other change in district characteristics, testing conditions or contents, policy or other data to account for the drop. It has also been suggested that the existence of the exemption has reduced the number of special education students who might have repeatedly taken the CAHSEE in order to get a diploma. The CAHSEE exemption expires December 31, 2007. Data regarding the change in rates will be available in the 2007-08 APR, due February 2009.

In the Independent Evaluation of the CAHSEE done by the Human Resources Research Organization (HumRRO), data shows that English Learners also have a very difficult time passing the CAHSEE. In California, about 25% of students with disabilities are also English Learners. This combination, English Learners with disabilities, magnifies the challenge these students face in trying to earn a high school diploma.

Access to the core curriculum is also a serious issue for students with disabilities. The HumRRO report also showed a high correlation between performance on the California Standards Tests (CSTs) and performance on the CAHSEE. Students who spent most of their day in the general education classroom performed better on both assessments. California is working to scale up the use of best practices in standards-based instruction.

Schools and districts also seem to be unaware of how to select, monitor, and evaluate the appropriate use of accommodations and modifications in instruction and for assessment. We often get questions from the field about this issue. We find that providing students with simple accommodations quite often improves achievement. A Matrix of Test Variations for Statewide Assessment is posted on the Internet. When we provide professional development to the field we continuously try to stress the importance of using appropriate accommodations and modifications that meet the students’ needs.

A number of improvement activities have been conducted during 2006-07:

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Develop and disseminate Braille Mathematics Standards and Reading Standards for students who are blind or visually impaired can meet California’s high-quality content standards and succeed in California’s statewide accountability system. | 2005-2007 | CDE staff, task force |
| In 2002, the California Legislature enacted Assembly Bill 2326, which called for the establishment of a task force to develop Braille Reading Standards. The task force was convened and it issued its recommendations to the State Board of Education in 2004. | 2005-2007 | Type: Policy and Legislated Stakeholder Task Workgroup and Technical Assistance including dissemination http://www.cde.ca.gov/sp/se/sr/ |
| In 2005, the Legislature enacted Assembly Bill 897. That legislation called for the development of Braille Mathematics Standards and required the State Board to adopt both Braille Reading and Braille Mathematics Standards for pupils who are blind or visually impaired by June 2006. | 2005-2007 | Type: Policy and Legislated Stakeholder Task Workgroup and Technical Assistance including dissemination http://www.cde.ca.gov/sp/se/sr/ |

These Braille standards give visually impaired students access to California’s high-quality content standards which will allow these students to demonstrate proficiency in California’s statewide accountability system. Improving access and achievement outcomes for visually impaired students will improve the graduation rate.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

Proposed Targets Existing benchmarks are based on data that includes students receiving diplomas based on the CAHSEE exemption and the CAHSEE waiver. CDE is proposing to adjust our district level benchmarks downward by 13% as this is the average value of the drop in districts as well as students from 2005-06 to 2006-07 methodologies.

### California’s District-level Graduation Annual Benchmarks and Targets

### by District Type, 2005-12 (Percent of Students)

| Year | District Type |  |
| --- | --- | --- |
|  | High School Districts Grades 9-12 | Unified and High School Districts Grades 7-12 |
| 2007-08 | 40 | 26 |
| 2008-09 | 43 | 32 |
| 2009-10 | 48 | 40 |
| 2010-11 | 54 | 50 |
| 2011-12 | 63 | 63 |

The statewide benchmark level of 90% of districts meeting or exceeding district level benchmarks would remain unchanged.

| FFY | Measurable and Rigorous Benchmarks and Targets |
| --- | --- |
| 2005 (2005-06) | Ninety percent of districts will meet or exceed established annual benchmarks. |
| 2006 (2006-07) | Ninety percent of districts will meet or exceed established annual benchmarks |
| 2007 (2007-08) | Ninety percent of districts will meet or exceed established annual benchmarks |
| 2008 (2008-09) | Ninety percent of districts will meet or exceed established annual benchmarks |
| 2009 (2009-10) | Ninety percent of districts will meet or exceed established annual benchmarks |
| 2010 (2010-11) | Ninety percent of districts will meet or exceed established annual benchmarks |

Proposed Improvement Activities

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Continue to provide technical assistance regarding graduation standards, promotion/retention guidelines, California High School Exit Exam (CAHSEE) | 2005-2011 | CDE staff, contractor Type: Special Project of Training and Technical Assistance |

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Development of English Learners with Disabilities Handbook | October 2008 | CDE Staff and outside agencies Type: Special Project of Training and Technical Assistance |
| Development of a Web-based training module for understanding and writing standards-based IEPs. | February 2008 | CDE Staff and outside agencies Type: Special Project of Training and Technical Assistance |
| Presentation at Superintendent’s statewide Achievement Gap Summit | November 2007 | CDE Staff and outside agency Type: Special Project of Training and Technical Assistance |

The development of the English Learners with Disabilities Handbook for use by practitioners in the field will provide increased access to California content standards for these students. The graduation rate will increase by providing greater access to core curriculum which will allow students to progress through the curriculum toward graduation.

The standards-based IEPs web-based training module will also increase access to the core curriculum for students with disabilities. It will train teachers on how to identify key standards, unpack the standards, and develop individualized goals for students. Increasing teachers’ understanding of the content standards and understand of how to develop targeted goals will increase student achievement thereby increasing the graduation rate.

California Comprehensive Center and CDE prepared a presentation for the State Superintendent’s Achievement Gap Summit. A copy of the presentation was distributed to nearly 4,000 participants. The outcomes for participants were to Identify who needs supports and accommodations, identify why supports and accommodations are needed, select, monitor and evaluate appropriate supports and accommodations, and identify specific examples of supports and accommodations that adjust instructional strategies. Helping school staff understand how to administer accommodations appropriately will help increase student access to the curriculum and increase achievement, thus increasing the graduation rate.

Monitoring Priority: FAPE in the LRE

Indicator 2:  Percent of youth with IEPs dropping out of high school compared to the percent of all youth in the State dropping out of high school.

(20 U.S.C. 1416 (a)(3)(A))

Measurement: Through the CASEMIS, the SED collects information about individual students receiving special education services. This allows SED to calculate the percent of special education students dropping out. The dropout percentage for students with disabilities is calculated by taking the number of special education students identified as dropping out or not known to be continuing divided by the total number of special education students. Only students in the 7th or higher grade or age 12 or older are included in the calculation.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | Eighty-six percent of districts will meet or exceed established annual benchmarks |

Actual Target Data for (FFY 2006 (2006-07):

All district types exceeded the eighty-six percent target.

District level benchmarks for 2006-07 are listed in Table 2a. It should be noted that benchmark is a maximum - a district that is at or below the district level benchmark is a district that meets the benchmark.

Table 2a

### California’s District-level Dropout Annual Benchmarks and Targets

### by District Type for 2006-07 (Percent of Students)

| Year | District Type |  |  |
| --- | --- | --- | --- |
|  | High School Districts Grades 9-12 | Unified and High School Districts Grades 7-12 | Elementary School Districts |
| 2006-07 | 6.6 | 7.8 | 3.6 |

Table 2b depicts the number and percent of districts that met the 2006-07 benchmark. Statewide, ninety-six percent of districts met the annual benchmark. Of the 967 LEAs reporting students with disabilities, 624 reported 19 or more students that had dropped out. Of the 624 LEAs of sufficient size (n>19) to calculate a percentage, 600 met or fell below the benchmark level.

Table 2b

California’s District-level Dropout Rate by District Type

Percent Making Benchmarks

| District Type | Total Districts | Districts Meeting Benchmark | % Meeting Benchmark |
| --- | --- | --- | --- |
| High School Districts Grades 9-12 | 73 | 70 | 95% |
| Unified and High School Districts Grades 7-12 | 323 | 311 | 96% |
| Elementary School Districts | 228 | 219 | 96% |

Table 2c indicates that less than two percent of students with disabilities, statewide, dropped out.

Table 2c

California’s Statewide Dropout Rate

| Total Students – Drop Out | 6,938 |
| --- | --- |
| Total Students Exiting | 355,449 |
| Percent of Students Dropping out | 1.95% |

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

Because of the CAHSEE exemption mentioned in Indicator 1 – Graduation Rate, many students earned a regular high school diploma who may not have graduated if the CAHSEE requirement were in place. Because these students were able to graduate, the drop out rate remained low.

Beginning in January 2008, there will no longer be an exemption of the CAHSEE requirement available to students with disabilities. This will make it more difficult for some of these students to graduate with a high school diploma. Because of this, we may see some increase in the drop out rate in the 2007-08 school year.

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Facilitate and provide training, technical assistance in a wide range of research-based core messages to assist in improving special education services in areas such as: the quality and number of teachers and other personnel who work with students with disabilities, the coordination of services for students with disabilities, the behavioral supports available for students with disabilities, academic outcomes, particularly in the area of literacy/English-language arts, the participation of parents and family members, and in the collection and dissemination of data. | August 31, 2007 | CDE staff and contractors |
| Transition to Adult Living: A Guide for Secondary Education – This comprehensive handbook is written for students parents, and teachers. It offers practical guidance and resources in support of transition efforts for students with disabilities as they move into the world of adulthood and/or independent living. | September 2007 | CDE staff and contractors |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Provide Building Effective Schools Together (BEST) positive behavioral supports program training and technical assistance focused on decreasing dropout rates. | 2005-June 30, 2011 Fall and Spring | Contractor, CDE and LEA Staff Type: Special Project Training and Technical Assistance http://www.calstat.org/sigPcse.html |
| Promote awareness of the general education dropout prevention initiative on behalf of students with disabilities | 2005-June 30, 2011 | CDE and LEA staffs Type: Technical Assistance, information dissemination http://www.cde.ca.gov/ls/ai/dp/ |

CDE provided Building Effective Schools Together (BEST) positive behavioral supports program training and technical assistance focused on decreasing dropout rates.  These supports, focusing on reducing negative behavior and reinforcing positive behavior, helps students develop a positive attitude toward school. This positive attitude toward school decreases the desire to drop out.

CDE promoted awareness of the general education dropout prevention initiative on behalf of students with disabilities. Focus on reducing the drop out rate for all students has helped maintain the low drop out rate for students with disabilities. When students with disabilities participate in programs designed for all students, they also benefit.

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Participate in State Superintendent’s initiative to close the achievement gap for students with disabilities. | December 2010 | CDE Staff and outside agencies Type: Type: Technical Assistance, information dissemination |

Participating in the State Superintendent’s initiative to close the achievement gap will benefit students with disabilities. Focus on research-based instructional strategies that are known to close the achievement gap, will maintain student motivation and decrease the drop out rate.

Monitoring Priority: FAPE in the LRE

Indicator 3:  Participation and performance of children with disabilities on statewide assessments:

- Percent of districts that have a disability subgroup that meets the State’s minimum “n” size meeting the State’s AYP objectives for progress for disability subgroup.

- Participation rate for children with IEPs in a regular assessment with no accommodations; regular assessment with accommodations; alternate assessment against grade level standards; alternate assessment against alternate achievement standards.

- Proficiency rate for children with IEPs against grade level standards and alternate achievement standards.

(20 U.S.C. 1416 (a)(3)(A))

Measurement: A. Percent = [(# of districts meeting the State’s AYP objectives for progress for the disability subgroup (children with IEPs)) divided by the (total # of districts that have a disability subgroup that meets the State’s minimum “n” size in the State)] times 100. A. Participation rate = - # of children with IEPs in assessed grades; - # of children with IEPs in regular assessment with no accommodations (percent = [(b) divided by (a)] times 100); - # of children with IEPs in regular assessment with accommodations (percent = [(c) divided by (a)] times 100); - # of children with IEPs in alternate assessment against grade level achievement standards (percent = [(d) divided by (a)] times 100); and - # of children with IEPs in alternate assessment against alternate achievement standards (percent = [(e) divided by (a)] times 100). Account for any children included in a but not included in b, c, d, or e above. Overall Percent = [(b + c + d + e) divided by (a)]. B. Proficiency rate = - # of children with IEPs in assessed grades; - # of children with IEPs in assessed grades who are proficient or above as measured by the regular assessment with no accommodations (percent = [(b) divided by (a)] times 100); - # of children with IEPs in assessed grades who are proficient or above as measured by the regular assessment with accommodations (percent = [(c) divided by (a)] times 100); - # of children with IEPs in assessed grades who are proficient or above as measured by the alternate assessment against grade level achievement standards (percent = [(d) divided by (a)] times 100); and - # of children with IEPs in assessed grades who are proficient or above as measured against alternate achievement standards (percent = [(e) divided by (a)] times 100). Account for any children included in a but not included in b, c, d, or e above. Overall Percent = [(b + c + d + e) divided by (a)].

| FFY | Measurable and Rigorous Target By School Subgroup (Percent of Students who are Proficient or Advanced) | English Language Arts | Math |
| --- | --- | --- | --- |
| 2006 (2006-07) | Elementary Schools, Middle Schools, Elementary School Districts | 24.4% | 26.5% |
|  | High Schools, High School Districts | 22.3% | 20.9% |
|  | Unified School Districts, High School Districts, County Office of Education | 23.0% | 23.7% |

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 | 3A. 52 percent of districts will meet the State’s AYP objectives for the disability subgroup. 3B. 95 percent of students with disabilities in the assessed grades will participate in statewide assessments 3C. Consistent with NCLB accountability framework, the 2005-11 AMOs (benchmarks) for the percent proficient on statewide assessments are broken down by school subgroup and are provided in the cells below. |

Actual Target Data for 2006 (2006-07)

3.A. AYP Objectives. Table 3a depicts the number and percent of districts meeting Adequate Yearly Progress Objectives

Table 3a

Number and Percent of Districts meeting Adequate Yearly Progress Objectives

|  |  | 2004-05 | 2005-06 | 2006-07 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Measured | Met |  |
|  |  | % | % | N | N | % |
| Participation | ELA | 97.5% | 78.4% | 512 | 404 | 78.9% |
|  | Math | 95.1% | 86.7% | 512 | 461 | 90.0% |
|  | Both | 95.1% | 75.6% | 512 | 397 | 77.5% |
| Proficiency | ELA | 58.4% | 66.9% | 481 | 206 | 42.8% |
|  | Math | 83.6% | 87.7% | 486 | 447 | 92.0% |
|  | Both | 56.6% | 64.4% | 481 | 203 | 42.2% |
| Overall | All AYP | 53.5% | 53.9% | 512 | 180 | 35.2% |
| Includes students in grades 2 through 8 and 10. |  |  |  |  |  |  |
| Students in grades 2 through 8 take the STAR tests, |  |  |  |  |  |  |
| Students in grade 10 take the California High School Exit Exam |  |  |  |  |  |  |
| Data source for 2004-05 is AYP database: apr05adb.dbf updated 6/20/2006 |  |  |  |  |  |  |
| Data source for 2005-06 is AYP database: apr06adb.dbf updated 9/20/2006 |  |  |  |  |  |  |
| Data source for 2006-07 is AYP database: apr07adb.dbf updated 11/28/2007 |  |  |  |  |  |  |
| California generally uses an N size of 100 for calculating AYP results. A more detailed description of minimum N size may be found on page 5 of the “Overview of California’s 2006-07 Accountability Progress Reporting System” at http://www.cde.ca.gov/ta/ac/ay/documents/overview07.pdf. |  |  |  |  |  |  |

Overall, there was a drop in the percent of districts meeting overall AYP objectives in 2006-07 (35.2%) from 53.9% in 2005-06. This appears to be due to the drop in the percent of districts proficient in English Language Arts from 66.9% in 2005-06 to 42.8% in 2006-07. The drop in district proficiency may be attributable to the number of districts who failed to qualify for an adjustment of an additional 20 percentage points due to low participation rates in the prior year.

3.B. Participation Table 3b depicts the number and percent of students participating in statewide assessment programs under various test conditions.

Table 3b

Participation of Students Receiving Special Education Services in California, 2005-06 through 2006-07

| Assessment Description | English Language Arts |  |  |  | Mathematics |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005-06 |  | 2006-07 |  | 2005-06 |  | 2006-07 |  |
|  | Number | Percent | Number | Percent | Number | Percent | Number | Percent |
| a. children with IEPs in assessed grades | 360,617 | 100.0 | 372,074 | 100.0 | 360,563 | 100.0 | 369,320 | 100.0 |
| b. Regular assessment no accommodations | 244,632 | 67.8 | 288,270 | 77.5 | 241,503 | 67.0 | 277,641 | 75.2 |
| c. Regular assessments with accommodations | 76,446 | 21.2 | 32,410 | 8.7 | 78,006 | 21.6 | 48,462 | 13.1 |
| d. Alternate assessment against grade-level standards | 29,297 | 8.1 | 30,168 | 8.1 | 29,298 | 8.1 | 30,101 | 8.2 |
| e. Alternate assessment against alternate achievement standards | 0 | 0.0 | 0 | 0.0 | 0 | 0.0 | 0 | 0.0 |
| Other - Not tested, Out of Level | 10,242 | 2.8 | 21,226 | 5.7 | 11,756 | 3.3 | 13,116 | 3.6 |
| Overall Percent (b+c+d+e)/a |  | 97.2 |  | 94.3 |  | 96.7 |  | 96.4 |
| Sources: 618 Report, Table 6, 2005-06 and 2006-07 |  |  |  |  |  |  |  |  |
| Note: Only students in Grades 3 through 8 and 10 are included in this table. AYP reports for California also include students in Grade 2. |  |  |  |  |  |  |  |  |

Overall participation dropped in English Language Arts from 97.2% in 2005-06 to 94.3% in 2006-07. There was a substantial increase in the number and percent of students taking the test with no accommodations and a substantial decrease in the number and percent of students taking the test with accommodations. Participation in the mathematics test remained fairly level – 96.7% in 2005-06 and 96.4% in 2006-07. Similar increases were noted in the number and percent of students taking the assessments with no accommodations and decreases in the number and percent of students taking the test with accommodations.

3.C. Proficiency. Table 3c depicts the number and percent of students scoring proficient and above who tested using various test conditions.

Table 3c

Proficiency rate of Students Receiving Special Education Services in California, 2004-05 through 2005-06

| Assessment Description | English Language Arts |  |  |  | Mathematics |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2005-06 |  | 2006-07 |  | 2005-06 |  | 2006-07 |  |
|  | Number | Percent | Number | Percent | Number | Percent | Number | Percent |
| a. children with IEPs in assessed grades | 360,617 | 100.0 | 372,074 | 100.0 | 360,563 | 100.0 | 369,320 | 100.0 |
| b.& c. Regular assessment with and without accommodations | 48,932 | 13.6 | 50,464 | 13.6 | 55,846 | 15.5 | 63,258 | 17.1 |
| b. Regular assessment no accommodations | Unknown | Unknown | 48,255 | 13.0 | Unknown | Unknown | 59,589 | 16.1 |
| c. Regular assessments with accommodations | Unknown | Unknown | 2,209 | 0.6 | Unknown | Unknown | 3,669 | 1.0 |
| d. Alternate assessment against grade-level standards | 17,419 | 4.8 | 19,419 | 5.2 | 17,167 | 4.8 | 17,042 | 4.6 |
| e. Alternate assessment against alternate achievement standards | 0 | 0.0 | 0 | 0.0 | 0 | 0.0 | 0 | 0.0 |
| Overall | 66,351 | 18.4 | 69,883 | 18.8 | 73,013 | 20.2 | 80,300 | 21.7 |
| Sources: 618 Report, Table 6, 2005-06 and 2006-07 |  |  |  |  |  |  |  |  |
| Notes: Only students in Grades 3 through 8 and 10 are included in this table. AYP reports for California also include students in Grade 2. |  |  |  |  |  |  |  |  |

Proficiency rates for students with disabilities have remained relatively stable between 2005-06 and 2006-07. Students with disabilities continue to demonstrate slightly higher proficiency rates on Mathematics than on English Language Arts. Table 3c represents students who scored proficient and advanced on the California Standards Test; the California Alternate Performance Assessment, and the California High School Exit Exam (grade 10). Table 3c does not include students who scored below the proficient level; it does not include students who did not test due to parental exemption or absence; and it does not include students who had invalid scores.

Table 3.C.1. depicts the percent of students receiving special education services scoring proficient or advanced by district type in 2005-06 and 2006-07. These are the rigorous targets and benchmarks included in the SPP.

Table 3.C.1. Percent of Students Scoring Proficient by District Type 2005-06 and 2006-07

| District Type | 2005-06 |  |  |  | 2006-07 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | English Language Arts |  | Math |  | English Language Arts |  | Math |  |
|  | Target | Actual | Target | Actual | Target | Actual | Target | Actual |
| Unified, COE, HS 7-12 | 23.0% | 19.6% | 23.7% | 22.4% | 23.0% | 20.8% | 23.7% | 24.3% |
| Elementary | 24.4% | 20.8% | 26.5% | 24.8% | 24.4% | 22.7% | 26.5% | 26.6% |
| HS 9-12 | 22.3% | 16.7% | 23.7% | 14.8% | 22.3% | 16.3% | 20.9% | 17.1% |

Overall, the percent of students scoring proficient or advanced increased between 2005-06 and 2006-07 in both English Language Arts and Math across district types. The only exception was a slip in English Language Arts from 16.7% to 16.3% for students served in High School districts. While no district type met the benchmarks in 2005-06 in either English Language Arts or Math, in 2006-07 both Unified and Elementary districts met the target for Math. Table 3.C.2 displays the raw data used to calculate the percent of students scoring proficient by district type in 2006-07.

| Table 3.C.2. Data Used to Calculate Percent of Students Scoring Proficient in 2006-07 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Special Education |  | ELA |  |  | Math |  |  |  |
| TYPE | N of LEA | Valid Test N | Prof & Adv N | Prof & Adv % | Valid Test N | Prof & Adv N | Prof & Adv % |  |
| Unified, COE, HS 7-12 | 400 | 273,679 | 56,918 | 20.8% | 279,175 | 67,859 | 24.3% |  |
| Elementary | 558 | 88,474 | 20,105 | 22.7% | 89,638 | 23,806 | 26.6% |  |
| HS 9-12 | 74 | 8,908 | 1,456 | 16.3% | 9,085 | 1,551 | 17.1% |  |
| Data source for 2006-07 is AYP database: apr07adb.dbf updated 11/28/2007 |  |  |  |  |  |  |  |  |

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2005 (2005-06):

“N” size for reporting assessment data in California. In its California’s Part B 2005 SPP/APR Response Table OSEP Indicated that:

The State did not submit raw data and the minimum “n” size data or the number of The districts that met the “n” size. The State must provide the required data in the FFY 2006 APR due February 1, 2008.

California generally uses an N size of 100 for calculating AYP results. A more detailed description of minimum N size may be found on page 5 of the “Overview of California’s 2006-07 Accountability Progress Reporting System” at http://www.cde.ca.gov/ta/ac/ay/documents/overview07.pdf.

#### Improvement Activities Completed

Improvement Activities have been completed as follows:

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Create blueprints for California Modified Assessment (CMA) (overlaps with CAPA). | May-August 2005 | CAPA/CMA Workgroups, CDE staff, Contractor, ETS |
| Pursue the development of an integrated database to pro-actively identify upcoming corrective actions across all components of the monitoring system. | June 30, 2006 | Outside Contractor subject to approval by the Department of Finance, CDE staff |
| Explore Web based applications for all components of the monitoring system to strengthen assessment. | June 30, 2006 | CDE staff |
| Collaborate with CDE Program Improvement and Interventions Office to infuse special education indicators into the Academic Performance Survey (APS) and District Assistance Survey (DAS). | Ongoing | CDE staff and contractors |
| Provide regionalized training and technical assistance related to using the KPI data for program improvement and assessment. | June 30, 2006 | CDE staff |
| Provide five Web casts that cover the concept of Response to Intervention (RtI) and stream this content for on-demand viewing. | December. 2005, January. February. March and April 2006 | CDE staff, contractors, SELPA |

The most notable slippage in this indicator is related to the drop in the percent of districts meeting overall AYP objectives. As noted above, this slippage is probably attributable to failure to qualify for an adjustment of an additional 20 percentage points due to low participation rates in the prior year. While districts did not fare as well overall, student proficiency is increased over the prior year, though not to the target level in all areas.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2005 (2005-2006):

In 2007-08, CDE monitoring teams will continue to review participation rates, in order to ensure the continuation of the proficiency bonus while the California Modified Achievement test is implemented and included in AYP calculations.

The following improvement activities will be continued:

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timelines | Resources |
| Cross Branch Coordination with Program Improvement to utilize data for analysis and improvement plans. | 2006 - 2010 | Riverside COE staff, CDE staff |
| Develop CMA in coordination with Standards and Assessment Division. | May 2005-2009 | CDE staff, contractor |
| Provide technical assistance to schools focused on the implementation of reform programs to high poverty and NCLB school wide schools. | Ongoing | California Comprehensive Assistance Center, CDE staff |
| Develop and maintain IDEA 2004 information Web page with links to important references and resources on the Reauthorization of IDEA, including statewide assessment. | December 2004 – ongoing | CDE/SED staff; Web capability of CDE Web page http://www.cde.ca.gov/sp/se/lr/ideareathztn.asp |
| Develop and disseminate Pocketbook of Special Education Statistics, including statewide assessment data. | Annually | CDE staff |

The following improvement activities will be added in 2006-07:

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timelines | Resources |
| Collaborate with the Standards and Assessment Division on statewide assessments in relation to students with disabilities. | 2007-2010 | CDE/SED Staff, contractors |
| Develop state guidance on student participation in statewide assessments in alignment with the April 2007 Federal regulations. | 2007-2010 | CDE/SED Staff, contractors |
| Develop and disseminate Student Participation in Statewide Assessments: Guidelines for IEP Team Decision-Making Tool Kit. | 2007-2009 | CDE/SED Staff |
| Train the Trainers workshops to build local capacity around student participation in statewide assessments. | 2008 | CDE/SED Staff |
| Collaborate with the field on the development of guidelines for students with significant cognitive disabilities for participation on alternate assessments. | Ongoing | CDE/SED Staff |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 1 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

Appendix 1 – Table 6 REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT

| SECTION A. ENROLLMENT DATA FOR THE MATH ASSESSMENT1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| GRADE LEVEL |  | STUDENTS WITH IEPs (1) | ALL STUDENTS (2) | Students with IEPs <= All Students |
| 3 |  | 51928 | 467240 | NO |
| 4 |  | 55950 | 469917 | NO |
| 5 |  | 57626 | 478111 | NO |
| 6 |  | 54668 | 484586 | NO |
| 7 |  | 51940 | 490324 | NO |
| 8 |  | 48363 | 490915 | NO |
| HSCH (SPECIFY GRADE:) | 10 | 48845 | 497959 | NO |
| 1At a date as close as possible to the testing date. |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 2 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION B. PARTICIPATION OF STUDENTS WITH DISABILITIES ON MATH ASSESSMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| GRADE LEVEL |  | STUDENTS WITH DISABILITIES WHO TOOK REGULAR ASSESSMENT ON GRADE LEVEL ACHIEVEMENT STANDARDS |  |  |  |  |
|  |  | TOTAL (3) | SUBSET (OF 3) WHO TOOK THE ASSESSMENT WITH ACCOMODATIONS (3A) | LEP STUDENTS IN US < 12 MONTHS WHOSE ENGLISH PROFICIENCY TEST REPLACED REGULAR READING ASSESSMENT (3B)1 | SUBSET (OF 3) WHOSE ASSESSMENT RESULTS WERE INVALID2 (3C) | Sum of col 3A, 3B, & 3C should be <= col 3 |
| 3 |  | 46588 | 7996 |  | 206 | 8202 |
| 4 |  | 50571 | 10239 |  | 335 | 10574 |
| 5 |  | 52458 | 10890 |  | 435 | 11325 |
| 6 |  | 49347 | 7660 |  | 585 | 8245 |
| 7 |  | 46396 | 4799 |  | 607 | 5406 |
| 8 |  | 42609 | 4399 |  | 611 | 5010 |
| HSCH : | 10 | 41107 | 2479 |  | 194 | 2673 |
| 1 This column is gray because it does not apply to the math assessment. Do not enter data in this column. |  |  |  |  |  |  |
| 2 Invalid results are assessment results that cannot be used for reporting and or aggregation due to problems in the testing process (e.g. students do not take all portions of the assessment, students do not fill out the answer sheet correctly) or changes in testing materials that resulted in a score that is not deemed by the State to be comparable to scores received by students who took the assessment without these changes. |  |  |  |  |  |  |

| SECTION B. PARTICIPATION OF STUDENTS WITH DISABILITIES ON MATH ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GRADE LEVEL |  | STUDENTS WITH DISABILITIES WHO TOOK ALTERNATE ASSESSMENT |  |  |  |  |  |  |  |
|  |  | TOTAL (4) | SUBSET (OF 4) WHOSE ALTERNATE WAS SCORED AGAINST GRADE LEVEL STANDARDS (4A) | SUBSET (OF 4) WHOSE ALTERNATE WAS SCORED AGAINST ALTERNATE ACHIEVEMENT STANDARDS (4B) | SUBSET (OF 4B) COUNTED AT THE LOWEST ACHIEVEMENT LEVEL BECAUSE OF THE NCLB CAP1 (4C) | SUBSET (OF 4) WHOSE ASSESSMENT RESULTS WERE INVALID2 (4D) | Sum of col 4A & 4B should be equal to Col 4 | Col 4C should be < col 4B | Col 4D should be < col 4 |
| 3 |  | 4364 | 4364 | 0 | 0 | 0 | 4364 |  |  |
| 4 |  | 4240 | 4240 | 0 | 0 | 0 | 4240 |  |  |
| 5 |  | 4099 | 4099 | 0 | 0 | 0 | 4099 |  |  |
| 6 |  | 4305 | 4305 | 0 | 0 | 0 | 4305 |  |  |
| 7 |  | 4454 | 4454 | 0 | 0 | 0 | 4454 |  |  |
| 8 |  | 4475 | 4475 | 0 | 0 | 0 | 4475 |  |  |
| HSCH : | 10 | 4164 | 4164 | 0 | 0 | 0 | 4164 |  |  |
| 1 NCLB 1% cap is the limit on the number of scores on an alternate assessment on alternate achievement standards that can be counted as proficient AYP calculations. If in 2006-07 your state had an approved exception to the 1% cap as indicated in Section A, use your 2006-07 adjusted cap rather than 1% when determining the number of students that must be counted in the lowest achievement level. |  |  |  |  |  |  |  |  |  |
| 2 Invalid results are assessment results that cannot be used for reporting and or aggregation due to problems in the testing process (e.g. students do not take all portions of the assessment or students do not fill out the answer sheet correctly) or changes in testing materials that resulted in a score that is not deemed by the State to be comparable to scores received by students who took the assessment without these changes. |  |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 4 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION B. PARTICIPATION OF STUDENTS WITH DISABILITIES ON MATH ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| STUDENTS WHO DID NOT TAKE AN ASSESSMENT IN ACCORDANCE WITH NCLB |  |  |  |  |  |  |  |  |  |
| GRADE LEVEL |  | STUDENTS WHO TOOK AN OUT OF LEVEL TEST (5) | STUDENTS WHO DID NOT TAKE ANY ASSESSMENT |  |  |  |  |  |  |
|  |  |  |  | PARENTAL EXEMPTION (6) | ABSENT (7) | EXEMPT FOR OTHER REASONS5 (8) |  | Sum of columns 3 through 8 should equal col 1, Section A | Number reported in col 1, Section A |
| 3 |  | 0 |  | 446 | 530 | 0 |  | 51928 | 51928 |
| 4 |  | 0 |  | 478 | 661 | 0 |  | 55950 | 55950 |
| 5 |  | 0 |  | 465 | 604 | 0 |  | 57626 | 57626 |
| 6 |  | 0 |  | 343 | 673 | 0 |  | 54668 | 54668 |
| 7 |  | 0 |  | 306 | 784 | 0 |  | 51940 | 51940 |
| 8 |  | 0 |  | 339 | 940 | 0 |  | 48363 | 48363 |
| HSCH | 10 | 0 |  | 20 | 3554 | 0 |  | 48845 | 48845 |
| 1 In a separate listing, report the number of students exempted for other reasons by grade and specific reason. |  |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 5 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 6 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION C. PERFORMANCE OF STUDENTS WITH DISABILITIES ON MATH ASSESSMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | REGULAR ASSESSMENT ON GRADE LEVEL (9A) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 | 2 | 3 | 4 |  |  |  |  |  |  |  |  |
| GRADE LEVEL | TEST NAME | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | 9A ROW TOTAL1 | Computed row Total | Computed row total should equal col 3 minus col 3B minus 3C |
| 3 | STAR-CST | 21953 | 8732 | 8321 | 7376 | 0 | 0 | 0 | 0 | 0 | 46382 | 46382 | 46382 |
| 4 | STAR-CST | 24032 | 11228 | 8103 | 6873 | 0 | 0 | 0 | 0 | 0 | 50236 | 50236 | 50236 |
| 5 | STAR-CST | 31930 | 8812 | 7324 | 3957 | 0 | 0 | 0 | 0 | 0 | 52023 | 52023 | 52023 |
| 6 | STAR-CST | 31676 | 10025 | 5043 | 2018 | 0 | 0 | 0 | 0 | 0 | 48762 | 48762 | 48762 |
| 7 | STAR-CST | 32265 | 8143 | 3890 | 1491 | 0 | 0 | 0 | 0 | 0 | 45789 | 45789 | 45789 |
| 8 | STAR-CST | 29686 | 8352 | 3299 | 661 | 0 | 0 | 0 | 0 | 0 | 41998 | 41998 | 41998 |
| HSCH :10 | CAHSEE | 27919 | 8092 | 3968 | 934 | 0 | 0 | 0 | 0 | 0 | 40913 | 40913 | 40913 |
| LOWEST ACHIEVEMENT LEVEL CONSIDERED PROFICIENT: 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 The total number of students reported by Achievement Level in 9A is to equal the number reported in column 3 minus the number reported in columns 3B and 3C. |  |  |  |  |  |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 7 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION C. PERFORMANCE OF STUDENTS WITH DISABILITIES ON MATH ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ALTERNATE ASSESSMENT ON GRADE LEVEL STANDARDS (9B) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 | 2 | 3 | 4 |  |  |  |  |  |  |  |  |  |
| GRADE LEVEL | TEST NAME | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | 9B ROW TOTAL1 | Computed row Total | Column 4A - column 4D should be less than or equal to computed total | Column 4A should be greater than or equal to computed total |
| 3 | CAPA | 527 | 759 | 1408 | 1670 | 0 | 0 | 0 | 0 | 0 | 4364 | 4364 | 4364 | 4364 |
| 4 | CAPA | 771 | 764 | 1308 | 1397 | 0 | 0 | 0 | 0 | 0 | 4240 | 4240 | 4240 | 4240 |
| 5 | CAPA | 659 | 668 | 1173 | 1599 | 0 | 0 | 0 | 0 | 0 | 4099 | 4099 | 4099 | 4099 |
| 6 | CAPA | 1445 | 1042 | 1093 | 725 | 0 | 0 | 0 | 0 | 0 | 4305 | 4305 | 4305 | 4305 |
| 7 | CAPA | 1333 | 967 | 1187 | 967 | 0 | 0 | 0 | 0 | 0 | 4454 | 4454 | 4454 | 4454 |
| 8 | CAPA | 1219 | 949 | 1218 | 1089 | 0 | 0 | 0 | 0 | 0 | 4475 | 4475 | 4475 | 4475 |
| HSCH:10 | CAPA | 1148 | 808 | 988 | 1220 | 0 | 0 | 0 | 0 | 0 | 4164 | 4164 | 4164 | 4164 |
| LOWEST ACHIEVEMENT LEVEL CONSIDERED PROFICIENT: 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 The total number of students reported by achievement level in 9B is equal to the number reported in Column 4A minus that portion of 4D that refers to invalid results from assessments scored against grade level achievement standards. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 8 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION C. PERFORMANCE OF STUDENTS WITH DISABILITIES ON MATH ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ALTERNATE ASSESSMENT SCORED AGAINST ALTERNATE STANDARDS (9C) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRADE LEVEL | TEST NAME | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | 9C ROW TOTAL2 |  | Computed row Total | (Column 4B - Column 4D)1 should be equal to or less than the computed total | (Column 4B - Column 4D)1 should be greater than or equal to computed total | (Column 4A + Column 4B - Column 4D)1 should be equal totals for column 9B plus 9C |
| 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4364 |
| 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4240 |
| 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4099 |
| 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4305 |
| 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4454 |
| 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4475 |
| HSCH:10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4164 |
| LOWEST ACHIEVEMENT LEVEL CONSIDERED PROFICIENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 Include all students whose assessment counted in the lowest achievement level because of the NCLB 1% cap. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 The total number of students reported by achievement level in 9C is to equal the number reported in column 4B minus that portion of 4D that refers to invalid results from assessments scored against alternate |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| SECTION C. PERFORMANCE OF STUDENTS WITH DISABILITIES ON MATH ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GRADE LEVEL |  | TOTAL FOR COLUMN 9A (ON PAGE 6)1 | TOTAL FOR COLUMN 9B (ON PAGE 7)1 | TOTAL FOR COLUMN 9C (ON PAGE 8)1 | NO VALID SCORE1,2 (10) | TOTAL1,3 (11) | Sum of Column 3 through column 8 | Number reported in col 1, Section A |
| 3 |  | 46382 | 4364 | 0 | 1182 | 51928 | 51928 | 51928 |
| 4 |  | 50236 | 4240 | 0 | 1474 | 55950 | 55950 | 55950 |
| 5 |  | 52023 | 4099 | 0 | 1504 | 57626 | 57626 | 57626 |
| 6 |  | 48762 | 4305 | 0 | 1601 | 54668 | 54668 | 54668 |
| 7 |  | 45789 | 4454 | 0 | 1697 | 51940 | 51940 | 51940 |
| 8 |  | 41998 | 4475 | 0 | 1890 | 48363 | 48363 | 48363 |
| HSCH : | 10 | 40913 | 4164 | 0 | 3768 | 48845 | 48845 | 48845 |
| 1 STATES SHOULD NOT REPORT DATA ON THIS PAGE. THESE DATA WILL BE CALCULATED FROM THE REPORTED DATA AFTER THE COUNTS ARE SUBMITTED. PLEASE REVIEW FORERRORS. |  |  |  |  |  |  |  |  |
| 2 Column 10 is calculated by summing the numbers reported in column 3C plus column 4D plus column 5 plus column 6 plus column 7 plus column 8. |  |  |  |  |  |  |  |  |
| 3 Column 11 should equal the number of students with IEPs reported in column 1 of Section A. If the number of students is not the same, provide an explanation. Column 11 should always equal the sum of the number of students reported in columns 3 plus column 4 plus column 5 plus column 6 plus column 7 plus column 8. |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 9 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 10 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION D. ENROLLMENT DATA FOR THE READING ASSESSMENT1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| GRADE LEVEL |  | STUDENTS WITH IEPs (1) | ALL STUDENTS (2) |  | Students with IEPs <= All Students |
| 3 |  | 52190 | 467394 |  | NO |
| 4 |  | 56104 | 470089 |  | NO |
| 5 |  | 57776 | 478262 |  | NO |
| 6 |  | 54870 | 484692 |  | NO |
| 7 |  | 52288 | 490472 |  | NO |
| 8 |  | 50074 | 491044 |  | NO |
| HSCH (SPECIFY GRADE:) | 10 | 48772 | 496778 |  | NO |
| 1At a date as close as possible to the testing date. |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 11 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION E. PARTICIPATION OF STUDENTS WITH DISABILITIES ON READING ASSESSMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | STUDENTS WITH DISABILITIES WHO TOOK REGULAR ASSESSMENT ON GRADE LEVEL ACHIEVEMENT STANDARDS |  |  |  |  |  |
| GRADE LEVEL |  | TOTAL (3) | SUBSET (OF 3) WHO TOOK THE ASSESSMENT WITH ACCOMODATIONS (3A) | LEP STUDENTS IN US < 12 MONTHS WHOSE ENGLISH PROFICIENCY TEST REPLACED REGULAR READING ASSESSMENT (3B)1 | SUBSET (OF 3) WHOSE ASSESSMENT RESULTS WERE INVALID2 (3C) | Sum of col 3A, 3B, & 3C should be <= col 3 |  |
| 3 |  | 46704 | 3988 | 0 | 1553 | 5541 |  |
| 4 |  | 50664 | 7229 | 0 | 1825 | 9054 |  |
| 5 |  | 52533 | 6473 | 0 | 1785 | 8258 |  |
| 6 |  | 49440 | 4825 | 0 | 1612 | 6437 |  |
| 7 |  | 46580 | 4608 | 0 | 1207 | 5815 |  |
| 8 |  | 44195 | 3249 | 0 | 1070 | 4319 |  |
| HSCH : | 10 | 41036 | 2038 | 0 | 1420 | 3458 |  |
| 1 Report those LEP students who, at the time of the reading assessment, were in the United States for less than 12 months and took the English proficiency test in place of the regular reading assessment. |  |  |  |  |  |  |  |
| 2 Invalid results are assessment results that cannot be used for reporting and or aggregation due to problems in the testing process (e.g. students do not take all portions of the assessment or students do not fill out the answer sheet correctly) or changes in testing materials that resulted in a score that is not deemed by the State to be comparable to scores received by students who took the assessment without these changes. |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 13 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION E. PARTICIPATION OF STUDENTS WITH DISABILITIES ON READING ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | STUDENTS WITH DISABILITIES WHO TOOK ALTERNATE ASSESSMENT |  |  |  |  |  |  |  |  |
| GRADE LEVEL |  | TOTAL (4) | SUBSET (OF 4) WHOSE ALTERNATE WAS SCORED AGAINST GRADE LEVEL STANDARDS (4A) | SUBSET (OF 4) WHOSE ALTERNATE WAS SCORED AGAINST ALTERNATIVE ACHIEVEMENT STANDARDS (4B) | SUBSET (OF 4B) COUNTED AT THE LOWEST ACHIEVEMENT LEVEL BECAUSE OF THE NCLB 1% CAP1 (4C) | SUBSET (OF 4) WHOSE ASSESSMENT RESULTS WERE INVALID2 (4D) |  | Sum of col 4A, 4B, & 4D should be equal to Col 4 | Col 4C should be < col 4B | Col 4D should be < col 4 |
| 3 |  | 4374 | 4374 | 0 | 0 | 0 |  | 4374 |  |  |
| 4 |  | 4247 | 4247 | 0 | 0 | 0 |  | 4247 |  |  |
| 5 |  | 4103 | 4103 | 0 | 0 | 0 |  | 4103 |  |  |
| 6 |  | 4313 | 4313 | 0 | 0 | 0 |  | 4313 |  |  |
| 7 |  | 4467 | 4467 | 0 | 0 | 0 |  | 4467 |  |  |
| 8 |  | 4487 | 4487 | 0 | 0 | 0 |  | 4487 |  |  |
| HSCH : | 10 | 4177 | 4177 | 0 | 0 | 0 |  | 4177 |  |  |
| 1 NCLB 1% cap is the limit on the number of scores on an alternate assessment on alternate achievement standards that can be counted as proficient AYP calculations. If in 2006-07 your state had an approved exception to the 1% cap as indicated in Section A, use your 2006-07 adjusted cap rather than 1% when determining the number of students that must be counted in the lowest achievement level. |  |  |  |  |  |  |  |  |  |  |
| 2 Invalid results are assessment results that cannot be used for reporting and or aggregation due to problems in the testing process (e.g. students do not take all portions of the assessment or students do not fill out the answer sheet correctly) or changes in testing materials that resulted in a score that is not deemed by the State to be comparable to scores received by students who took the assessment without these changes. |  |  |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION E. PARTICIPATION OF STUDENTS WITH DISABILITIES ON READING ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | STUDENTS WHO DID NOT TAKE AN ASSESSMENT IN ACCORDANCE WITH NCLB |  |  |  |  |  |  |  |
|  |  |  |  | STUDENTS WHO DID NOT TAKE ANY ASSESSMENT |  |  |  |  |  |
| GRADE LEVEL |  | STUDENTS WHO TOOK AN OUT OF LEVEL TEST (5) | PARENTAL EXEMPTION (6) |  | ABSENT (7) | EXEMPT FOR OTHER REASONS5 (8) | Sum of columns 3 through 8 should equal col 1, Section A |  | Number reported in col 1, Section A |
| 3 |  | 0 | 442 |  | 670 | 0 | 52190 |  | 52190 |
| 4 |  | 0 | 281 |  | 912 | 0 | 56104 |  | 56104 |
| 5 |  | 0 | 455 |  | 685 | 0 | 57776 |  | 57776 |
| 6 |  | 0 | 342 |  | 775 | 0 | 54870 |  | 54870 |
| 7 |  | 0 | 181 |  | 1060 | 0 | 52288 |  | 52288 |
| 8 |  | 0 | 323 |  | 1069 | 0 | 50074 |  | 50074 |
| HSCH: | 10 | 0 | 20 |  | 3539 | 0 | 48772 |  | 48772 |
| 1 In a separate listing, report the number of students exempted for other reasons by grade and specific reason. |  |  |  |  |  |  |  |  |  |

| SECTION F. PERFORMANCE OF STUDENTS WITH DISABILITIES ON READING ASSESSMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | REGULAR ASSESSMENT ON GRADE LEVEL (9A) |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 | 2 | 3 | 4 |  |  |  |  |  |  |  |  |  |
| GRADE LEVEL | TEST NAME | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | 9A ROW TOTAL1 | Computed row Total | Computed row total should equal col 3 minus col 3B minus 3C |  |
| 3 | STAR-CST | 27008 | 10199 | 5905 | 2039 | 0 | 0 | 0 | 0 | 0 | 45151 | 45151 | 45151 |  |
| 4 | STAR-CST | 23965 | 12997 | 6789 | 5088 | 0 | 0 | 0 | 0 | 0 | 48839 | 48839 | 48839 |  |
| 5 | STAR-CST | 28676 | 12903 | 6000 | 3169 | 0 | 0 | 0 | 0 | 0 | 50748 | 50748 | 50748 |  |
| 6 | STAR-CST | 30141 | 10792 | 4563 | 2332 | 0 | 0 | 0 | 0 | 0 | 47828 | 47828 | 47828 |  |
| 7 | STAR-CST | 29688 | 9770 | 4482 | 1433 | 0 | 0 | 0 | 0 | 0 | 45373 | 45373 | 45373 |  |
| 8 | STAR-CST | 29100 | 9494 | 3231 | 1300 | 0 | 0 | 0 | 0 | 0 | 43125 | 43125 | 43125 |  |
| H SCH: 10 | CAHSEE | 26253 | 9230 | 2935 | 1198 | 0 | 0 | 0 | 0 | 0 | 39616 | 39616 | 39616 |  |
| LOWEST ACHIEVEMENT LEVEL CONSIDERED PROFICIENT: 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 The total number of students reported by achievement level in 9A is to equal the number reported in column 3 minus the number reported in columns 3B and 3C. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 15 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION F. PERFORMANCE OF STUDENTS WITH DISABILITIES ON READING ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ALTERNATE ASSESSMENT ON GRADE LEVEL STANDARDS (9B) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 |  | 2 |  | 3 |  | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRADE LEVEL | TEST NAME |  | Achievement Level |  | Achievement Level |  | Achievement Level |  | Achievement Level |  | Achievement Level |  | Achievement Level |  |  | Achievement Level |  |  | Achievement Level |  |  | Achievement Level |  | 9B ROW TOTAL1 | Computed row Total | Column 4A - column 4D should be less than or equal to computed total |  | Column 4A should be greater than or equal to computed total |
| 3 | CAPA |  | 474 |  | 784 |  | 1374 |  | 1742 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 4374 | 4374 | 4374 |  | 4374 |
| 4 | CAPA |  | 946 |  | 629 |  | 1116 |  | 1556 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 4247 | 4247 | 4247 |  | 4247 |
| 5 | CAPA |  | 810 |  | 558 |  | 1047 |  | 1688 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 4103 | 4103 | 4103 |  | 4103 |
| 6 | CAPA |  | 1135 |  | 687 |  | 1240 |  | 1251 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 4313 | 4313 | 4313 |  | 4313 |
| 7 | CAPA |  | 1042 |  | 675 |  | 1176 |  | 1574 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 4467 | 4467 | 4467 |  | 4467 |
| 8 | CAPA |  | 930 |  | 585 |  | 1219 |  | 1753 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 4487 | 4487 | 4487 |  | 4487 |
| HSCH : 10 | CAPA |  | 852 |  | 642 |  | 997 |  | 1686 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4177 | 4177 | 4177 |  | 4177 |
| LOWEST ACHIEVEMENT LEVEL CONSIDERED PROFICIENT: 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 The total number of students reported by achievement level in 9B is equal to the number reported in Column 4A minus that portion of 4D that refers to invalid results from assessments scored against grade level achievement standards. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 16 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 17 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

| SECTION F. PERFORMANCE OF STUDENTS WITH DISABILITIES ON READING ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ALTERNATE ASSESSMENT SCORED AGAINST ALTERNATE STANDARDS (9C) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRADE LEVEL | TEST NAME | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | Achievement Level | 9C ROW TOTAL2 |  | Computed row Total | (Column 4B - Column 4D)1 should be equal to or less than the computed total | (Column 4B - Column 4D)1 should be greater than or equal to computed total | (Column 4A + Column 4B - Column 4D)1 should be equal totals for column 9B plus 9C |
| 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4374 |
| 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4247 |
| 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4103 |
| 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4313 |
| 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4467 |
| 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4487 |
| HSCH : 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4177 |
| LOWEST ACHIEVEMENT LEVEL CONSIDERED PROFICIENT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 Include all students whose assessment counted in the lowest achievement level because of the NCLB 1% cap. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 The total number of students reported by achievement level in 9C is to equal the number reported in column 4B minus that portion of 4D that refers to invalid results from assessments scored against alternate achievement standards. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| SECTION F. PERFORMANCE OF STUDENTS WITH DISABILITIES ON READING ASSESSMENT (CONTINUED) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| GRADE LEVEL |  | TOTAL FOR COLUMN 9A (ON PAGE 15) | TOTAL FOR COLUMN 9B (ON PAGE 16) | TOTAL FOR COLUMN 9C (ON PAGE 17) | NO VALID SCORE2 (10) | TOTAL3 (11) | Sum of Column 3 through column 8 | Number reported in col 1, Section A |
| 3 |  | 45151 | 4374 | 0 | 2665 | 52190 | 52190 | 52190 |
| 4 |  | 48839 | 4247 | 0 | 3018 | 56104 | 56104 | 56104 |
| 5 |  | 50748 | 4103 | 0 | 2925 | 57776 | 57776 | 57776 |
| 6 |  | 47828 | 4313 | 0 | 2729 | 54870 | 54870 | 54870 |
| 7 |  | 45373 | 4467 | 0 | 2448 | 52288 | 52288 | 52288 |
| 8 |  | 43125 | 4487 | 0 | 2462 | 50074 | 50074 | 50074 |
| HSCH : | 10 | 39616 | 4177 | 0 | 4979 | 48772 | 48772 | 48772 |
| 1 STATES SHOULD NOT REPORT DATA ON THIS PAGE. THESE DATA WILL BE CALCULATED FROM THE REPORTED DATA AFTER THE COUNTS ARE SUBMITTED. PLEASE REVIEW FOR ERRORS. |  |  |  |  |  |  |  |  |
| 2 Column 10 is calculated by summing the numbers reported in column 3C plus column 4D plus column 5 plus column 6 plus column 7 plus column 8. |  |  |  |  |  |  |  |  |
| 3 Column 11 should equal the number of students with IEPs reported in column 1 of Section A. If the number of students is not the same, provide an explanation. Column 11 should always equal the sum of the number of students reported in columns 3 plus column 4 plus column 5 plus column 6 plus column 7 plus column 8. |  |  |  |  |  |  |  |  |

| U.S. DEPARTMENT OF EDUCATION |  | PAGE 18 OF 18 |
| --- | --- | --- |
| OFFICE OF SPECIAL EDUCATION | TABLE 6 |  |
| AND REHABILITATIVE SERVICES |  | OMB NO. 1820-0659 |
| OFFICE OF SPECIAL EDUCATION | REPORT OF THE PARTICIPATION AND PERFORMANCE OF STUDENTS WITH DISABILITIES ON STATE |  |
| PROGRAMS | ASSESSMENTS BY CONTENT AREA, GRADE, AND TYPE OF ASSESSMENT | FORM EXPIRES: 09/30/2007 |

Monitoring Priority: FAPE in the LRE

Indicator 4A:  Rates of suspension and expulsion:  Percent of districts identified by the State as having a significant discrepancy in the rates of suspensions and expulsions of children with disabilities for greater than 10 days in a school year.

Indicator 4B:  This measure is not required to be reported for the FFY 2006 APR as per Instructions for the FFY 2006 SPP/APR

Measurement: Percent = [(# of districts identified by the State as having significant discrepancies in the rates of suspensions and expulsions of children with disabilities for greater than 10 days in a school year) divided by the (# of districts in the State)] times 100. A district has a significant discrepancy when the rate of suspensions and expulsions of children with disabilities for greater than 10 days in a school year exceeds one percent.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | No more than 10.4 percent of districts will have rates of suspensions and expulsions of children with disabilities for greater than 10 days in a school year that exceed one percent. |

Actual Target Data for 2006:

Indicator 4A: 10.3% of districts have an overall suspension or expulsion rate greater than one percent.

Calculation:  88 / 852 *100 = 10.3 %

Indicator 4B: The measure is not reported this year as per Instructions for the FFY 2006 SPP/APR

Percents are not calculated for districts of residence reporting fewer than 20 students receiving special education services. Districts large enough to be calculated were considered to have met the target if fewer than two students were suspended or expelled for more than ten days.

The percent of districts that have an overall suspension or expulsion rate greater than one percent is intended to decrease over the years. The 10.3 percent of districts that have an overall suspension or expulsion rate greater than one percent in 2006-2007 is better than the target value of 10.4. The 2006-2007 result is a decrease of 7.6 percentage points from the 17.9 percent reported for 2005-2006.

Of the 852 districts with a population of students receiving special education large enough to calculate (N>19), 764 districts met the target of not more than one percent of students ages 3 through 22 suspended or expelled for more than 10 days during the 2006-2007 school year. Statewide, 4,528 students were suspended or expelled for more than ten days, 0.6 percent of the total population of 819,954 students served during 2006-2007. There is no substantial relationship between the number of students receiving special education in a district and the percent suspended or expelled for more than 10 days. There is a modest variation among the major regions in the state. The central region has the highest (13.7) percent of districts over the 1.0 percent level; the northern region the lowest (7.4 percent). At 9.6%, the southern region is just below the overall state figure of 10.3 percent.

There is considerable variation in suspension and expulsion rates when examined both by race and ethnic categories and by gender. At 1.3 percent, African American students are 2.4 times as likely to be suspended or expelled for more than 10 days as are all students; at 0.2 percent, Asian students are least likely to be suspended or expelled. More males (0.7 percent) are suspended or expelled than are females (0.2 percent). Among males, African American students have the highest rate of suspension or expulsion (1.6 percent); the rate is lowest for Asian males (0.3 percent). Among females, African American students have the highest rate of suspension or expulsion (0.8 percent); the rate is lowest for Asian females (0.1 percent).

Rates of suspension and expulsion vary among the disability categories. Students with Emotional Disturbance have the highest rate (1.9 percent), followed by students with a Specific Learning Disability (0.8 percent) and students with Other Health Impairment and those with Traumatic Brain Injury (each at 0.7 percent).

Monitoring Findings in 2006-07 Appendix 1 contains a list of items tested for reporting in 2006-07. Unlike prior years (when a low key performance indicator triggered a special review of discipline), monitoring items related to IEP development, suspension and expulsion, behavior intervention and procedural safeguards were included in all Verification and Special Education Self Reviews initiated in 2006-07. As a result, there was an overall increase in the number of findings over 2005-06. In 2006-07 there were four systemic findings reported to four LEAs and 225 student level findings reported to 42 LEAs. All have correction dates in 2007-08.

Correction of Monitoring Findings Reported in 2005-06 Appendix 1 contains a list of the items tested for reporting. In 2005-06, there were 5 systemic findings reported for 5 LEAs and 25 student level findings reported for 14 LEAs. All of the systemic findings are closed and all but three of the student level findings are closed. The three complaints are still open pending completion of compensatory services.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

The following improvement activities were completed in 2006-07:

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Provide Building Effective Schools Together (BEST) positive behavioral supports program training and technical assistance focused on decreasing dropout rates. | 2005-June 30, 2011 Fall and Spring | Contractor, CDE and LEA Staff Type: Special Project Training and Technical Assistance |

In addition, in the California Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

In its FFY 2006 APR, the State must describe the review, and if appropriate revision, of policies, procedures, and practices relating to the development and implementation of IEPs, the use of positive behavioral interventions and supports, and procedural safeguards to ensure compliance with the IDEA for: (1) the LEAs identified as having significant discrepancies in the FFY 2005 APR; and (2) the LEAs identified as having significant discrepancies in the FFY 2006 APR.

As noted above, all Verification and Special Education Self Reviews included review of policies, procedures and practices in 2006-07 using the items found in Appendix 1. All districts found to have noncompliant findings at the student and district level have corrective action plans specifying what must be done to correct the identified noncompliance. In addition, a special self-review of districts below the benchmark in Indicator 4.A. and determined to have disproportionate representation as defined in Indicator 4.B. in 2005-06 was conducted in the fall of 2007. A copy of the Self Review instrument may be found in Appendix 2. Based on the self review, all districts found to have noncompliance related to policies; procedures and practices related to discipline will have a corrective action plan and will correct the noncompliance within one year of identification.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2007 (2007-08): [If applicable]

| CONTINUING ACTIVITIES |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Timeline |  |  | Resources |
| Provide technical assistance on reinventing high school. | Ongoing |  |  | CDE Staff |
| Provide technical assistance to schools focused on the implementation of reform programs to high poverty. |  | Ongoing | CDE Staff and contractors |  |

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| CDE will work with SELPAs, LEAs and County Offices of Education to clarify responsibilities and improve behavior emergency and other behavioral incident reporting. | July 2007 – July 2008 | CDE Staff |
| CDE will work with SELPAs, LEAs and County Offices of Education to update and improve monitoring items and instruments for reviewing policies, practices and procedures related to this indicator. | January 2008 – April 2008 | CDE Staff and contractors |

Appendix 1

Behavior and Discipline Items tested for reporting in 2005-06 and 2006-07

| Item No | Compliance Test |
| --- | --- |
| 2-5-3.1 | Does the functional analysis assessment include a systematic observation of the targeted behavior? |
| 2-5-3.4 | Does the functional analysis assessment include an ecological analysis of the setting in which the behavior occurs most frequently? |
| 2-5-4.1 | Does the functional analysis assessment result in a written report that includes a description of the nature and severity of the targeted behaviors? |
| 2-5-3.2 | Does the functional analysis assessment include all of the required elements, including a systematic observation of the antecedent events? |
| 2-5-3.5 | Does the functional analysis assessment include a review of records for health and medical factors? |
| 2-5-4.2 | Does the functional analysis assessment result in a written report that includes a description of the targeted behaviors including baseline data, antecedents and consequences? |
| 2-5-4.3 | Does the functional analysis assessment result in a written report that includes a description of the rate of the alternative behaviors, their antecedents and consequences? |
| 3-4-1.9 | Does the IEP team include the case manager, for the behavior intervention plan whenever the team reviews the functional analysis assessment and develops the behavior intervention plan (Hughes Act), which becomes part of the IEP? |
| 2-2-2.6.4 | Is there evidence that the current assessment includes information about social, emotional, and behavioral status? |
| 3-4-1.2.1.1 | Does the general education teacher help decide the appropriate positive behavior interventions and supports, and other strategies for the student and supplementary aids and services and program modifications and support for school personnel? |
| 2-5-4.4 | Does the functional analysis assessment result in a written report that includes recommendations for consideration by the IEP team, which may include a proposed behavior plan? |
| 2-5-1 | Does the IEP team specify the development of a functional analysis behavior assessment, when it has been determined that other behavioral/instructional approaches specified in the student’s IEP have been ineffective? |
| 2-5-3.3 | Does the functional analysis assessment include a systematic observation and analysis of the consequences? |
| 4-3-4.1 | Is an interim alternative educational setting determined by the IEP team when there is a change in placement? |
| 4-3-3.6 | In making the manifestation determination, did the IEP team determine that the special education services, supplementary aids and services, and behavior intervention strategies were provided consistently with the student's IEP and placement? |
| 4-3-3.5 | In making the manifestation determination, did the IEP team determine that the student's IEP and placement were appropriate? |
| 4-3-3.3 | In making the manifestation determination, did the IEP team consider whether the disability impaired the student's ability to control the behavior that led to the disciplinary action? |
| 4-3-3.4 | In making the manifestation determination, did the IEP team consider all relevant information including evaluation and diagnostic results, parent information, observations of the student, and the student's IEP and placement? |
| 4-3-5.2 | If a parent received proper notice of the meeting, chooses not to participate in the IEP meeting or to consent to an extension beyond 20 consecutive school days, is the meeting conducted without the parent? |
| 4-3-9 | Are parents informed that they have the right to pursue a due process hearing if they disagree with the decisions of the IEP team regarding expulsion? |
| 4-3-10 | Is the expulsion hearing conducted only after the pre-expulsion assessment is completed and the IEP team convenes and makes the required findings? |
| 4-3-10.1 | Did the IEP team convene prior to the expulsion hearing and determine if the alleged misconduct was a manifestation of the student's disability? |
| 4-3-10.2 | Did the IEP team convene prior to the expulsion hearing and find that placement was appropriate? |
| 4-3-3.2 | In making the manifestation determination, did the IEP team consider whether the disability impaired the student's ability to understand the impact and consequences of the behavior in question? |
| 4-3-11 | Are relevant disciplinary procedures applicable to all children carried out only when it has been determined that the placement was appropriate and that the behavior was not a manifestation of the disability? |
| 4-3-5.1 | If a parent is unable to attend the IEP meeting, is a telephone conference used for the IEP meeting to consider expulsion? |
| 4-3-10.3 | Did the IEP team convene prior to the expulsion hearing and find that the behavior interventions described in the IEP were followed? |
| 4-3-6 | Is there a pre-expulsion assessment prior to the IEP meeting held to consider expulsion? |
| 4-3-3 | In making the manifestation determination, did the IEP team consider all required elements? |
| 4-3-2.4 | If disciplinary action changes a student’s placement for 10 days or more, does the student return to the pre disciplinary action placement unless a court order or parent permission has been obtained? |
| 4-3-2.3 | If disciplinary action is considered to change a student's placement for 10 days or more, are functional analysis assessments and behavioral plans developed to address the behavior that resulted in the suspension if such a plan is not already in place? |
| 4-3-2.2 | If disciplinary action is considered to change a student's placement for 10 school days or more, is the IEP meeting held before the 10th day of suspension to consider if the behavior was a manifestation of the student's disability? |
| 4-3-2.1 | If disciplinary action is considered to change a student’s placement for 10 days or more, are the parents notified on the same day this decision is made and given a copy of their rights or Notice of Procedural Safeguards? |
| 4-3-2 | If disciplinary action is considered to change a student’s placement for 10 days or more because the student has violated a rule or code of conduct applying to all students does the LEA follow all of the required procedures? |
| 4-3-1 | When a disciplinary action involving suspension or expulsion of more than 10 days in a school year occurs, is the student provided all IEP services on the 11th day? |
| 4-3-3.1 | In making the manifestation determination, did the IEP team consider whether the services included in the behavior intervention plan were consistent with the IEP? |

Appendix 2

Self Review Instrument

INSTRUCTIONS: DISPROPORTIONATE REPRESENTATION IN DISCIPLINARY ACTIONS

The review of SPPI 4B: Disproportionality - Suspension/Expulsion by Ethnic Category

- To conduct the Review of Policies and Procedures:

- Use the CDE provided protocol to conduct a review of the district’s Policies and Procedures relative to the suspension/expulsion of special education students.

- Conduct the examination of the district’s Policies and Procedures using the items listed under the heading Policies and Procedures.

- Mark each item reviewed as either Compliant or Non-Compliant depending on whether it is determined that there is or is not a Policy or Procedure that addresses that item.

- Please submit one (1) completed Policies and Procedures review protocol to CDE.

- To conduct the Practices Review:

- Use the CDE provided protocol to conduct a review of the district’s practices relative to the suspension/expulsion of special education students.

- Select a sample of fifteen (15) records of district special education students who have been suspended and/or expelled for 10 days or more.

- Using the CDE provided protocol, examine each student record and mark each item reviewed as either Compliant or Non-Compliant.

- For each reviewed record that has Non-Compliant findings, a separate form, STUDENT CORRECTIVE ACTION FORM, must be completed. The form identifies: the student by name; his/her date of birth; the item number found non-compliant; the finding made; the planned corrective action; and the date the correction was made.

- This form, if applicable, must be attached to each student’s review protocol. Please submit one review protocol for each student record reviewed – for a total of fifteen (15). Attach to each protocol, when there are non-compliant findings, a copy of the STUDENT CORRECTIVE ACTION FORM.

NOTE:  If the district conducted a Verification Review (VR) or a Special Education Self-Review (SESR) during 2006-07, this review does not need to be completed. Instead, please submit to CDE a signed Assurance statement that the review was completed and if Non-compliant issues were found that all corrections were made.

PLEASE NOTE THAT ALL DOCUMENTS MUST BE SUBMITTED TO CDE NO LATER THAN NOVEMBER 21, 2007.

| Item No | Compliance Test | Legal References | Compliant | Noncompliant |
| --- | --- | --- | --- | --- |
| Review of Policies and Procedures |  |  |  |  |
| Assessment |  |  |  |  |
| 2-5-1 | Do district policies and procedures include a provision that the IEP team must call for the development of a functional analysis behavior assessment, when it has been determined that other behavioral/instructional approaches specified in the student’s IEP have been ineffective? | EC 565235, CCR 3052(b). |  |  |
| 2-5-3.1 | Do district policies and procedures include a provision that the functional analysis assessment include a systematic observation of the targeted behavior? | EC 565235, CCR 3052(b). |  |  |
| 2-5-3.2 | Do district policies and procedures include a provision that the functional analysis assessment include all of the required elements, including a systematic observation of the antecedent events? | EC 565235, CCR 3052(b). |  |  |
| 2-5-3.3 | Do district policies and procedures include a provision that the functional analysis assessment include a systematic observation and analysis of the consequences? | EC 565235, CCR 3052(b). |  |  |
| 2-5-3.4 | Do district policies and procedures include a provision that the functional analysis assessment include an ecological analysis of the setting in which the behavior occurs most frequently? | 5 CCR 3052(b). |  |  |
| 2-5-3.5 | Do district policies and procedures include a provision that the functional analysis assessment include a review of records for health and medical factors? | 5 CCR 3052(b). |  |  |
| 2-5-4.1 | Do district policies and procedures include a provision that the functional analysis assessment result in a written report that includes a description of the nature and severity of the targeted behaviors? | 5 CCR 3052(b). |  |  |
| 2-5-4.2 | Do district policies and procedures include a provision that the functional analysis assessment result in a written report that includes a description of the targeted behaviors including baseline data, antecedents and consequences? | 5 CCR 3052(b). |  |  |
| 2-5-4.3 | Do district policies and procedures include a provision that the functional analysis assessment result in a written report that includes a description of the rate of the alternative behaviors, their antecedents and consequences? | 5 CCR 3052(b). |  |  |
| 2-5-4.4 | Do district policies and procedures include a provision that the functional analysis assessment result in a written report that includes recommendations for consideration by the IEP team, which may include a proposed behavior plan? | 5 CCR 3052(b). |  |  |
| IEP team |  |  |  |  |
| 3-4-1.2.1.1 | Do district policies and procedures include a provision that the general education teacher help decide the appropriate positive behavior interventions and supports, and other strategies for the student and supplementary aids and services and program modifications and support for school personnel? | 20 USC 1414(d)(3)(C), 34 CFR 300.324 (a)(3)(i), EC 56341.1(b)(1). |  |  |
| 3-4-1.9 | Do district policies and procedures include a provision that the IEP team include the case manager, for the behavior intervention plan whenever the team reviews the functional analysis assessment and develops the behavior intervention plan (Hughes Act), which becomes part of the IEP? | 5CCR 3052(c). |  |  |
| IEP - Additional Requirements |  |  |  |  |
| 4-3-1 | Do district policies and procedures include a provision that when a disciplinary action involving suspension or expulsion of more than 10 days in a school year occurs, that the student is provided all IEP services on the 11th day? | 20 USC 1415(k)(1)(D), 34 CFR 300.534(d). |  |  |
| 4-3-2 | Do district policies and procedures include a provision that if disciplinary action is considered to change a student’s placement for 10 days or more because the student has violated a rule or code of conduct applying to all students that the LEA follow all of the required procedures? | 20 USC 1415(k)(1)(C), 34 CFR 303.530. |  |  |
| 4-3-2.1 | Do district policies and procedures include a provision that if disciplinary action is considered to change a student’s placement for 10 days or more, that the parents are notified on the same day this decision is made and given a copy of their rights or Notice of Procedural Safeguards? | 1415(k)(1)(H), 34 CFR 303.530(h). |  |  |
| 4-3-2.2 | Do district policies and procedures include a provision that if disciplinary action is considered to change a student's placement for 10 school days or more, that the IEP meeting is held before the 10th day of suspension to consider if the behavior was a manifestation of the student's disability? | 20 USC 1415(k)(1)(E), 34 CFR 300.530(e). |  |  |
| 4-3-2.3 | Do district policies and procedures include a provision that if disciplinary action is considered to change a student's placement for 10 days or more, that functional analysis assessments and behavioral plans are developed to address the behavior that resulted in the suspension if such a plan is not already in place? | 20 USC 1415(k)(1)(F)(i), 34 CFR 300.530(f). |  |  |
| 4-3-2.4 | Do district policies and procedures include a provision that if disciplinary action changes a student’s placement for 10 days or more, that the student returns to the pre disciplinary action placement unless a court order or parent permission has been obtained? | 20 USC 1415 (k)(1)(F)(iii), 34 CFR 300.121, 34 CFR 300.530(f)(2). |  |  |
| 4-3-3 | Do district policies and procedures include a provision that in making the manifestation determination, that the IEP team considers all required elements? | 20 USC 1415 (k)(1)(F), 34 CFR 300.530(f)(2). |  |  |
| 4-3-3.1 | Do district policies and procedures include a provision that in making the manifestation determination, that the IEP team considers whether the services included in the behavior intervention plan were consistent with the IEP? | 20 USC 1415(k)(1)(E)(ii), 34 CFR 300.530(e)(1)(ii). |  |  |
| 4-3-3.2 | Do district policies and procedures include a provision that in making the manifestation determination, that the IEP team considers whether the disability impaired the student's ability to understand the impact and consequences of the behavior in question? | 20 USC 1415(k)(1)(E)(i)(I), 34 CFR 300.530(e)(1)(i). |  |  |
| 4-3-3.3 | Do district policies and procedures include a provision that in making the manifestation determination, that the IEP team considers whether the disability impaired the student's ability to control the behavior that led to the disciplinary action? | 20 USC 1415(k)(1)(E)(i)(I), 34 CFR 300.530(e)(1)(i). |  |  |
| 4-3-3.4 | Do district policies and procedures include a provision that in making the manifestation determination, that the IEP team considers all relevant information including evaluation and diagnostic results, parent information, observations of the student, and the student's IEP and placement? | 20 USC 1415(k)(1)(E)(i), 34 CFR 300.530(e)(1)(i). |  |  |
| 4-3-3.5 | Do district policies and procedures include a provision that in making the manifestation determination, that the IEP team determines that the student's IEP and placement were appropriate? | 20 USC 1415(k)(1)(E)(i) |  |  |
| 4-3-3.6 | Do district policies and procedures include a provision that in making the manifestation determination, that the IEP team determines that the special education services, supplementary aids and services, and behavior intervention strategies were provided consistently with the student's IEP and placement? | 20 USC 1415(k)(1)(E)(i)(II), 34 CFR 300.530(e)(1)(ii). |  |  |
| 4-3-4.1 | Do district policies and procedures include a provision that there is an interim alternative educational setting determined by the IEP team when there is a change in placement? | 20 USC 1415(k)(2), 34 CFR 300.531. |  |  |
| 4-3-5 | Does the district implement appropriate policies and procedures to ensure parent participation? | Honing v Doe |  |  |
| 4-3-5.1 | Do district policies and procedures include a provision that if a parent is unable to attend the IEP meeting, there is a telephone conference used for the IEP meeting to consider expulsion? | 34 CFR 300.345, 34 CFR 300.322. |  |  |
| 4-3-6 | Do district policies and procedures include a provision that there is a pre-expulsion assessment prior to the IEP meeting held to consider expulsion? | 1415(k)(1)(E)(i)&(ii), 34 CFR 300.530(f), 30 EC 48915.5. (a). |  |  |
| 4-3-9 | Do district policies and procedures include a provision that parents are informed that they have the right to pursue a due process hearing if they disagree with the decisions of the IEP team regarding expulsion? | 20 USC 1415 (c)(1)(C), 34 CFR 300.351(a) and 34 CFR 300.507, 30 EC 48915.5. (a). |  |  |
| 4-3-10 | Do district policies and procedures include a provision that the expulsion hearing is conducted only after the pre-expulsion assessment is completed and the IEP team convenes and makes the required findings? | 20 USC 1415(k)(1)(E)(i), 34CFR 300.350(e)(1), 30 EC 48915.5. (a). |  |  |
| 4-3-10.1 | Do district policies and procedures include a provision that the IEP team convenes prior to the expulsion hearing and determine if the alleged misconduct was a manifestation of the student's disability? | 21 USC 1415(k)(1)(E)(i), 34 CFR 300.350(e)(1), 30 EC 48915.5. (a). |  |  |
| 4-3-10.2 | Do district policies and procedures include a provision that the IEP team convenes prior to the expulsion hearing and find that placement was appropriate? | 22 USC 1415(k)(1)(E), 34 CFR 300.350(e)(1), 30 EC 48915.5. (a). |  |  |
| 4-3-10.3 | Do district policies and procedures include a provision that the IEP team convenes prior to the expulsion hearing and find that the behavior interventions described in the IEP were followed? | 23 USC 1415(k)(1)(F)(i) and (ii), 34 CFR 300.350(e)(1), 30 EC 48915.5. (a). |  |  |
| 4-3-11 | Do district policies and procedures include a provision that relevant disciplinary procedures applicable to all children are carried out only when it has been determined that the placement was appropriate and that the behavior was not a manifestation of the disability? | 20 USC 1415(k)(5)(A)(1)(A) and (B) and (C), 34 CFR 300.350(h), 30 EC 48915.5. (a). |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Review of Practices |  |  |  |  |  |  |  |
| Assessment |  |  |  |  |  |  |  |
| 2-2-2.6.4 | Is there evidence that the current assessment includes information about social, emotional, and behavioral status? | As included in Assessment Plan. | Social, emotional, behavior status checked on the Assessment Plan as an area of assessment and addressed in the Assessment Report; addressed on the IEP. | 34 CFR 300.304(c)(4), 30 EC 56320(f). |  |  |  |
| 2-5-1 | Does the IEP team specify the development of a functional analysis behavior assessment, when it has been determined that other behavioral/instructional approaches specified in the student’s IEP have been ineffective? | If there is indication that the behavioral/instructional approaches have been ineffective, student records must include documentation that the IEP team specified the development of a functional analysis evaluation. | Look in the present performance and/or other notes in the IEP to determine if the IEP team felt the behavioral/ instructional approaches in the IEP have been effective. Also check Assessment Reports. Look for a functional analysis evaluation. | EC 565235, CCR 3052(b). |  |  |  |
| 2-5-3.1 | Does the functional analysis assessment include a systematic observation of the targeted behavior? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | EC 565235, CCR 3052(b). |  |  |  |
| 2-5-3.2 | Does the functional analysis assessment include all of the required elements, including a systematic observation of the antecedent events? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | EC 565235, CCR 3052(b). |  |  |  |
| 2-5-3.3 | Does the functional analysis assessment include a systematic observation and analysis of the consequences? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | EC 565235, CCR 3052(b). |  |  |  |
| 2-5-3.4 | Does the functional analysis assessment include an ecological analysis of the setting in which the behavior occurs most frequently? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | 5 CCR 3052(b). |  |  |  |
| 2-5-3.5 | Does the functional analysis assessment include a review of records for health and medical factors? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | 5 CCR 3052(b). |  |  |  |
| 2-5-4.1 | Does the functional analysis assessment result in a written report that includes a description of the nature and severity of the targeted behaviors? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | 5 CCR 3052(b). |  |  |  |
| 2-5-4.2 | Does the functional analysis assessment result in a written report that includes a description of the targeted behaviors including baseline data, antecedents and consequences? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | 5 CCR 3052(b). |  |  |  |
| 2-5-4.3 | Does the functional analysis assessment result in a written report that includes a description of the rate of the alternative behaviors, their antecedents and consequences? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | 5 CCR 3052(b). |  |  |  |
| 2-5-4.4 | Does the functional analysis assessment result in a written report that includes recommendations for consideration by the IEP team, which may include a proposed behavior plan? | If a functional analysis was completed, student records must include documentation. | Review functional analysis Assessment Report. | 5 CCR 3052(b). |  |  |  |
| IEP team |  |  |  |  |  |  |  |
| 3-4-1.2.1.1 | Does the general education teacher help decide the appropriate positive behavior interventions and supports, and other strategies for the student and supplementary aids and services and program modifications and support for school personnel? | If appropriate, there is evidence that the general education teacher participated in considerations of appropriate behavior interventions for the student. | Look in the student record for evidence that the student's general education teacher participated in the development of appropriate positive behavior interventions and strategies. Check the IEP to see if the general education teacher attended the IEP meeting. | 20 USC 1414(d)(3)(C), 34 CFR 300.324 (a)(3)(i), EC 56341.1(b)(1). |  |  |  |
| 3-4-1.9 | Does the IEP team include the case manager, for the behavior intervention plan whenever the team reviews the functional analysis assessment and develops the behavior intervention plan (Hughes Act), which becomes part of the IEP? | If the child has a behavior intervention plan, the IEP team must include the case manager. | If there is a written notice of the IEP team meeting, check to see if it includes an intent to address the student's behavior; develop a behavior intervention plan and meet with the child's case manager. Check the IEP to determine if the behavior intervention includes the name of a case manager. | 5CCR 3052(c). |  |  |  |
| IEP - Additional Requirements |  |  |  |  |  |  |  |
| 4-3-1 | When a disciplinary action involving suspension or expulsion of more than 10 days in a school year occurs, is the student provided all IEP services on the 11th day? | Must be documented in student record. | Check the student record for evidence of notices or information provided to the student’s parents regarding arrangements to continue services. | 20 USC 1415(k)(1)(D), 34 CFR 300.534(d). |  |  |  |
| 4-3-2 | If disciplinary action is considered to change a student’s placement for 10 days or more because the student has violated a rule or code of conduct applying to all students does the LEA follow all of the required procedures? |  |  | 20 USC 1415(k)(1)(C), 34 CFR 303.530. |  |  |  |
| 4-3-2.1 | If disciplinary action is considered to change a student’s placement for 10 days or more, are the parents notified on the same day this decision is made and given a copy of their rights or Notice of Procedural Safeguards? | The district must have evidence that the parents were notified and given a copy of their rights. | Look for evidence in the student record. Check for notifications or contacts with the parents. | 1415(k)(1)(H), 34 CFR 303.530(h). |  |  |  |
| 4-3-2.2 | If disciplinary action is considered to change a student's placement for 10 school days or more, is the IEP meeting held before the 10th day of suspension to consider if the behavior was a manifestation of the student's disability? | The district must have evidence that the IEP meeting was held within 10 days of the student's suspension. | Check for an IEP and look at the date. Is the date within 10 days of the suspension? | 20 USC 1415(k)(1)(E), 34 CFR 300.530(e). |  |  |  |
| 4-3-2.3 | If disciplinary action is considered to change a student's placement for 10 days or more, are functional analysis assessments and behavioral plans developed to address the behavior that resulted in the suspension if such a plan is not already in place? | The district must have evidence of a behavioral assessment and behavior plan. | Must be included in the student record. Look for a copy of the functional assessment and behavior plan. | 20 USC 1415(k)(1)(F)(i), 34 CFR 300.530(f). |  |  |  |
| 4-3-2.4 | If disciplinary action changes a student’s placement for 10 days or more, does the student return to the pre disciplinary action placement unless a court order or parent permission has been obtained? | Must be documented in student record. | Review district policies and procedures. Review district records of suspension and expulsion. Review student record. | 20 USC 1415 (k)(1)(F)(iii), 34 CFR 300.121, 34 CFR 300.530(f)(2). |  |  |  |
| 4-3-3 | In making the manifestation determination, did the IEP team consider all required elements? |  |  | 20 USC 1415 (k)(1)(F), 34 CFR 300.530(f)(2). |  |  |  |
| 4-3-3.1 | In making the manifestation determination, did the IEP team consider whether the services included in the behavior intervention plan were consistent with the IEP? | There is evidence of the IEP team meeting to consider the manifestation determination. | Look for evidence that the IEP team considered whether services, including the behavior intervention strategies, were provided consistent with the IEP. | 20 USC 1415(k)(1)(E)(ii), 34 CFR 300.530(e)(1)(ii). |  |  |  |
| 4-3-3.2 | In making the manifestation determination, did the IEP team consider whether the disability impaired the student's ability to understand the impact and consequences of the behavior in question? | There is evidence of the IEP team meeting to consider the manifestation determination. | The IEP team must give consideration to whether the child's disability may have impaired the child's ability to understand the consequences of the subject behavior. Look for evaluation and diagnostic results, information supplied by parents, observations | 20 USC 1415(k)(1)(E)(i)(I), 34 CFR 300.530(e)(1)(i). |  |  |  |
| 4-3-3.3 | In making the manifestation determination, did the IEP team consider whether the disability impaired the student's ability to control the behavior that led to the disciplinary action? | There is evidence of the IEP team meeting to consider the manifestation determination. | Look for an Assessment Report or other written materials. | 20 USC 1415(k)(1)(E)(i)(I), 34 CFR 300.530(e)(1)(i) . |  |  |  |
| 4-3-3.4 | In making the manifestation determination, did the IEP team consider all relevant information including evaluation and diagnostic results, parent information, observations of the student, and the student's IEP and placement? | There is evidence of the IEP team meeting to consider the manifestation determination. | Look for an Assessment Report, notices to parents, information received from parents, or other related materials. | 20 USC 1415(k)(1)(E)(i), 34 CFR 300.530(e)(1)(i). |  |  |  |
| 4-3-3.5 | In making the manifestation determination, did the IEP team determine that the student's IEP and placement were appropriate? | There is evidence of the IEP team meeting to consider the manifestation determination. | Review district records of suspension and expulsion. Review student record. | 20 USC 1415(k)(1)(E)(i) |  |  |  |
| 4-3-3.6 | In making the manifestation determination, did the IEP team determine that the special education services, supplementary aids and services, and behavior intervention strategies were provided consistently with the student's IEP and placement? | There is evidence of the IEP team meeting to consider the manifestation determination. | Did district staff determine that services were provided consistently? Check IEP and notes, reports in student record. | 20 USC 1415(k)(1)(E)(i)(II), 34 CFR 300.530(e)(1)(ii). |  |  |  |
| 4-3-4.1 | Is an interim alternative educational setting determined by the IEP team when there is a change in placement? | The interim alternative educational setting is determined by the IEP team. | Review documentation in selected IEPs. Interview staff and administrators. Review policies and procedures. | 20 USC 1415(k)(2), 34 CFR 300.531. |  |  |  |
| 4-3-5 | Does the district implement appropriate policies and procedures to ensure parent participation? |  | Review district policies and procedures. Review district records of suspension and expulsion. Review student record. | Honing v Doe |  |  |  |
| 4-3-5.1 | If a parent is unable to attend the IEP meeting, is a telephone conference used for the IEP meeting to consider expulsion? | Must be documented in policies and procedures. Must be documented in student record. | Review district policies and procedures. Review district records of suspension and expulsion. Review student record. | 34 CFR 300.345, 34 CFR 300.322. |  |  |  |
| 4-3-5.2 | If a parent received proper notice of the meeting, chooses not to participate in the IEP meeting or to consent to an extension beyond 20 consecutive school days, is the meeting conducted without the parent? | Must be documented in policies and procedures. Must be documented in student record. | Review district policies and procedures. Review district records of suspension and expulsion. Review student record. | California and 20 USC 1414(f), 34 CFR 300.326, 30 EC 48915(d). |  |  |  |
| 4-3-6 | Is there a pre-expulsion assessment prior to the IEP meeting held to consider expulsion? | There is evidence of a pre-expulsion assessment in the student record. | Did the IEP team review the IEP, Assessment Reports, health records, and school discipline records? | 1415(k)(1)(E)(i)&(ii), 34 CFR 300.530(f), 30 EC 48915.5. (a). |  |  |  |
| 4-3-9 | Are parents informed that they have the right to pursue a due process hearing if they disagree with the decisions of the IEP team regarding expulsion? | The district must inform parents of their right to a due process hearing. | Look for a notice or copy of a parent rights document. | 20 USC 1415 (c)(1)(C), 34 CFR 300.351(a) and 34 CFR 300.507, 30 EC 48915.5. (a). |  |  |  |
| 4-3-10 | Is the expulsion hearing conducted only after the pre-expulsion assessment is completed and the IEP team convenes and makes the required findings? | The district must have evidence of their pre-expulsion assessment and an IEP team meeting. | Look for the IEP and related assessment materials and other documents. | 20 USC 1415(k)(1)(E)(i), 34CFR 300.350(e)(1), 30 EC 48915.5. (a). |  |  |  |
| 4-3-10.1 | Did the IEP team convene prior to the expulsion hearing and determine if the alleged misconduct was a manifestation of the student's disability? | The district must have evidence of their pre-expulsion assessment and an IEP team meeting. | Look for the IEP and related assessment materials and other documents. | 21 USC 1415(k)(1)(E)(i), 34 CFR 300.350(e)(1), 30 EC 48915.5. (a). |  |  |  |
| 4-3-10.2 | Did the IEP team convene prior to the expulsion hearing and find that placement was appropriate? | The district must have evidence of their pre-expulsion assessment and an IEP team meeting. | Look for the IEP and related assessment materials and other documents. | 22 USC 1415(k)(1)(E), 34 CFR 300.350(e)(1), 30 EC 48915.5. (a). |  |  |  |
| 4-3-10.3 | Did the IEP team convene prior to the expulsion hearing and find that the behavior interventions described in the IEP were followed? | The district must have evidence of their pre-expulsion assessment and an IEP team meeting. | Look for the IEP and related assessment materials and other documents. | 23 USC 1415(k)(1)(F)(i) and (ii), 34 CFR 300.350(e)(1), 30 EC 48915.5. (a). |  |  |  |
| 4-3-11 | Are relevant disciplinary procedures applicable to all children carried out only when it has been determined that the placement was appropriate and that the behavior was not a manifestation of the disability? | The district must have evidence that the IEP team determined the placement was appropriate. | Look for a report or other written materials that summarize the findings of the determination review. | 20 USC 1415(k)(5)(A)(1)(A) and (B) and (C), 34 CFR 300.350(h), 30 EC 48915.5. (a). |  |  |  |

Monitoring Priority: FAPE in the LRE

Indicator 5:  Percent of children with IEPs aged 6 through 21:

- Removed from regular class less than 21% of the day;

- Removed from regular class greater than 60% of the day; or

- Served in public or private separate schools, residential placements, or homebound or hospital placements.

(20 U.S.C. 1416(a)(3)(A))

Measurement: - Percent = [(# of children with IEPs removed from regular class less than 21% of the day) divided by the (total # of students aged 6 through 21 with IEPs)] times 100. - Percent = [(# of children with IEPs removed from regular class greater than 60% of the day) divided by the (total # of students aged 6 through 21 with IEPs)] times 100. - Percent = [(# of children with IEPs served in public or private separate schools, residential placements, or homebound or hospital placements) divided by the (total # of students aged 6 through 21 with IEPs)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | - 53 percent or more of students will be removed from regular class less than 21 percent of the day; - No more than 23 percent will be removed from regular class more than 60 percent of the day; and - No more than 4.2 percent are served in public or private separate schools, residential placements, or homebound or hospital placements. |

Actual Target Data for (FFY 2006):

Table 5a depicts the number and percent of students, aged 6 through 21 with IEPs, who receive special education and related services in various settings:

Table 5a

Number and Percent of Students Served in Various Settings

| Setting | No. of Students | Percent of Students | 2006 Target |
| --- | --- | --- | --- |
| 5 A. Removed from regular class less than 21 percent of the day | 300,051 | 49.5% | 53% or more |
| 5 B. Removed from regular class greater than 60% of the day | 155,153 | 25.6% | No more than 23% |
| 5 C. Served in public or private separate schools, residential placements, or homebound or hospital placements | 25,025 | 4.1% | No more than 4.2% |

- 49.5 percent were removed from regular class less than 21 percent of the day;

Calculation: 300,051 / 606,037 *100 = 49.5 %

- 25.6 percent were removed from regular class more than 60 percent of the day; and

Calculation: 155,153 / 606,037 *100 = 25.6%

- 4.1 percent were served in public or private separate schools, residential placements, or homebound or hospital placements

Calculation: 25,025 / 606,037 *100 = 4.1%

Statewide, two of the three targets were not met: the percent of students removed from regular class less than 21 percent of the day and the percent of students removed from regular class more than 60 percent of the day. The percent of students removed from regular class less than 21 percent of the day is a measure that is designed to increase, while the percent of students removed from regular class more than 60 percent of the day is intended to decrease over the years. The statewide percentage for removal less than 21 percent slipped 0.9 percent from the 51.3 percent reported for 2005-2006 to 49.5 percent, and fell short of the 53 percent target by 3.5 percentage points. The percentage for removal from regular class for more than 60 percent of the day slipped by 1.4 percent to 25.6 percent, not meeting the target of 23 percent by 2.6 percentage points.

The percent of students in separate facilities, a measure that is designed to decrease over time, progressed by 0.2 percent to 4.1 percent, better than the target of no more than 4.2 percent.

Of the 786 districts with values large enough to calculate, 525 (66.8%) districts met the target of under 21 percent out of regular class, 497 (63.2%) districts met the target for less than 60 percent out of regular class, and 640 (81.4%) districts met the target for students served in separate facilities. These districts were evenly represented geographically and on a size basis.

Most students are proportionately represented by ethnicity in each of the LRE levels. African American students are over represented in the 60 percent removal group. They are 14.9 percent of students removed 60 percent or more; compared to their 12.1 percent of their representation in the overall special education population. African Americans are also over represented among students who are served in separate facilities. They constitute 19.5 percent of the students served in separate facilities; compared to their 12.1 percent representation in the overall special education population.

By disability, students with Speech and Language Impairments, Other Health Impairments and Specific Learning Disabilities are proportionately represented in all three levels. Students with Hearing Impairments and Visual Impairments are adequately represented in the less than 21 percent removal group, but are overrepresented in the 60 percent removal and separate facility groups. Children with more severe disabilities are disproportionately represented across all LRE conditions – under represented in the less than 21 percent removal group and over represented in the 60 percent removal and separate facility groups. It should be noted that participation of children with low incidence and severe disabilities in special classes and separate facilities would be expected given the nature of their educational needs.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

As noted above, two of the three targets were not met: the percent of students removed from regular class less than 21 percent of the day and the percent of students removed from regular class more than 60 percent of the day. The percent of slippage (3.5% and 2.6%) represents a two year trend of falling short of the target measures. This slippage cannot be explained by changes in data collection, policy, funding or changes in personnel or the population of students served. It would appear that CDE needs to reverse this trend through increased attention in monitoring and through the addition of self improvement assessments and improvement planning for those LEAs falling below the established benchmarks.

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Provide specific training on LRE for County Offices of Education participating in the CDE District and Improvement Teams (DAIT) who work locally with districts in program improvement | 2006-07 | CDE Contractor w/West Ed, California Comprehensive Center Type: Monitoring –Training and Technical Assistance Project aligned to selected SPP Indicators and NCLB |
| data examination and visits on possible site selection demonstrating promising practices in LRE | Began 2006-07 | CDE Contractor w/West Ed, California Comprehensive Center Type: Monitoring –Training and Technical Assistance Project aligned to selected SPP Indicators and NCLB |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Continue implementation of the Facilitated Focused Monitoring Project including the “scaling up” focused monitoring work which contains targeted technical assistance around LRE in the context of improving academic outcomes for all students, including students with disabilities. | 2005-June 30, 2011 | CDE staff, Contractor Type: Monitoring –Training and Technical Assistance Project aligned to selected SPP Indicators |
| Using requirements of IDEA 2004, evidence-based research and state Board of Education adopted policy on LRE and state content and performance standards, conduct Regional and Statewide State Improvement Grant (SIG) Leadership Institutes as well as specialized technical assistance to assist schools staff and in implementing the LRE for students with disabilities as stated in their IEPs. | 2005-June 30, 2011 Fall and spring regional Annually for statewide | CDE staff, contractor Type: Special Project, Training and Technical Assistance |
| Implement the State Personnel Development Grant (SPDG) that provides training and technical assistance in scientifically-based research and instruction in the areas of literacy and behavior, as well as sustaining and promoting activities that foster special education/general education collaboration. | January-March 2007 and implementation of the new federal grant January 2008-2012. | State Personnel Development Grant (SPDG), United State Department of Education (USDOE), Office of Special Education Programs (OSEP) federal grant competition Type: Monitoring – Training and Technical Assistance Special Project aligned to SPP Indicators |
| Conduct activities related to parent involvement, Least Restrictive Environment (LRE) Response to Intervention (RtI), and Secondary Transition. | January-March 2007 and implementation of the new federal grant January 2008-2012. | CDE staff, contractor Type: General Supervision, Monitoring and Enforcement |
| Based on CDE data review from monitoring findings including CASEMIS information, determine needs for technical assistance regarding noncompliant findings, provide focused technical assistance to sites and LEAs regarding LRE | 2005-June 30, 2011 | CDE staff, contractor Type: General Supervision, Monitoring and Enforcement |

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Provide web-based IEP training module to emphasize how IEP teams can address standards based IEPs; Educational Benefit Processes to develop an IEP, IEP team decisions about student participation in state assessments and IEP team information about Least Restrictive Environment (LRE). | December 31, 2007 | CDE staff and California Comprehensive Center Type: Special Project of Training and Technical Assistance |
| Begin Preliminary development and implementation of training and technical assistance around several topics, including LRE with a Charter LEA participating in a CDE pilot project. | 2007-2010 Pilot timeline | CDE staff, contractor, SELPA Director Type: General Supervision, training and technical assistance special project |
| Participate in the development, implementation, and evaluation, including training and technical assistance regarding the LRE survey utilized in the CDE Program Improvement activities such as the Site Assistance Intervention Teams (SAIT) and District Assistance Intervention Teams (DAIT) for Program Improvement sites and districts under No Child Left Behind (NCLB). | 2005-June 30, 2011 | CDE staff, contractor, California Comprehensive Center Type: Statewide CDE Initiative to close the achievement gap for all subgroups including students with disabilities http://www.wested.org/cs/we/view/pj/204 |
| Develop and implement an LRE self assessment and improvement planning module in Verification and Self Review Software. | January 2008 – January 2009 | CDE staff and contractors |

Monitoring Priority: FAPE in the LRE

Indicator 8:  Percent of parents with a child receiving special education services who report that schools facilitated parent involvement as a means of improving services and results for children with disabilities.

(20 U.S.C. 1416(a)(3)(A)

Measurement: Percent = [(# of respondent parents who report schools facilitated parent involvement as a means of improving services and results for children with disabilities) divided by the (total # of respondent parents of children with disabilities)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | 74 percent of parents will report that schools facilitated parent involvement as a means of improving services and results for children with disabilities |

Actual Target Data for (2006-07): Overall 87.81 percent of respondents (30, 579 parents) reported that schools facilitated parent involvement as a means of improving services and results for children with disabilities. Table 8a depicts information about Parent Survey responses statewide. This data is collected through monitoring processes Verification Reviews (VR) and Special Education Self Reviews (SESR) through a survey in which parents report that schools facilitated parent involvement as a means of improving services and results for children with disabilities. Sixty districts were not required to complete surveys because of their very small size (N<20). A copy of the Parent Survey may be found in Appendix 2.

Table 8a

2006-07 Parent Survey Responses

| Survey Distribution | Responses |
| --- | --- |
| Surveys Mailed | 179,465 |
| Surveys Returned | 39,115 |
| Percent of Mailed Returned | 21.80% |
| Percent Returned of Special Education Enrollment | 16.57% |
| Surveys Responding to Q5 | 34,824 |
| Surveys with "YES" to Q5 | 30,579 |
| Percent Responding "YES" | 87.81% |

Table 8b depicts the enrollment characteristics of the districts participating in the Parent Survey process. The total enrollment of the districts included (n=191) was 2,137,685. The total special education enrollment for the districts included was 236,079, representing 34.74percent of the state special education enrollment for December 2006.

Table 8b

2006-07Enrollment of Districts Participating in the Sample

| Sample | Sample Total | State Total | Percent of State Total |
| --- | --- | --- | --- |
| Districts Included | 191 | 1,056 | 18.18% |
| Gen.Ed. Enrollment | 2,137,685 | 6,285,309 | 34.01% |
| Sp.Ed. Enrollment | 236,079 | 679,486 | 34.74% |

Table 8c provides a comparison between parent responses in 2005-06 and in 2006-07 in districts of different size. Overall there were more responses in 2006-07 than in 2005-06. The percent of “Yes” answers were increased for moderately sized districts (14,999 to 29,999), they remained constant at 12% for the largest district, but declined in both large (30,000 to 149,000) and small districts (less than 5000). The sample of districts in 2006-07 included many more small districts (Special Education N<20) than in 2005-06.

Table 8c

District size response rate comparing 2005-06 and 2006-07

|  | 2005-06 |  |  | 2006-07 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| District Size | n of Districts | n Yes | % Yes | n of Districts | n Yes | % Yes |
| 150,000 + | 1 | 3159 | 12% | 1 | 3,499 | 12% |
| 30,000 – 149,999 | 11 | 8249 | 32% | 9 | 6,231 | 21% |
| 15,000 – 29,999 | 14 | 4726 | 19% | 21 | 7,966 | 26% |
| 5,000 – 14,999 | 31 | 4801 | 19% | 44 | 8,872 | 29% |
| 1,000 – 4,999 | 75 | 3862 | 15% | 62 | 3,307 | 11% |
| 1 – 999 | 103 | 813 | 3% | 54 | 677 | 2% |
| Less that 20 | 6 did not participate due to small size |  |  | 60 do not participate due to small size |  |  |
| Total | 235 | 25,610 | 100% | 191 | 30,552 | 100% |

Discussion of Completed Improvement Activities and Explanation of Progress or Slippage that occurred for 2006 (2006-07)

Sampling Plan In its California Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

OSEP’s March 22, 2006 SPP response letter required the State to submit a revised sampling methodology that describes how data were collected with State’s FFY 2005 APR, due February 1, 2007. The State submitted a revised sampling plan. The sampling plan for this indicator is not technically sound. Please call your state contact as soon as possible.

## CDE revised its sampling and sent a review draft to OSEP. The full sampling plan may be found in Appendix 1. The main features of the sampling plan are summarized below:

## Key Design Characteristics of the 2005-06 and 2006-07 Sampling Plans

- All districts participating in Verification and Special Education Self Reviews will send surveys to all families of students receiving special education services.

- Small districts (special education N<20) will not be required to participate.

- Large districts (general education N>50,000) will survey at least a quarter of the families of students receiving special education services each year.

- All districts will secure a sample of at least 20% of the families surveyed.

- A statewide survey of districts will be completed in 4 years.

## Changes to base sampling plan in 2007-08

- Survey instruments will collect information about the ethnicity and disability for the child of the parent who is responding. This will enable CDE to evaluate the representiveness of the samples at the district and state level.

- CDE will explore changes to the monitoring plan cycle to equalize workload across monitoring years.

- CDE will require small districts to survey families of students with disabilities and to report responses. Data will be used in state level reporting, but local calculations will not be made for districts with a denominator less than 20. If this is begun in 2007-08, all small districts will be surveyed within the current timeframe of this SPP.

## Additional data collection beginning in 2008-09

- During 2007-08, CDE will work with PTIs and FECs to develop a three year sampling plan to collect family involvement information using the NCSEAM parent involvement survey.

- This data collection will be conducted independently of monitoring processes by parent centers and CDE staff (PSRS Parent Helpline)

- Data from this method will be compared to monitoring survey results.

Explanation of Progress: In 2005-06 69% of parents reported that schools facilitated parent involvement as a means of improving services and results for children with disabilities. An 18% improvement was shown from 2005-06 to 2006-07. The completed improvement activities have led to improved data by incorporating the parent survey into all monitoring processes. The parent survey was updated by adding a parent involvement question to the parent survey for Special Education Self Reviews, Verification Reviews, and Nonpublic School Reviews. Adding this question to the parent survey has provided a systematic process for collecting how parents feel about how schools facilitate parent involvement as a means of improving services and results for children with disabilities. Part of this improved parent survey process has provided Web based access to the parent survey for parents and Districts. Completing these improvement activities has allowed the State to surpass the measurable and rigorous target for parent involvement.

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Improvement | Timelines | Resources |
| Incorporate updated parent survey into all monitoring processes. | September 2007 | CDE staff and contractors |
| Met with parent organizations (Parent Training and Information Centers (PTIs) and Family Empowerment Centers (FECs)) to develop instrument for use in 2007-08 | June 2007 | CDE staff, NCSEAM, contractors, PTIs, and FEC’s Type: Special Project, Technical Assistance and Stakeholder |
| Used information gathered from parent survey in planning for all monitoring processes. | September 2007 | CDE staff and contractors Type: Monitoring Project |
| Added survey question to parent surveys for Special Education Self Reviews, Verification Reviews, and Nonpublic School Reviews | January 2006 | CDE staff and contractors Type: General Supervision, Monitoring Project |

Revisions, with Justification, to Proposed Targets / Continuing and Added Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Improvement Activities | Resources |
| Conduct analysis and prepare plans for Annual Performance Reports on all indicators, including parent involvement. | July 1, 2005 to June 30, 2011 | CDE staff Type: General Supervision, Monitoring Project |
| Explore Web based applications for all components of the monitoring system including parent involvement. | June 30, 2008 | Outside Contractor subject to approval by the Department of Finance, CDE staff Type: General Supervision, Monitoring Project |

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| During 2007-08, CDE will work with PTIs and FECs to develop a three year sampling plan to collect family involvement information using the NCSEAM parent involvement survey. | June 30, 2008 | CDE Staff and outside agencies Type: General Supervision, Monitoring Project |
| Data collection will be conducted independently of monitoring processes by parent centers and CDE staff (PSRS Parent Helpline). | June 30, 211 | CDE Staff Type: General Supervision, Monitoring Project |
| Develop a detailed revised sampling plan. | September 2007 | CDE Staff: Type: General Supervision, Monitoring Project |

Appendix 1

Parent Involvement Sampling Plan

In 2005-06, the CDE added a question to the monitoring surveys and processes designed to collect information about the number of parents who report that schools facilitated parent involvement to improve services and results for children with disabilities. This method was anticipated to reach approximately one quarter of the LEAs in the state. LEAs were required to send a survey to all parents in the district. A minimum of a 20 percent response rate was required. As in previous SESR processes, these data will be incorporated into the monitoring plans and the SESR database. Districts serving fewer than 20 students in special education were excluded. In addition, districts serving more than 50,000 special education students were required to complete parent surveys annually.

In 2006-07, CDE continued to use the survey and continued to work with the National Center on Special Education Accountability Monitoring (NCSEAM), parent organizations in California, and state and local district personnel to incorporate appropriate elements of the Part B Parent/Family Involvement measures into the SESR surveys in order to add to the existing, problem-oriented data.

In June 2007, CDE received a letter from the Office of Special Education Programs regarding the sampling plan for this indicator:

“The State provided baseline data, targets and improvement activities and OSEP accepts the SPP for this indicator. OSEP’s March 22, 2006 SPP response letter required the State to submit a revised sampling methodology that describes how data were collected with the State’s FFY 2005 APR, due February 1, 2007.

The State submitted a revised sampling plan. The sampling plan for this indicator is not technically sound. Please call your State contact as soon as possible”

(California’s Part B FFY 2005 SPP/APR Response Table, pg.6)

Conversation with OSEP staff indicated that CDE needed to submit additional information and to revise its sampling methodology;

## Key Design Characteristics of the 2005-06 and 2006-07 Sampling Plans

- All districts participating in Verification and Special Education Self Reviews will send surveys to all families of students receiving special education services.

- Small districts (special education N<20) will not be required to participate.

- Large districts (general education N>50,000) will survey at least a quarter of the families of students receiving special education services each year.

- All districts will secure a sample of at least 20% of the families surveyed.

- A statewide survey of districts will be completed in 4 years.

Sampling characteristics appear as follows;

| Year | No.of Districts | No. of Counties | Gen.Ed. Enrollment | Spec.Ed. Enrollment |
| --- | --- | --- | --- | --- |
| 1 | 328 | 19 | 1,640,503 | 175,964 |
| 2 | 325 | 15 | 2,558,623 | 284,488 |
| 3 | 225 | 11 | 822,969 | 86,311 |
| 4 | 245 | 13 | 1,263,214 | 139,101 |
| Total | 1123 | 58 | 6,285,309 | 685,864 |

| Year | % of Districts | % of Counties | % Gen.Ed. Enrollment | % Spec.Ed. Enrollment |
| --- | --- | --- | --- | --- |
| 1 | 29.21 | 32.76 | 26.1 | 25.66 |
| 2 | 28.94 | 25.86 | 40.71 | 41.48 |
| 3 | 20.04 | 18.97 | 13.09 | 12.58 |
| 4 | 21.82 | 22.41 | 20.1 | 20.28 |
| Total | 100.00 | 100.00 | 100.00 | 100.00 |

This approach has some weaknesses:

- Current monitoring practices do not include information about the ethnicity and disability of the students whose parents are responding to the survey. This limits the ability to evaluate the representativeness of the sample.

- The monitoring cycle was developed by the prior CDE general education monitoring system and is no longer used by general education. The regional workloads are out of balance.

- Families from small districts are not included in the overall, statewide sample.

## Changes to base sampling plan in 2007-08

- Survey instruments will collect information about the ethnicity and disability for the child of the parent who is responding. This will enable CDE to evaluate the representiveness of the samples at the district and state level.

- CDE will explore changes to the monitoring plan cycle to equalize workload across monitoring years.

- CDE will require small districts to survey families of students with disabilities and to report responses. Data will be used in state level reporting, but local calculations will not be made for districts with a denominator less than 20. If this is begun in 2007-08, all small districts will be surveyed within the current timeframe of this SPP.

## Additional data collection beginning in 2008-09

- During 2007-08, CDE will work with PTIs and FECs to develop a three year sampling plan to collect family involvement information using the NCSEAM parent involvement survey.

- This data collection will be conducted independently of monitoring processes by parent centers and CDE staff (PSRS Parent Helpline)

- Data from this method will be compared to monitoring survey results.

Appendix 2

Survey Instrument

Listed below are the questions used to obtain parent input during Verification and Special Education Self Reviews. Question 5 is the primary source of information about parents with a child receiving special education services who report that schools facilitated parent involvement as a means of improving services and results for children with disabilities.

Please circle your answers with one of the following responses:

Y = Yes			N = No		DK = Don’t Know

PLEASE ANSWER ONLY THOSE QUESTIONS THAT APPLY TO YOU AND YOUR CHILD.

Questions 1 – 5 apply to all parents

| 1 | Does the district make a good faith effort to assist your child with achieving the goals and objectives or benchmarks listed in his/her Individualized Education Program (IEP)? | Y | N | DK |
| --- | --- | --- | --- | --- |
| 2 | Do you receive progress reports on how your child is meeting his/her Individualized Education Program/ Individualized Family Service Plan (IEP/IFSP) goals/ outcomes at least as often as the regular report card schedule? | Y | N | DK |
| 3 | Are the services your child is receiving in accordance with his/her IEP? | Y | N | DK |
| 4 | Do you receive a copy of your parental rights (procedural safeguards) at least one time per year? | Y | N | DK |
| 5 | Did the school district facilitate parent involvement as a means of improving services and results for your child? | Y | N | DK |

Questions 6 – 7 are for parents of Infants/Toddlers only

| 6 | If your child is under three (3)-years of age, is his/her Individualized Family Service Plan (IFSP) reviewed with you at least every six (6) months? | Y | N | DK |
| --- | --- | --- | --- | --- |
| 7 | Were the transition services for your child from infant to preschool programs planned and implemented as written? | Y | N | DK |

Questions 8 – 21 are for parents of School Age children (Preschool through 12th grade)

| 8 | Do you understand the reasons why your child was referred for Special Education services? | Y | N | DK |
| --- | --- | --- | --- | --- |
| 9 | Were your child’s strengths considered during the IEP Meeting? | Y | N | DK |
| 10 | Were the results of your child’s assessment used to plan IEP goals? | Y | N | DK |
| 11 | Is your child re-evaluated for Special Education every three (3) years? | Y | N | DK |
| 12 | Does the district have an IEP meeting for your child at least once a year? | Y | N | DK |
| 13 | Does a regular education teacher attend your child’s IEP meeting, unless you and the district agree, under specified circumstances, to excuse him/her? | Y | N | DK |
| 14 | Were information and any concerns you had about your child considered when planning and writing his/her IEP/IFSP? | Y | N | DK |
| 15 | At your child’s IEP meeting, did the team discuss your child’s program in terms of the least restrictive environment (e.g., general education classroom, resource, special day class, etc.) for him/her? | Y | N | DK |
| 16 | Are teachers and service providers informed of specific responsibilities related to implementing your child’s IEP, and the specific accommodations, program modifications and support for school personnel? | Y | N | DK |
| 17 | Did you discuss a variety of program options for your child at the IEP meeting? | Y | N | DK |
| 18 | Are IEP goals and objectives reviewed and revised at the IEP meeting, based on both progress and lack of progress? | Y | N | DK |
| 19 | Does your child have the opportunity to participate in school and extra curricular activities (such as, assemblies, field trips and after school activities)? | Y | N | DK |
| 20 | Did the IEP team discuss how your child would participate in State and district testing? | Y | N | DK |

| 21 | If your child will turn 16 years of age before his/her next IEP meeting, did the IEP team discuss transition services (e.g., career interests, employment, high school classes) at the most recent meeting? | Y | N | DK |
| --- | --- | --- | --- | --- |

Questions 22 – 26 are for parents who don’t speak English at home or for parents of students who are learning English at school

| 22 | Does your child’s IEP indicate that he/she is an English Learner? | Y | N | DK |
| --- | --- | --- | --- | --- |
| 23 | As an English Learner, does your child receive services to assist with progress in English language development? | Y | N | DK |
| 24 | As an English learner, does your child receive the language support in Special Education classes necessary to learn subjects other than English, such as math or science? | Y | N | DK |
| 25 | If you speak a language other than English, upon request, do you receive information from the school in your native language? | Y | N | DK |
| 26 | Upon request, does the district provide a language interpreter for your child’s IEP meeting? | Y | N | DK |

Question 27 applies to all parents

| 27 | Do you have any other concerns or information about you or your child’s Special Education experience that you would like to tell us? Please attach your comments to this form. |
| --- | --- |

Child’s Age: _____	Child’s Ethnicity: _______________ Child’s Disability: ____________

Monitoring Priority: Disproportionality

Indicator 9:  Percent of districts with disproportionate representation of racial and ethnic groups in special education and related services that is the result of inappropriate identification.

(20 U.S.C. 1416(a)(3)(C))

Measurement: Percent = [(# of districts with disproportionate representation of racial and ethnic groups in special education and related services that is the result of inappropriate identification) divided by the (# of districts in the State)] times 100. Include State’s definition of “disproportionate representation.” Describe how the State determined that disproportionate representation of racial and ethnic groups in special education and related services was the result of inappropriate identification, e.g., monitoring data, review of policies, practices and procedures under 618(d), etc.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | 0 percent of districts will have disproportionate representation of racial and ethnic groups in special education and related services that is the result of inappropriate identification |

Actual Target Data for 2006 (2006-07):

Overall, there were 208 of 786 districts with denominators less than 20 who were identified as potentially disproportionate. 33 of the 786 or 4.19 percent were found to have noncompliant policies, procedures, or practices related to identification.

Calculation / 786 *100 = 4.19 %

For each district, California calculates a race-neutral measure labeled the Disparity Index as part of the Quality Assurance Process (QAP). Specifically, the number of students ages six through 22 receiving special education within each ethnic category is divided by the total number of all students ages six through 22  in that ethnic category (e.g., the percentage of African Americans receiving special education relative to the total number of African Americans in the district). The index is simply the range between the lowest and the highest group percentages. For example, if the percentage for African Americans is the highest at 15% and the percentage for Hispanics is the lowest at 8%, then the Disparity Index is 7 points. The underlying concept is that if the identification process is race neutral, the disparity index will be relatively low. The state has set a system of decreasing annual benchmarks leading to a maximum disparity of 5 points by 2011-12.

California combined the disparity measure with a composition index in a race neutral approach to identifying which districts are disproportionate. The first test is to identify those districts that have a disparity that is higher than the annual benchmark.

The second test, based on the composition index, looks at the proportion of each ethnicity’s age 6 to 22 enrollment in special education in a district (e.g., the percentage of American Indians in the total special education population). To test for proportional overrepresentation, for each ethnic category, this special education proportion is compared to the proportion of that ethnic group in the total grade one through grade 12 population of the district. Grade one through grade 12 is used because age by federal ethnic categories is not available for all students receiving a public education. When the proportion of students ages 6 to 22 receiving special education for any ethnic category is more than 20 percent higher than its proportion in grade one through 12 populations in the district, then the district is considered disproportionate in test two. For example, if White students make up 15% of the special education population and they are only 10% of the overall school population, the white students in special education exceed their representation in the general education by more than 20% and the district would be consider to have disproportionate representation using this second test.

If the district exceeds the benchmark using the disparity test AND the district is determined to have disproportionate representation using the second test, the district is identified as disproportionately overrepresented.

To test for proportional under-representation, the proportion of each ethnic enrollment in special education in a district is compared to the proportion of that group in the total grade 1 through 12 population of the district. When the proportion of students ages 6 to 22 receiving special education for any ethnic category is more than 40 percent lower than its proportion in the grades 1 through 12 populations AND the district has higher disparity using the disparity test, the district is identified as proportionately underrepresented.

Across California, African American students are proportionately overrepresented; Asian students are underrepresented. These disproportions are observed using both total student counts (see Table 9a) and counts of the number of overrepresented and underrepresented groups within districts (see Table 9b)

Table 9a

Over- and Under-representation of Students by Ethnicity in California

| Students | American Indian | Asian | African American | Hispanic | White | Total |
| --- | --- | --- | --- | --- | --- | --- |
| GE N | 44,541 | 664,344 | 446,596 | 2,785,215 | 1,723,619 | 5,664,315 |
| GE P | 0.8% | 11.7% | 7.9% | 49.2% | 30.4% | 100.0% |
| GE P + 20 | 0.9% | 14.1% | 9.5% | 59.0% | 36.5% |  |
| GE P - 40 | 0.5% | 7.0% | 4.7% | 29.5% | 18.3% |  |
| SE N | 5,384 | 37,409 | 72,014 | 286,350 | 203,783 | 604,940 |
| SEP | 0.9% | 6.2% | 11.9% | 47.3% | 33.7% | 100.0% |
| Over Representation |  |  | Yes |  |  |  |
| Under Representation |  | Yes |  |  |  |  |

Table 9b

Over- and Under-representation of Students by Districts in California

| Districts | American Indian | Asian | African American | Hispanic | White |
| --- | --- | --- | --- | --- | --- |
| Over Representation | 61 | 5 | 162 | 50 | 67 |
| Under Representation | 19 | 112 | 3 | 8 | 0 |

Disproportionate representation is determined to be the result of inappropriate identification through a review of policies, procedures and practices. Districts are identified as having disproportionate representation as described above. The list of districts is compared to the list of districts scheduled for Verification Review (VR) or Special Education Self Review (SESR). If a district is scheduled for either review, the review of policies, procedures and practices is conducted through their regularly scheduled review. If a district is not on the list of districts scheduled for review, the district is required to complete a special self-review of policies, procedures and practices that is mailed to the district. The same review items are used in the VRs, SESRs and the special self-review. Findings of noncompliance are included in the regular corrective action plans for the VRs and SESRs. Findings of noncompliance identified through the special self-review result in a corrective action plan, monitored by the Focused Monitoring and Technical Assistance Consultant assigned to the district. A copy of the VR, SESR, and special self-review protocol is contained in Appendix 1.

Correction of Noncompliance Identified in 2005-06. In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

Additionally, the State must include data and information that demonstrate that the LEAs identified in the FFY 2005 APR as having disproportionate representation that was the results of inappropriate identification are in compliance with child find, evaluation, and eligibility requirements in 34 CFR §§300.111, 300.201 and 300.301 through 300.311

Of the 15 districts with noncompliant policies and procedures identified in 2005-06, two had already corrected the noncompliance and 13 had corrective action plans that were to be completed in 2006-07.

All of the districts completed their corrective action plans within one year of identification.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for (Insert FFY):

Comparison to Baseline Data for FFY 2005 (2005-06). Overall, there were 121 of 766 districts identified as potentially disproportionate in 2005-06. Fifteen of the 766 or 1.95 percent were found to have noncompliant policies and procedures related to identification. In 2006-07 there were 208 districts out of 786 districts identified as potentially disproportionate. Thirty-six of the 786 or 4.19% were found to have noncompliant policies, procedures and practices related to identification. Not only is there an increase in the number of districts identified as disproportionately represented, but the percentage with inappropriate policies, procedures and practices related to identification is increased as well. The increase in the number of districts may be related to the identification of districts that had disproportionate under-representation. Otherwise, there are no particular trends related to geography or district size; staffing or resource changes. The increase in the percentage of districts found noncompliant may be due to a change the methods used for conducting monitoring. In 2005-06, districts with disproportionate representation were required to “hand enter” self review items into the monitoring software. In 2006-07, the monitoring software automatically included all of the items for the review. This has resulted in a larger number of noncompliance findings at the district level coming through the software-generated reviews (33 districts in 2006-07) compared to none in 2005-06. It does not appear that “self” review is less accurate than CDE staff review, as 33 of the 36 districts were ones that self identified through the Special Education Self Review (SESR) process. It has been suggested that conducting the review of policies, procedures and practices related to identification as a part of a larger review of a district may yield more accurate results than a review that is focused solely on the issue of disproportionality.

Population size  In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

In the FFY 2006 APR, due February 1, 2008, the State must clarify the determination of “with large enough student populations.” If the State is using a numerical threshold at the district level, it must clarify this process, since the State appears to be excluding a large number of districts from its review.

As noted above, California uses an N of 20 as the minimum number in a denominator to generate percentage calculations. As a result, for this indicator, in both 2005-06 and in 2006-07, a district was excluded from the total if, in either the Ethnic Disparity calculation or the comparison of composition index calculations, a denominator dropped below 20.

Practices review. In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

The State also must clarify how practices are reviewed when determining whether disproportionate representation of racial and ethnic groups in special education and related services is the result of inappropriate identification.

As noted above, the CDE has added a practices review to the review of policies, procedures and practices related to identification. A copy of the review protocol and instructions may be found in Appendix 1. Essentially, a review of student records was added to the review of policies and procedures, using record review items already present in CDE’s monitoring software. For Verification Reviews and Special Education Self Reviews, these additional items were a required component of all reviews. The same items were prepared in print form for the special self reviews. Considerable discussion has taken place in various stakeholder groups about the issues of practices. Samples from other states and from the National Center on Culturally Responsive Education Systems (NCCRESt) have been reviewed. The existing practices review may be responsible for the identification of more noncompliance, but does not necessarily get at the root causes of these issues. Stakeholders feel very strongly that this issue is not a special education issue, alone, and requires substantial change in general education policies, procedures and practices as well. California will continue to refine its review of practices through participation in the Superintendents Closing the Achievement Gap initiative and in conjunction with stakeholder workgroups.

Racial or ethnic groups with disproportionate representation In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

The State identified 1.95% of districts with disproportionate representation that was the result of inappropriate identification, but did not identify the racial or ethnic groups with disproportionate representation.

Table 9a and 9b above summarize statewide calculations related to each ethnic group. In 2006-07, African Americans are over-represented most frequently and Asians are most frequently under-represented. This was also true in 2005-06.

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Identify districts that are significantly disproportionate, using existing instruments and procedures to test new definition. | July 2007 | CDE Staff, OSEP Type: Monitoring and Enforcement |
| Work with WRRC to conduct a study of promising practices among districts that are not disproportionate and achieve successful student outcomes on statewide testing. | January 2007 to January 2008 | Federal contractors (WRRC) CDE staff Type: Technical Assistance |
| Use refined procedures to Identify districts with significant disproportionality and establish plans for supervision and technical assistance. | July 2008 | CDE staff Type: Monitoring and Enforcement |
| Reconvene Larry P. Task Force to reexamine testing matrix and publish revised matrix. | July 2007 to July 2008 | CDE staff, field experts, Larry P. Task Force, CDE staff Type: Special Project Policy Development |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for (2006-07) (If applicable)

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Work with Western Regional Resource Center (WRRC) and other Federal contractors to identify and disseminate research-based practices related to preventing disproportionate representation and to address the interface between eligibility and disproportionality. | 2005-2010 Ongoing | Federal contractors (WRRC) CDE staff Type: Technical Assistance |
| Work with WRRC to conduct a study of promising practices among districts that are not disproportionate and achieve successful student outcomes on statewide testing. | January 2007 to January 2008 | Federal contractors (WRRC) CDE staff Type: Technical Assistance |
| Refine policies, procedures, and practices instruments. | October 2007 and annually thereafter | CDE Staff, OSEP Type: Monitoring and Enforcement |

As noted above, Considerable discussion has taken place in various stakeholder groups about the issues of practices. Samples from other states and from the National Center on Culturally Responsive Education Systems (NCCRESt) have been reviewed. The existing practices review may be responsible for the identification of more noncompliance, but does not necessarily get at the root causes of these issues. Stakeholders feel very strongly that this issue is not a special education issue, alone, and requires substantial change in general education policies, procedures and practices as well. California will continue to refine its review of practices through participation in the Superintendents Closing the Achievement Gap initiative and in conjunction with stakeholder workgroups.

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Convene special meetings of ISES and SELPA stakeholder groups to develop two types of practices reviews: - Compliance based to address IDEA monitoring requirements - Research based to address improvement needed outside of a compliance context | January 2008 to June 2010 | CDE staff and Contractors Western Regional Resource Center |
| Incorporate preliminary self review and improvement planning modules into monitoring software, based on NCCRESt | June 2008 | CDE staff and Contractors |
| Participate in Superintendents Closing the Achievement Gap initiative: - Assign staff to participate - Provide information from SPP and APR - Assist in the development of products and materials - Secure general education input and participation in the development of district level practices review. | June 2007 to June 2010 | CDE staff and Contractors |

Appendix 1

Review Protocol and Instructions

INSTRUCTIONS: DISPROPORTIONATE REPRESENTATION

The review of:  	SPPI 9:  Disproportionality Overall

SPPI 10: Disproportionality - By Federal Ethnic Category by Disability

- To conduct the Review of Policies and Procedures:

- Use the CDE provided protocol to conduct a review of the district’s Policies and Procedures relative to the disproportionality of special education students overall and by federal ethnic category by disability of special education students.

- Conduct the examination of the district’s Policies and Procedures using the items listed under the heading Policies and Procedures.

- Mark each item reviewed as either Compliant or Non-Compliant depending on whether it is determined that there is or is not a Policy or Procedure that addresses that item.

- Please submit one (1) completed Policies and Procedures review protocol to CDE.

NOTE:	If your district conducted a Verification Review (VR) or a Special Education Self-Review (SESR) during 2006-07, please submit a letter or email advising CDE that the Policies and Procedures review findings and/or information previously reported to CDE remains accurate and complete. If this relates to your district you do not need to conduct another policies and procedures review.

- To conduct the Practices Review:

- Use the CDE provided protocol to conduct a review of the district’s practices relative to the identification of the ethnic distribution of students. For SPPI 9, select student records for those ethnicities identified as over and/or underrepresented. For SPPI 10 select student records in the six (6) special education eligibility categories – Specific Learning Disability, Mental Retardation, Speech, Language Instruction, Other Health Impairment, Emotional Disturbance, and Autism

- Select a sample of fifteen (15) records of district special education students.

- Using the CDE provided protocol, examine each student record and mark each item reviewed as either Compliant or Non-Compliant.

- For each reviewed record that has Non-Compliant findings, a separate form, STUDENT CORRECTIVE ACTION FORM, must be completed. The form identifies: the student by name; his/her date of birth; the item number found non-compliant; the finding made; the planned corrective action; and the date the correction was made. This form, if applicable, must be attached to each student’s review protocol.

- Please submit one review protocol for each student record reviewed – for a total of fifteen (15). Attach to each protocol, when there are non-compliant findings, a copy of the STUDENT CORRECTIVE ACTION FORM.

NOTE:	If the district conducted a Verification Review (VR) or a Special Education Self-Review (SESR) during 2006-07, this review does not need to be completed. Instead, please submit to CDE a signed assurance statement that the review was completed and if Non-compliant issues were found that all corrections were made

Appendix 1

Review Protocol and Instructions

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Practices Review |  |  |  |  |  |  |  |
| Assessment |  |  |  |  |  |  |  |
| Assessment Plan |  |  |  |  |  |  |  |
| 2-1-1.3 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes the individual's primary language and language proficiency status (LEP/FEP) for English language learners? | The child's primary language and language proficiency in English must be indicated in the Assessment Plan. | The Assessment Plan must include this statement. | 30 EC 52164.15, CCR 3022. |  |  |  |
| 2-1-1.6 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes a description of alternative means that will be used to assess language impairment or specific learning disabilities when standard tests are considered invalid? | Plan must include description of alternate means if alternate means were used to assess child. | The plan should specify the methods that will be used as an alternative. Look for expected language performance level and/or severe discrepancy when standardized tests are considered to be invalid and description of alternative means. | 5 CCR 3030(c)(4)(B), 5 CCR 3030 (j)(4)(B). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Procedures |  |  |  |  |  |  |  |
| 2-2-2.2 | Is there evidence that the current assessment is comprehensive and that materials and procedures used to assess a student with limited English proficiency are selected and administered to ensure that they measure the extent to which the student has a disability and needs special education, rather than measuring the student’s English proficiency?. | Policies and procedures address selection of materials and procedures for assessment of English learners. In the student record, the Assessment Report references the LEP status, the primary language and the implications upon the assessment. | Review the Assessment Report for references to the LEP status, the primary language and the validity of assessment materials and procedures. Interview assessors. | 34 CFR 300.304(c)(1)(i). |  |  |  |
| 2-2-5.2 | Do assessment procedures ensure that IQ tests are not administered to African- American students? | Student records indicate that an IQ measure was not administered to an African-American student. | Review the plan, Assessment Report and other assessment information. Determine if the Assessment Plan indicated alternative assessments to obtain information about cognitive development. Were the alternative assessments administered as appropriate? Interview staff and parents. | Larry P. vs. Riles. |  |  |  |
| 2-2-5.3 | Do assessment procedures ensure that materials are used to assess specific areas of educational need and do not rely merely on procedures that provide a single IQ score? | Student record documents use of multiple types of measures as indicated. | Description of assessment materials on the Assessment Plan and within the Assessment Report(s). Identification of a variety of sources including standardized tests, teacher report, health and developmental history, medical records, social and cultural background, adaptive behavior. The present level of performance on the IEP reflects the assessments. | 20 USC 1414 (b)(2), 34 CFR 300.304(c)(2), 30 EC 56320(c). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Report |  |  |  |  |  |  |  |
| 2-3-1.1 | Does the written assessment report include the results of tests administered in the student's primary language by qualified personnel? | Assessment Report must include documentation of language of assessment for children whose primary language is not English. | Look for a statement on the Assessment Report and on the IEP that addresses how the assessment addressed the student whose primary language is not English. | EC 563205 CCR 3023(a). |  |  |  |
| 2-3-1.2 | If a test was administered through an interpreter, does the written report include a statement regarding validity of the assessment? | Report must include notation that validity may have been affected if translator is used. | Look for a statement of validity in the Assessment Report when appropriate. For example, when an interpreter is used or alternative assessments were used. | 20 USC 1414(b)(3)(A)(iii), 5 CCR 3023(a). |  |  |  |
| IEP Process | If neither parent can attend the IEP meeting does the LEA use other means to ensure parent participation including individual or conference phone calls? |  |  |  |  |  |  |
| IEP - Additional Requirements |  |  |  |  |  |  |  |
| 3-5-8 | For a student with limited English proficiency (English language learners (ELL)), does the IEP team consider the language needs of the student as such needs relate to the student’s IEP and does the IEP include linguistically appropriate goals and objectives. | If appropriate, IEP consideration must be evident. | Look in the Assessment Report and/or any other documentation that the LEA has assessed the child's language needs. Look in the IEP for a statement that the IEP team has considered the child's language needs. Look for linguistically appropriate goals and objectives. | 20 USC 1414(d)(3)(B)(ii), 34 CFR 300.324 (a)(2)(ii), 30 EC 56345(b)(2) & 56341.1(b)(2). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Procedural Safeguards |  |  |  |  |  |  |  |
| Written Prior Notice |  |  |  |  |  |  |  |
| 10-2-1 | Are all students whose home language survey indicates a language other than English assessed using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must assess any pupil whose native language is other than English as determined by the home language survey for English language proficiency. | Review policies and procedures. Review files of students with disabilities whose home language is other than English to see if their English language proficiency has been assessed. Interview administrators and staff. | EC 306(a)5 CCR 11511(a). |  |  |  |
| 10-2-2 | Does the LEA assess all students identified as English learners annually using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must annually assess all children identified as English learners and maintain a record of all pupils who participate in each administration of the CELDT. | Review policies and procedures to ensure that children with disabilities who are English learners are assessed. Interview staff and administrators about participation of children with disabilities in the CELDT. | EC 3135 CCR 11511, 5 CCR 11512. |  |  |  |
| 10-2-3 | In developing the IEP for students identified as English learners, does the IEP team consider the results of the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The IEP team must consider the results of the child's performance on statewide assessment programs and must consider the language needs of English learners as those needs relate to the IEP. | Review district policies and procedures. Review the child's Assessment Report and/or IEP (present performance, IEP notes) to determine if CELDT results were part of the IEP team consideration. Interview administrators, staff and parents about the IEP team. | 34CFR 300.324(a). |  |  |  |
| 10-2-4 | Does the IEP of students identified as English learners include a determination of whether CELDT will be administered with or without modifications or accommodations, or whether English proficiency will be measured using an alternate assessment? | The IEP must include a determination of whether the CELDT is administered with or without modifications, accommodations or through an alternate means. | Review district policies and procedures. Review the child's IEP (including IEP notes) to determine if the IEP team determined how the CELDT would be administered. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.320, 5 CCR 11516. |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 10-2-5 | Does the IEP of students identified as English learners include activities which lead to the development of English language proficiency. | The IEP must include linguistically appropriate goals, objectives, programs and services including English language development activities. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development in IEPs. | 34CFR 300.320, 5 CCR 3001. |  |  |  |
| 10-2-6 | Does the IEP of students identified as English learners include instructional systems which meet the language development needs of the student and ensure access to the general education curriculum? | The IEP must include linguistically appropriate goals, objectives, programs and services including instructional systems which meet the language development needs of the student. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development and instruction in the general curriculum for English learners with disabilities. Review the IEP for language of instruction. | 34CFR 300.320, 6 CCR 3001. |  |  |  |
| Policies and Procedure Review |  |  |  |  |  |  |  |
| Assessment |  |  |  |  |  |  |  |
| Assessment Plan |  |  |  |  |  |  |  |
| 2-1-1.3 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes the individual's primary language and language proficiency status (LEP/FEP) for English language learners? | The child's primary language and language proficiency in English must be indicated in the Assessment Plan. | The Assessment Plan must include this statement. | 30 EC 52164.15, CCR 3022. |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Procedures |  |  |  |  |  |  |  |
| 2-2-2.2 | Is there evidence that the current assessment is comprehensive and that materials and procedures used to assess a student with limited English proficiency are selected and administered to ensure that they measure the extent to which the student has a disability and needs special education, rather than measuring the student’s English proficiency?. | Policies and procedures address selection of materials and procedures for assessment of English learners. In the student record, the Assessment Report references the LEP status, the primary language and the implications upon the assessment. | Review the Assessment Report for references to the LEP status, the primary language and the validity of assessment materials and procedures. Interview assessors. | 34 CFR 300.304(c)(1)(i). |  |  |  |
| 2-2-5.2 | Do assessment procedures ensure that IQ tests are not administered to African- American students? | Student records indicate that an IQ measure was not administered to an African-American student. | Review the plan, Assessment Report and other assessment information. Determine if the Assessment Plan indicated alternative assessments to obtain information about cognitive development. Were the alternative assessments administered as appropriate? Interview staff and parents. | Larry P. vs. Riles. |  |  |  |
| 2-2-5.3 | Do assessment procedures ensure that materials are used to assess specific areas of educational need and do not rely merely on procedures that provide a single IQ score? | Student record documents use of multiple types of measures as indicated | Description of assessment materials on the Assessment Plan and within the Assessment Report(s). Identification of a variety of sources including standardized tests, teacher report, health and developmental history, medical records, social and cultural background, adaptive behavior. The present level of performance on the IEP reflects the assessment | 20 USC 1414 (b)(2), 34 CFR 300.304(c)(2), 30 EC 56320(c). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IEP Process | If neither parent can attend the IEP meeting does the LEA use other means to ensure parent participation including individual or conference phone calls? |  |  |  |  |  |  |  |
| IEP - Additional Requirements |  |  |  |  |  |  |  |  |
| 3-5-8 | For a student with limited English proficiency (English language learners (ELL)), does the IEP team consider the language needs of the student as such needs relate to the student’s IEP and does the IEP include linguistically appropriate goals, objectives, programs and services? | If appropriate, IEP consideration must be evident. | Look in the Assessment Report and/or any other documentation that the LEA has assessed the child's language needs. Look in the IEP for a statement that the IEP team has considered the child's language needs. Look for linguistically appropriate goals, objectives, programs and services? | 20 USC 1414(d)(3)(B)(ii), 34 CFR 300.324 (a)(2)(ii), 30 EC 56345(b)(2) & 56341.1(b)(2). |  |  |  |  |
| Procedural Safeguards |  |  |  |  |  |  |  |  |
| Written Prior Notice |  |  |  |  |  |  |  |  |
| 10-2-1 | Are all students whose home language survey indicates a language other than English assessed using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must assess any pupil whose native language is other than English as determined by the home language survey for English language proficiency. | Review policies and procedures. Review files of students with disabilities whose home language is other than English to see if their English language proficiency has been assessed. Interview administrators and staff. | EC 306(a)5 CCR 11511(a). |  |  |  |  |
| 10-2-2 | Does the LEA assess all students identified as English learners annually using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must annually assess all children identified as English learners and maintain a record of all pupils who participate in each administration of the CELDT. | Review policies and procedures to ensure that children with disabilities who are English learners are assessed. Interview staff and administrators about participation of children with disabilities in the CELDT. | EC 3135 CCR 11511, 5 CCR 11512. |  |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10-2-3 | In developing the IEP for students identified as English learners, does the IEP team consider the results of the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The IEP team must consider the results of the child's performance on statewide assessment programs and must consider the language needs of English learners as those needs relate to the IEP. | Review district policies and procedures. Review the child's Assessment Report and/or IEP (present performance, IEP notes) to determine if CELDT results were part of the IEP team consideration. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.324(a). |  |  |  |  |
| 10-2-4 | Does the IEP of students identified as English learners include a determination of whether CELDT will be administered with or without modifications or accommodations, or whether English proficiency will be measured using an alternate assessment? | The IEP must include a determination of whether the CELDT is administered with or without modifications, accommodations or through an alternate means. | Review district policies and procedures. Review the child's IEP (including IEP notes) to determine if the IEP team determined how the CELDT would be administered. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.320, 5 CCR 11516. |  |  |  |  |
| 10-2-5 | Does the IEP of students identified as English learners include activities which lead to the development of English language proficiency. | The IEP must include linguistically appropriate goals, objectives, programs and services including English language development activities. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development in IEPs. | 34CFR 300.320, 5 CCR 3001. |  |  |  |  |
| 10-2-6 | Does the IEP of students identified as English learners include instructional systems which meet the language development needs of the student and ensure access to the general education curriculum? | The IEP must include linguistically appropriate goals, objectives, programs and services including instructional systems which meet the language development needs of the student. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development and instruction in the general curriculum for English learners with disabilities. Review the IEP for language of instruction and instructional delivery systems. | 34CFR 300.320, 6 CCR 3001. |  |  |  |  |

Monitoring Priority: Disproportionality

Indicator 10:  Percent of districts with disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification.

(20 U.S.C. 1416(a)(3)(C))

Measurement: Percent = [(# of districts with disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification) divided by the (# of districts in the State)] times 100. Include State’s definition of “disproportionate representation.” Describe how the State determined that disproportionate representation of racial and ethnic groups in specific disability categories was the result of inappropriate identification, e.g., monitoring data, review of policies, practices and procedures under 618(d), etc.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | 0 percent of districts will have disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification |

Actual Target Data for 2006 (2006-07):

Overall, 56 of 786 districts (denominator values greater than 19) were identified as disproportionate. 15 of the 56 (1.91 percent of the 786 districts) were found to have noncompliant policies, procedures, and practices related to identification.

Calculation: 15 / 786 *100 = 1.91%

To align with the established parameters for this measure, California adjusted the populations used to calculate this measure starting with data collected in 2006-07. For students receiving special education, the number of students ages six through 22 is used as the numerator in the calculations. Because age by federal ethnic categories is not available for all students receiving a public education, the number of students in grade one through grade 12 is used as the denominator.

In 2006-07, California calculated composition indices for each of thirty disability-ethnicity cells based on the distributions of students in five ethnic categories and six disability categories. Students in the following six disability categories are included: mental retardation, specific learning disabilities, emotional disturbance, speech or language impairments, other health impairments, and autism.

Separately for each disability, the state determines the proportion each ethnic category is of the total enrollment within that disability for students ages six through 22 receiving special education. For each ethnic category, this proportion is compared to the proportion of that group in the total population of students in grades one through 12 of the district.

A disability-ethnic category cell is overrepresented when the proportion of that cell is more than 20 percent higher than the proportion for the corresponding ethnic category in the grade one through 12 populations.

In previous years, potential under-representation was not examined when identifying districts that must review their policies, procedures, and practices. In 2006-07, California expanded the test to include a measurement of proportional under-representation. Using the same calculations as described above, a disability-ethnic category cell is underrepresented when the proportion of that cell is more than 40 percent lower than the proportion for the corresponding ethnic category in the grade one through 12 populations.

A district is considered disproportionally represented if more than 10 of the thirty disability-ethnic category cells are overrepresented, or if more than 10 of the thirty disability-ethnic category cells are underrepresented.

Disproportionate representation is determined to be the result of inappropriate identification through a review of policies, procedures and practices. Districts are identified as having disproportionate representation as described above. The list of districts is compared to the list of districts scheduled for Verification Review (VR) or Special Education Self Review (SESR). If a district is scheduled for either review, the review of policies, procedures and practices is conducted through their regularly scheduled review. If a district is not on the list of districts scheduled for review, the district is required to complete a special self review of policies, procedures and practices that is mailed to the district. The same review items are used in the VRs, SESRs and the special self review. Findings of noncompliance are included in the regular corrective action plans for the VRs and SESRs. Findings of noncompliance identified through the special self review result in a corrective action plan, monitored by the Focused Monitoring and Technical Assistance Consultant assigned to the district. A copy of the VR, SESR, and special self review protocol is contained in Appendix 1.

In 2006-07 a list of potentially disproportionate districts was compiled using the methodology described above. Some of these districts were already slated for Verification Reviews (VRs) or Special Education Self Reviews (SESRs), which included a review of policies, procedures and practices related to identification. Other disproportionally represented districts are required to complete a self assessment of identical items related to identification.

Baseline data for 2005-06 In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

The State did not provide data on the percent of districts with disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification as required by 34 CFR §300.600(d)(3). The State must provide, in its FFY 2006 APR, baseline data from FFY 2005 on the percent of districts identified with disproportionate representation of racial and ethnic groups in specific disability categories that was the result of inappropriate identification, and describe how the State made that determination (e.g., monitoring data, review of policies, practices and procedures, etc).

and

In reporting on disproportionate representation by disability category that is the result of inappropriate identification under this indicator, the State reported that it used a definition of disproportionality for one racial group (African-American) that was different from that used for all other racial and ethnic groups. Specifically, the State reported that it “set a threshold for disproportionality based on 10 of 30 cells or three or more of the African American disability categories in which the percentage of students is more than 20 percent above what would be expected based on the percent of that ethnic group among the population of students receiving special education and related services.” The State did not provide a rationale for this difference. Under 34 CFR §300.600(d)(3) a State may, in reviewing data for each race ethnicity category, do so in a statistically appropriate manner, and may set an “n” size that applies to all racial and ethnic groups, but it must review data for all race ethnicity categories in the State consistently and must do the analysis at the LEA level for all race and ethnic groups meeting that “n” size that are present in any of its LEAs. Therefore, it appears that the State is not complying with 34 CFR §300.600(d)(3). To the extent that the State’s review for disproportionality does not look at disproportionality for all race and ethnic groups applying the same criteria, the State must revise its method of reviewing disproportionality and, in its FFY 2006 APR, describe and report on the revisions it has made and the results of its review of data and information for all race ethnicity categories in the State to determine if there is dispropointionate representation that is the result of inappropriate identification for both FFY 2005 and FFY 2006

In the 2005-06 SPP, the CDE identified 191 districts as being disproportionately represented by disability. These figures were revised to reflect both over- and under-representation and to eliminate the use of differential criteria for African American students. Using these revised calculations, 45 of the 792 districts with the denominator > 19 were identified as having disproportionate representation. The drop in the number of districts from the numbers cited in the 2005-06 SPP is not surprising, as all of the districts identified (191) were found using the differential criteria for African American students.

A special survey was sent to the 45 districts identified using 2005-06 data (See Appendix 2)

Of the 45 districts have completed their special self review, 15 have not responded.  Of the non-respondents, 2 have been put on special conditions, 8 have been sent sanction letters, and 5 are receiving regular technical assistance to enable them to complete the reviews. CDE staff is continuously in contact with those districts who have not returned surveys. Based on surveys returned to date, there are 30 of the 45 districts that have noncompliance related to identification.  Overall, in the baseline year, 3.79% of districts were disproportionate due to inappropriate policies, procedures and practices related to identification.

Calculation:  (30/ 792*100=.3.79%)

Table 10a summarizes state level over- and under-representation by ethnicity and disability.

Table 10a

Over- and Under- Representation of Students by Ethnicity and Disability in California

| Students | American Indian | Asian | African American | Hispanic | White | Total |
| --- | --- | --- | --- | --- | --- | --- |
| GE N | 44,541 | 664,344 | 446,596 | 2,785,215 | 1,723,619 | 5,664,315 |
| GE P | 0.8% | 11.7% | 7.9% | 49.2% | 30.4% | 100.0% |
| GE P + 20 | 0.9% | 14.1% | 9.5% | 59.0% | 36.5% |  |
| GE P - 40 | 0.5% | 7.0% | 4.7% | 29.5% | 18.3% |  |
| Mental Retardation |  |  |  |  |  |  |
| SE N | 333 | 3,288 | 19,746 | 4,655 | 10,477 | 38,499 |
| SEP | 0.9% | 8.5% | 12.1% | 51.3% | 27.2% | 100.0% |
| Over Representation |  |  | Yes |  |  |  |
| Under Representation |  |  |  |  |  |  |
| Speech or Language Impairment |  |  |  |  |  |  |
| SE N | 1,130 | 12,564 | 61,177 | 9,438 | 49,158 | 133,467 |
| SEP | 0.8% | 9.4% | 7.1% | 45.8% | 36.8% | 100.0% |
| Over Representation |  |  |  |  | Yes |  |
| Under Representation |  |  |  |  |  |  |
| Emotional Disturbance |  |  |  |  |  |  |
| SE N | 348 | 809 | 6,576 | 5,921 | 13,137 | 26,791 |
| SEP | 1.3% | 3.0% | 22.1% | 24.5% | 49.0% | 100.0% |
| Over Representation | Yes |  | Yes |  | Yes |  |
| Under Representation |  | Yes |  | Yes |  |  |
| Other Health Impairment |  |  |  |  |  |  |
| SE N | 420 | 1,637 | 11,873 | 4,852 | 20,930 | 39,712 |
| SEP | 1.1% | 4.1% | 12.2% | 29.9% | 52.7% | 100.0% |
| Over Representation | Yes |  | Yes |  | Yes |  |
| Under Representation |  | Yes |  |  |  |  |
| Specific Learning Disability |  |  |  |  |  |  |
| SE N | 2,751 | 11,245 | 163,091 | 41,451 | 83,943 | 302,481 |
| SEP | 0.9% | 3.7% | 13.7% | 53.9% | 27.8% | 100.0% |
| Over Representation |  |  | Yes |  |  |  |
| Under Representation |  | Yes |  |  |  |  |
| Autism |  |  |  |  |  |  |
| SE N | 186 | 4,654 | 8,809 | 2,741 | 14,713 | 31,103 |
| SEP | 0.6% | 15.0% | 8.8% | 28.3% | 47.3% | 100.0% |
| Over Representation |  | Yes |  |  | Yes |  |
| Under Representation |  |  |  | Yes |  |  |

When looking at student enrollment cross California (Table 10a), American Indian students are proportionately over-represented in Emotional Disturbance and Other Health Impairment; they are 1.6 times as likely to be identified as having Emotional Disturbance as would be expected from their proportion in the general education population. American Indian students are not under-represented in any disability category.

Asian students are 1.3 times as likely to be proportionately over-represented in Autism as would be expected from their proportion in the general education population; the only disability category in which they are over-represented. Proportional under-representation occurs in Emotional Disturbance, Other Health Impairment and Specific Learning Disability (the only overrepresented ethnic group in this category) for Asian students; they are 3.9 times less likely to be identified as having Emotional disturbance as would be expected from their proportion in the general education population.

African American students are proportionately over-represented in Mental Retardation, Emotional Disturbance, and Specific Learning Disability (the only overrepresented ethnic group in the Mental Retardation and Specific Learning Disability categories); they are not under-represented in any disability category. The largest over-representation for African American students occurs in the Mental Retardation disability where they are 1.7 times as likely to be identified as would be expected from their proportion in the general education population.

For White students, the largest proportional over-representation occurs in the Other Health Impairment disability category where they are 1.7 times as likely to be included than would be expected from their proportion in the general education population. In addition, White students are proportionately overrepresented in the Speech or Language Impairment (the only overrepresented ethnic group in that category), Emotional Disturbance, and Autism disability categories; they are not under-represented in any disability category.

There is no disability category in which Hispanic students are proportionately over-represented. Proportional under-representation occurs in the Emotional Disturbance and Autism disability categories; these students are 1.7 times less likely to be identified as having Emotional Disturbance as would be expected from their proportion in the general education population.

Table 10b

Over- and Under-representation of Students by Ethnicity and Disability

in Districts in California

| Number of Districts | American Indian | Asian | African American | Hispanic | White |
| --- | --- | --- | --- | --- | --- |
| Mental Retardation |  |  |  |  |  |
| Over Representation | 9 | 6 | 40 | 15 | 15 |
| Under Representation | 5 | 34 | 3 | 9 | 11 |
| Speech or Language Impairment |  |  |  |  |  |
| Over Representation | 21 | 4 | 18 | 15 | 24 |
| Under Representation | 9 | 34 | 9 | 1 | 2 |
| Emotional Disturbance |  |  |  |  |  |
| Over Representation | 17 | 0 | 48 | 4 | 52 |
| Under Representation | 3 | 52 | 0 | 43 | 1 |
| Other Health Impairment |  |  |  |  |  |
| Over Representation | 13 | 4 | 48 | 3 | 54 |
| Under Representation | 3 | 50 | 2 | 41 | 1 |
| Specific Learning Disability |  |  |  |  |  |
| Over Representation | 35 | 0 | 54 | 25 | 17 |
| Under Representation | 6 | 56 | 0 | 3 | 4 |
| Autism |  |  |  |  |  |
| Over Representation | 3 | 20 | 23 | 0 | 49 |
| Under Representation | 2 | 14 | 7 | 51 | 1 |

Table 10b shows how most disability categories are proportionately overrepresented or underrepresented in at least some districts among the 56 disproportionate districts. There are no districts in which Asian students are proportionately overrepresented in the Emotional Disturbance or Specific Learning Disability categories; Hispanic students are not proportionately overrepresented in any districts in the Autism disability category. The largest number of disproportionate districts is 54 for African American Students with Specific Learning Disability. There are no districts in which African American students are proportionately underrepresented in either the category of Emotional Disturbance or that of Specific Learning Disability. Asian students are proportionately underrepresented in all 56 districts.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

The state of California continues to be above the benchmark of “0 percent of districts will have disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification.” There have been changes in the calculation methodology, but this change occurred in data for both 2005-06 and 2006-07. There are no other changes in policy, funding, or staffing that account for these levels. There are no geographic or size variable that account for this disproportionality.

CDE has continued to work with the WRRC to analyze data in order to identify districts with promising practices.  CDE has sponsored presentation of that information to the SELPA organization and to local administrator groups in various locales. The dissemination of data and surveys, alone, has created a great deal of attention to issues of disproportionality. None of these are as significant as the Superintendent’s initiative on Closing the Achievement Gap which has included the establishment of a special work group in the CDE and a major conference in November.

As noted in Indicator #9, the CDE has added a practices review to the review of policies, procedures and practices related to identification. Considerable discussion has taken place in various stakeholder groups about the issues of practices. Samples from other states and from the National Center on Culturally Responsive Education Systems (NCCRESt) have been reviewed. The existing practices review may be responsible for the identification of more noncompliance, but does not necessarily get at the root causes of these issues. Stakeholders feel very strongly that this issue is not a special education issue, alone, and requires substantial change in general education policies, procedures and practices as well. California will continue to refine its review of practices through participation in the Superintendents Closing the Achievement Gap initiative and in conjunction with stakeholder workgroups.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

The following activities will continue:

| CONTINUING ACTIVITES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Work with Western Regional Resource Center (WRRC) and other Federal contractors to identify and disseminate research-based practices related to preventing disproportionate representation and to address the interface between eligibility and disproportionality. | 2005-2010 Ongoing | Federal contractors (WRRC) CDE staff Type: Technical Assistance |
| Work with WRRC to conduct a study of promising practices among districts that are not disproportionate and achieve successful student outcomes on statewide testing. | January 2007 to January 2008 | Federal contractors (WRRC) CDE staff Type: Technical Assistance |
| Establish a definition of significant disproportionality | July 2007 | CDE Staff, California State Board of Education Type: Monitoring and Enforcement |
| Identify districts that are significantly disproportionate, using existing instruments and procedures to test new definition. | July 2007 | CDE Staff, OSEP Type: Monitoring and Enforcement |
| Refine policies, procedures, and practices instruments. | October 2007 and annually thereafter | CDE Staff, OSEP Type: Monitoring and Enforcement |
| Use refined procedures to Identify districts with significant disproportionality and establish plans for supervision and technical assistance | July 2008 | CDE staff Type: Monitoring and Enforcement |
| Reconvene Larry P. Task Force to reexamine testing matrix and publish revised matrix. | July 2007 to July 2008 | CDE staff, field experts Larry P. Task Force CDE staff Type: Special Project Policy Development |

The following activities will be added:

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Improvement Activities | Timelines | Resources and Type |
| Convene special meetings of ISES and SELPA stakeholder groups to develop two types of practices reviews: - Compliance based to address IDEA monitoring requirements - Research based to address improvement needed outside of a compliance context | January 2008 to June 2010 | CDE staff and Contractors, Western Regional Resource Center |
| Incorporate preliminary self review and improvement planning modules into monitoring software, based on NCCRESt | June 2008 | CDE staff and Contractors |
| Participate in Superintendents Closing the Achievement Gap initiative: - Assign staff to participate - Provide information from SPP and APR - Assist in the development of products and materials - Secure general education input and participation in the development of district level practices review. | June 2007 to June 2010 | CDE staff and Contractors |

Appendix 1

Review Protocol and Instructions

INSTRUCTIONS: DISPROPORTIONATE REPRESENTATION

The review of:  	SPPI 9:  Disproportionality Overall

SPPI 10: Disproportionality - By Federal Ethnic Category by Disability

- To conduct the Review of Policies and Procedures:

- Use the CDE provided protocol to conduct a review of the district’s Policies and Procedures relative to the disproportionality of special education students overall and by federal ethnic category by disability of special education students.

- Conduct the examination of the district’s Policies and Procedures using the items listed under the heading Policies and Procedures.

- Mark each item reviewed as either Compliant or Non-Compliant depending on whether it is determined that there is or is not a Policy or Procedure that addresses that item.

- Please submit one (1) completed Policies and Procedures review protocol to CDE.

NOTE:	If your district conducted a Verification Review (VR) or a Special Education Self-Review (SESR) during 2006-07, please submit a letter or email advising CDE that the Policies and Procedures review findings and/or information previously reported to CDE remains accurate and complete. If this relates to your district you do not need to conduct another policies and procedures review.

- To conduct the Practices Review:

- Use the CDE provided protocol to conduct a review of the district’s practices relative to the identification of the ethnic distribution of students. For SPPI 9, select student records for those ethnicities identified as over and/or underrepresented. For SPPI 10 select student records in the six (6) special education eligibility categories – Specific Learning Disability, Mental Retardation, Speech, Language Instruction, Other Health Impairment, Emotional Disturbance, and Autism

- Select a sample of fifteen (15) records of district special education students.

- Using the CDE provided protocol, examine each student record and mark each item reviewed as either Compliant or Non-Compliant.

- For each reviewed record that has Non-Compliant findings, a separate form, STUDENT CORRECTIVE ACTION FORM, must be completed. The form identifies: the student by name; his/her date of birth; the item number found non-compliant; the finding made; the planned corrective action; and the date the correction was made

This form, if applicable, must be attached to each student’s review protocol.

- Please submit one review protocol for each student record reviewed – for a total of fifteen (15). Attach to each protocol, when there are non-compliant findings, a copy of the STUDENT CORRECTIVE ACTION FORM.

NOTE:	If the district conducted a Verification Review (VR) or a Special Education Self-Review (SESR) during 2006-07, this review does not need to be completed. Instead, please submit to CDE a signed assurance statement that the review was completed and if Non-compliant issues were found that all corrections were made

Appendix 1

Policies, Procedures and Practices Review protocol for 2006-07

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Practices Review |  |  |  |  |  |  |  |
| Assessment |  |  |  |  |  |  |  |
| Assessment Plan |  |  |  |  |  |  |  |
| 2-1-1.3 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes the individual's primary language and language proficiency status (LEP/FEP) for English language learners? | The child's primary language and language proficiency in English must be indicated in the Assessment Plan. | The Assessment Plan must include this statement. | 30 EC 52164.15, CCR 3022. |  |  |  |
| 2-1-1.6 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes a description of alternative means that will be used to assess language impairment or specific learning disabilities when standard tests are considered invalid? | Plan must include description of alternate means if alternate means were used to assess child. | The plan should specify the methods that will be used as an alternative. Look for expected language performance level and/or severe discrepancy when standardized tests are considered to be invalid and description of alternative means. | 5 CCR 3030(c)(4)(B), 5 CCR 3030 (j)(4)(B). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Procedures |  |  |  |  |  |  |  |
| 2-2-2.2 | Is there evidence that the current assessment is comprehensive and that materials and procedures used to assess a student with limited English proficiency are selected and administered to ensure that they measure the extent to which the student has a disability and needs special education, rather than measuring the student’s English proficiency?. | Policies and procedures address selection of materials and procedures for assessment of English learners. In the student record, the Assessment Report references the LEP status, the primary language and the implications upon the assessment. | Review the Assessment Report for references to the LEP status, the primary language and the validity of assessment materials and procedures. Interview assessors. | 34 CFR 300.304(c)(1)(i). |  |  |  |
| 2-2-5.2 | Do assessment procedures ensure that IQ tests are not administered to African- American students? | Student records indicate that an IQ measure was not administered to an African-American student. | Review the plan, Assessment Report and other assessment information. Determine if the Assessment Plan indicated alternative assessments to obtain information about cognitive development. Were the alternative assessments administered as appropriate? Interview staff and parents. | Larry P. vs. Riles. |  |  |  |
| 2-2-5.3 | Do assessment procedures ensure that materials are used to assess specific areas of educational need and do not rely merely on procedures that provide a single IQ score? | Student record documents use of multiple types of measures as indicated. | Description of assessment materials on the Assessment Plan and within the Assessment Report(s). Identification of a variety of sources including standardized tests, teacher report, health and developmental history, medical records, social and cultural background, adaptive behavior. The present level of performance on the IEP reflects the assessments. | 20 USC 1414 (b)(2), 34 CFR 300.304(c)(2), 30 EC 56320(c). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Report |  |  |  |  |  |  |  |
| 2-3-1.1 | Does the written assessment report include the results of tests administered in the student's primary language by qualified personnel? | Assessment Report must include documentation of language of assessment for children whose primary language is not English. | Look for a statement on the Assessment Report and on the IEP that addresses how the assessment addressed the student whose primary language is not English. | EC 563205 CCR 3023(a). |  |  |  |
| 2-3-1.2 | If a test was administered through an interpreter, does the written report include a statement regarding validity of the assessment? | Report must include notation that validity may have been affected if translator is used. | Look for a statement of validity in the Assessment Report when appropriate. For example, when an interpreter is used or alternative assessments were used. | 20 USC 1414(b)(3)(A)(iii), 5 CCR 3023(a). |  |  |  |
| IEP Process | If neither parent can attend the IEP meeting does the LEA use other means to ensure parent participation including individual or conference phone calls? |  |  |  |  |  |  |
| IEP - Additional Requirements |  |  |  |  |  |  |  |
| 3-5-8 | For a student with limited English proficiency (English language learners (ELL)), does the IEP team consider the language needs of the student as such needs relate to the student’s IEP and does the IEP include linguistically appropriate goals and objectives. | If appropriate, IEP consideration must be evident. | Look in the Assessment Report and/or any other documentation that the LEA has assessed the child's language needs. Look in the IEP for a statement that the IEP team has considered the child's language needs. Look for linguistically appropriate goals and objectives. | 20 USC 1414(d)(3)(B)(ii), 34 CFR 300.324 (a)(2)(ii), 30 EC 56345(b)(2) & 56341.1(b)(2). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Procedural Safeguards |  |  |  |  |  |  |  |
| Written Prior Notice |  |  |  |  |  |  |  |
| 10-2-1 | Are all students whose home language survey indicates a language other than English assessed using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must assess any pupil whose native language is other than English as determined by the home language survey for English language proficiency. | Review policies and procedures. Review files of students with disabilities whose home language is other than English to see if their English language proficiency has been assessed. Interview administrators and staff. | EC 306(a)5 CCR 11511(a). |  |  |  |
| 10-2-2 | Does the LEA assess all students identified as English learners annually using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must annually assess all children identified as English learners and maintain a record of all pupils who participate in each administration of the CELDT. | Review policies and procedures to ensure that children with disabilities who are English learners are assessed. Interview staff and administrators about participation of children with disabilities in the CELDT. | EC 3135 CCR 11511, 5 CCR 11512. |  |  |  |
| 10-2-3 | In developing the IEP for students identified as English learners, does the IEP team consider the results of the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The IEP team must consider the results of the child's performance on statewide assessment programs and must consider the language needs of English learners as those needs relate to the IEP. | Review district policies and procedures. Review the child's Assessment Report and/or IEP (present performance, IEP notes) to determine if CELDT results were part of the IEP team consideration. Interview administrators, staff and parents about the IEP team. | 34CFR 300.324(a). |  |  |  |
| 10-2-4 | Does the IEP of students identified as English learners include a determination of whether CELDT will be administered with or without modifications or accommodations, or whether English proficiency will be measured using an alternate assessment? | The IEP must include a determination of whether the CELDT is administered with or without modifications, accommodations or through an alternate means. | Review district policies and procedures. Review the child's IEP (including IEP notes) to determine if the IEP team determined how the CELDT would be administered. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.320, 5 CCR 11516. |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 10-2-5 | Does the IEP of students identified as English learners include activities which lead to the development of English language proficiency. | The IEP must include linguistically appropriate goals, objectives, programs and services including English language development activities. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development in IEPs. | 34CFR 300.320, 5 CCR 3001. |  |  |  |
| 10-2-6 | Does the IEP of students identified as English learners include instructional systems which meet the language development needs of the student and ensure access to the general education curriculum? | The IEP must include linguistically appropriate goals, objectives, programs and services including instructional systems which meet the language development needs of the student. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development and instruction in the general curriculum for English learners with disabilities. Review the IEP for language of instruction. | 34CFR 300.320, 6 CCR 3001. |  |  |  |
| Policies and Procedure Review |  |  |  |  |  |  |  |
| Assessment |  |  |  |  |  |  |  |
| Assessment Plan |  |  |  |  |  |  |  |
| 2-1-1.3 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes the individual's primary language and language proficiency status (LEP/FEP) for English language learners? | The child's primary language and language proficiency in English must be indicated in the Assessment Plan. | The Assessment Plan must include this statement. | 30 EC 52164.15, CCR 3022. |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Procedures |  |  |  |  |  |  |  |
| 2-2-2.2 | Is there evidence that the current assessment is comprehensive and that materials and procedures used to assess a student with limited English proficiency are selected and administered to ensure that they measure the extent to which the student has a disability and needs special education, rather than measuring the student’s English proficiency?. | Policies and procedures address selection of materials and procedures for assessment of English learners. In the student record, the Assessment Report references the LEP status, the primary language and the implications upon the assessment. | Review the Assessment Report for references to the LEP status, the primary language and the validity of assessment materials and procedures. Interview assessors. | 34 CFR 300.304(c)(1)(i). |  |  |  |
| 2-2-5.2 | Do assessment procedures ensure that IQ tests are not administered to African- American students? | Student records indicate that an IQ measure was not administered to an African-American student. | Review the plan, Assessment Report and other assessment information. Determine if the Assessment Plan indicated alternative assessments to obtain information about cognitive development. Were the alternative assessments administered as appropriate? Interview staff and parents. | Larry P. vs. Riles. |  |  |  |
| 2-2-5.3 | Do assessment procedures ensure that materials are used to assess specific areas of educational need and do not rely merely on procedures that provide a single IQ score? | Student record documents use of multiple types of measures as indicated | Description of assessment materials on the Assessment Plan and within the Assessment Report(s). Identification of a variety of sources including standardized tests, teacher report, health and developmental history, medical records, social and cultural background, adaptive behavior. The present level of performance on the IEP reflects the assessment | 20 USC 1414 (b)(2), 34 CFR 300.304(c)(2), 30 EC 56320(c). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IEP Process | If neither parent can attend the IEP meeting does the LEA use other means to ensure parent participation including individual or conference phone calls? |  |  |  |  |  |  |  |
| IEP - Additional Requirements |  |  |  |  |  |  |  |  |
| 3-5-8 | For a student with limited English proficiency (English language learners (ELL)), does the IEP team consider the language needs of the student as such needs relate to the student’s IEP and does the IEP include linguistically appropriate goals, objectives, programs and services? | If appropriate, IEP consideration must be evident. | Look in the Assessment Report and/or any other documentation that the LEA has assessed the child's language needs. Look in the IEP for a statement that the IEP team has considered the child's language needs. Look for linguistically appropriate goals, objectives, programs and services? | 20 USC 1414(d)(3)(B)(ii), 34 CFR 300.324 (a)(2)(ii), 30 EC 56345(b)(2) & 56341.1(b)(2). |  |  |  |  |
| Procedural Safeguards |  |  |  |  |  |  |  |  |
| Written Prior Notice |  |  |  |  |  |  |  |  |
| 10-2-1 | Are all students whose home language survey indicates a language other than English assessed using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must assess any pupil whose native language is other than English as determined by the home language survey for English language proficiency. | Review policies and procedures. Review files of students with disabilities whose home language is other than English to see if their English language proficiency has been assessed. Interview administrators and staff. | EC 306(a)5 CCR 11511(a). |  |  |  |  |
| 10-2-2 | Does the LEA assess all students identified as English learners annually using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must annually assess all children identified as English learners and maintain a record of all pupils who participate in each administration of the CELDT. | Review policies and procedures to ensure that children with disabilities who are English learners are assessed. Interview staff and administrators about participation of children with disabilities in the CELDT. | EC 3135 CCR 11511, 5 CCR 11512. |  |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10-2-3 | In developing the IEP for students identified as English learners, does the IEP team consider the results of the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The IEP team must consider the results of the child's performance on statewide assessment programs and must consider the language needs of English learners as those needs relate to the IEP. | Review district policies and procedures. Review the child's Assessment Report and/or IEP (present performance, IEP notes) to determine if CELDT results were part of the IEP team consideration. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.324(a). |  |  |  |  |
| 10-2-4 | Does the IEP of students identified as English learners include a determination of whether CELDT will be administered with or without modifications or accommodations, or whether English proficiency will be measured using an alternate assessment? | The IEP must include a determination of whether the CELDT is administered with or without modifications, accommodations or through an alternate means. | Review district policies and procedures. Review the child's IEP (including IEP notes) to determine if the IEP team determined how the CELDT would be administered. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.320, 5 CCR 11516. |  |  |  |  |
| 10-2-5 | Does the IEP of students identified as English learners include activities which lead to the development of English language proficiency. | The IEP must include linguistically appropriate goals, objectives, programs and services including English language development activities. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development in IEPs. | 34CFR 300.320, 5 CCR 3001. |  |  |  |  |
| 10-2-6 | Does the IEP of students identified as English learners include instructional systems which meet the language development needs of the student and ensure access to the general education curriculum? | The IEP must include linguistically appropriate goals, objectives, programs and services including instructional systems which meet the language development needs of the student. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development and instruction in the general curriculum for English learners with disabilities. Review the IEP for language of instruction and instructional delivery systems. | 34CFR 300.320, 6 CCR 3001. |  |  |  |  |

Appendix 2

2005-06 Review of Policies and Procedures

INSTRUCTIONS: DISPROPORTIONATE REPRESENTATION

The review of:  	SPPI 10: Disproportionality - By Federal Ethnic Category by Disability

- To conduct the Review of Policies and Procedures:

- Use the CDE provided protocol to conduct a review of the district’s Policies and Procedures relative to the disproportionality of special education students overall and by federal ethnic category by disability of special education students.

- Conduct the examination of the district’s Policies and Procedures using the items listed under the heading Policies and Procedures.

- Mark each item reviewed as either Compliant or Non-Compliant depending on whether it is determined that there is or is not a Policy or Procedure that addresses that item.

- Please submit one (1) completed Policies and Procedures review protocol to CDE.

NOTE:	If your district conducted a Verification Review (VR) or a Special Education Self-Review (SESR) during 2006-07, please submit a letter or email advising CDE that the Policies and Procedures review findings and/or information previously reported to CDE remains accurate and complete. If this relates to your district you do not need to conduct another policies and procedures review.

- To conduct the Practices Review:

- Use the CDE provided protocol to conduct a review of the district’s practices relative to the identification of the ethnic distribution of students. For SPPI 9, select student records for those ethnicities identified as over and/or underrepresented. For SPPI 10 select student records in the six (6) special education eligibility categories – Specific Learning Disability, Mental Retardation, Speech, Language Instruction, Other Health Impairment, Emotional Disturbance, and Autism

- Select a sample of fifteen (15) records of district special education students.

- Using the CDE provided protocol, examine each student record and mark each item reviewed as either Compliant or Non-Compliant.

- For each reviewed record that has Non-Compliant findings, a separate form, STUDENT CORRECTIVE ACTION FORM, must be completed. The form identifies: the student by name; his/her date of birth; the item number found non-compliant; the finding made; the planned corrective action; and the date the correction was made

- This form, if applicable, must be attached to each student’s review protocol.

- Please submit one review protocol for each student record reviewed – for a total of fifteen (15). Attach to each protocol, when there are non-compliant findings, a copy of the STUDENT CORRECTIVE ACTION FORM.

NOTE:	If the district conducted a Verification Review (VR) or a Special Education Self-Review (SESR) during 2006-07, this review does not need to be completed. Instead, please submit to CDE a signed assurance statement that the review was completed and if Non-compliant issues were found that all corrections were made.

Appendix 2

2005-06 Review of Policies and Procedures

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Practices Review |  |  |  |  |  |  |  |
| Assessment |  |  |  |  |  |  |  |
| Assessment Plan |  |  |  |  |  |  |  |
| 2-1-1.3 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes the individual's primary language and language proficiency status (LEP/FEP) for English language learners? | The child's primary language and language proficiency in English must be indicated in the Assessment Plan. | The Assessment Plan must include this statement. | 30 EC 52164.15, CCR 3022. |  |  |  |
| 2-1-1.6 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes a description of alternative means that will be used to assess language impairment or specific learning disabilities when standard tests are considered invalid? | Plan must include description of alternate means if alternate means were used to assess child. | The plan should specify the methods that will be used as an alternative. Look for expected language performance level and/or severe discrepancy when standardized tests are considered to be invalid and description of alternative means. | 5 CCR 3030(c)(4)(B), 5 CCR 3030 (j)(4)(B). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Procedures |  |  |  |  |  |  |  |
| 2-2-2.2 | Is there evidence that the current assessment is comprehensive and that materials and procedures used to assess a student with limited English proficiency are selected and administered to ensure that they measure the extent to which the student has a disability and needs special education, rather than measuring the student’s English proficiency?. | Policies and procedures address selection of materials and procedures for assessment of English learners. In the student record, the Assessment Report references the LEP status, the primary language and the implications upon the assessment. | Review the Assessment Report for references to the LEP status, the primary language and the validity of assessment materials and procedures. Interview assessors. | 34 CFR 300.304(c)(1)(i). |  |  |  |
| 2-2-5.2 | Do assessment procedures ensure that IQ tests are not administered to African- American students? | Student records indicate that an IQ measure was not administered to an African-American student. | Review the plan, Assessment Report and other assessment information. Determine if the Assessment Plan indicated alternative assessments to obtain information about cognitive development. Were the alternative assessments administered as appropriate? Interview staff and parents. | Larry P. vs. Riles. |  |  |  |
| 2-2-5.3 | Do assessment procedures ensure that materials are used to assess specific areas of educational need and do not rely merely on procedures that provide a single IQ score? | Student record documents use of multiple types of measures as indicated. | Description of assessment materials on the Assessment Plan and within the Assessment Report(s). Identification of a variety of sources including standardized tests, teacher report, health and developmental history, medical records, social and cultural background, adaptive behavior. The present level of performance on the IEP reflects the assessments. | 20 USC 1414 (b)(2), 34 CFR 300.304(c)(2), 30 EC 56320(c). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Report |  |  |  |  |  |  |  |
| 2-3-1.1 | Does the written assessment report include the results of tests administered in the student's primary language by qualified personnel? | Assessment Report must include documentation of language of assessment for children whose primary language is not English. | Look for a statement on the Assessment Report and on the IEP that addresses how the assessment addressed the student whose primary language is not English. | EC 563205 CCR 3023(a). |  |  |  |
| 2-3-1.2 | If a test was administered through an interpreter, does the written report include a statement regarding validity of the assessment? | Report must include notation that validity may have been affected if translator is used. | Look for a statement of validity in the Assessment Report when appropriate. For example, when an interpreter is used or alternative assessments were used. | 20 USC 1414(b)(3)(A)(iii), 5 CCR 3023(a). |  |  |  |
| IEP Process | If neither parent can attend the IEP meeting does the LEA use other means to ensure parent participation including individual or conference phone calls? |  |  |  |  |  |  |
| IEP - Additional Requirements |  |  |  |  |  |  |  |
| 3-5-8 | For a student with limited English proficiency (English language learners (ELL)), does the IEP team consider the language needs of the student as such needs relate to the student’s IEP and does the IEP include linguistically appropriate goals and objectives. | If appropriate, IEP consideration must be evident. | Look in the Assessment Report and/or any other documentation that the LEA has assessed the child's language needs. Look in the IEP for a statement that the IEP team has considered the child's language needs. Look for linguistically appropriate goals and objectives. | 20 USC 1414(d)(3)(B)(ii), 34 CFR 300.324 (a)(2)(ii), 30 EC 56345(b)(2) & 56341.1(b)(2). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Procedural Safeguards |  |  |  |  |  |  |  |
| Written Prior Notice |  |  |  |  |  |  |  |
| 10-2-1 | Are all students whose home language survey indicates a language other than English assessed using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must assess any pupil whose native language is other than English as determined by the home language survey for English language proficiency. | Review policies and procedures. Review files of students with disabilities whose home language is other than English to see if their English language proficiency has been assessed. Interview administrators and staff. | EC 306(a)5 CCR 11511(a). |  |  |  |
| 10-2-2 | Does the LEA assess all students identified as English learners annually using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must annually assess all children identified as English learners and maintain a record of all pupils who participate in each administration of the CELDT. | Review policies and procedures to ensure that children with disabilities who are English learners are assessed. Interview staff and administrators about participation of children with disabilities in the CELDT. | EC 3135 CCR 11511, 5 CCR 11512. |  |  |  |
| 10-2-3 | In developing the IEP for students identified as English learners, does the IEP team consider the results of the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The IEP team must consider the results of the child's performance on statewide assessment programs and must consider the language needs of English learners as those needs relate to the IEP. | Review district policies and procedures. Review the child's Assessment Report and/or IEP (present performance, IEP notes) to determine if CELDT results were part of the IEP team consideration. Interview administrators, staff and parents about the IEP team. | 34CFR 300.324(a). |  |  |  |
| 10-2-4 | Does the IEP of students identified as English learners include a determination of whether CELDT will be administered with or without modifications or accommodations, or whether English proficiency will be measured using an alternate assessment? | The IEP must include a determination of whether the CELDT is administered with or without modifications, accommodations or through an alternate means. | Review district policies and procedures. Review the child's IEP (including IEP notes) to determine if the IEP team determined how the CELDT would be administered. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.320, 5 CCR 11516. |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 10-2-5 | Does the IEP of students identified as English learners include activities which lead to the development of English language proficiency. | The IEP must include linguistically appropriate goals, objectives, programs and services including English language development activities. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development in IEPs. | 34CFR 300.320, 5 CCR 3001. |  |  |  |
| 10-2-6 | Does the IEP of students identified as English learners include instructional systems which meet the language development needs of the student and ensure access to the general education curriculum? | The IEP must include linguistically appropriate goals, objectives, programs and services including instructional systems which meet the language development needs of the student. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development and instruction in the general curriculum for English learners with disabilities. Review the IEP for language of instruction. | 34CFR 300.320, 6 CCR 3001. |  |  |  |
| Policies and Procedure Review |  |  |  |  |  |  |  |
| Assessment |  |  |  |  |  |  |  |
| Assessment Plan |  |  |  |  |  |  |  |
| 2-1-1.3 | Does the LEA provide the parent with an Assessment Plan within 15 days of the referral for any proposed evaluation that includes the individual's primary language and language proficiency status (LEP/FEP) for English language learners? | The child's primary language and language proficiency in English must be indicated in the Assessment Plan. | The Assessment Plan must include this statement. | 30 EC 52164.15, CCR 3022. |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assessment Procedures |  |  |  |  |  |  |  |
| 2-2-2.2 | Is there evidence that the current assessment is comprehensive and that materials and procedures used to assess a student with limited English proficiency are selected and administered to ensure that they measure the extent to which the student has a disability and needs special education, rather than measuring the student’s English proficiency?. | Policies and procedures address selection of materials and procedures for assessment of English learners. In the student record, the Assessment Report references the LEP status, the primary language and the implications upon the assessment. | Review the Assessment Report for references to the LEP status, the primary language and the validity of assessment materials and procedures. Interview assessors. | 34 CFR 300.304(c)(1)(i). |  |  |  |
| 2-2-5.2 | Do assessment procedures ensure that IQ tests are not administered to African- American students? | Student records indicate that an IQ measure was not administered to an African-American student. | Review the plan, Assessment Report and other assessment information. Determine if the Assessment Plan indicated alternative assessments to obtain information about cognitive development. Were the alternative assessments administered as appropriate? Interview staff and parents. | Larry P. vs. Riles. |  |  |  |
| 2-2-5.3 | Do assessment procedures ensure that materials are used to assess specific areas of educational need and do not rely merely on procedures that provide a single IQ score? | Student record documents use of multiple types of measures as indicated | Description of assessment materials on the Assessment Plan and within the Assessment Report(s). Identification of a variety of sources including standardized tests, teacher report, health and developmental history, medical records, social and cultural background, adaptive behavior. The present level of performance on the IEP reflects the assessment | 20 USC 1414 (b)(2), 34 CFR 300.304(c)(2), 30 EC 56320(c). |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IEP Process | If neither parent can attend the IEP meeting does the LEA use other means to ensure parent participation including individual or conference phone calls? |  |  |  |  |  |  |  |
| IEP - Additional Requirements |  |  |  |  |  |  |  |  |
| 3-5-8 | For a student with limited English proficiency (English language learners (ELL)), does the IEP team consider the language needs of the student as such needs relate to the student’s IEP and does the IEP include linguistically appropriate goals, objectives, programs and services? | If appropriate, IEP consideration must be evident. | Look in the Assessment Report and/or any other documentation that the LEA has assessed the child's language needs. Look in the IEP for a statement that the IEP team has considered the child's language needs. Look for linguistically appropriate goals, objectives, programs and services? | 20 USC 1414(d)(3)(B)(ii), 34 CFR 300.324 (a)(2)(ii), 30 EC 56345(b)(2) & 56341.1(b)(2). |  |  |  |  |
| Procedural Safeguards |  |  |  |  |  |  |  |  |
| Written Prior Notice |  |  |  |  |  |  |  |  |
| 10-2-1 | Are all students whose home language survey indicates a language other than English assessed using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must assess any pupil whose native language is other than English as determined by the home language survey for English language proficiency. | Review policies and procedures. Review files of students with disabilities whose home language is other than English to see if their English language proficiency has been assessed. Interview administrators and staff. | EC 306(a)5 CCR 11511(a). |  |  |  |  |
| 10-2-2 | Does the LEA assess all students identified as English learners annually using the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The district must annually assess all children identified as English learners and maintain a record of all pupils who participate in each administration of the CELDT. | Review policies and procedures to ensure that children with disabilities who are English learners are assessed. Interview staff and administrators about participation of children with disabilities in the CELDT. | EC 3135 CCR 11511, 5 CCR 11512. |  |  |  |  |

| Item No | Compliance Test | Compliance Standard | Other Guidance | Legal References | Compliant | Noncompliant | Not Applicable |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10-2-3 | In developing the IEP for students identified as English learners, does the IEP team consider the results of the California English Language Development Test (CELDT) or an alternate to determine English language proficiency? | The IEP team must consider the results of the child's performance on statewide assessment programs and must consider the language needs of English learners as those needs relate to the IEP. | Review district policies and procedures. Review the child's Assessment Report and/or IEP (present performance, IEP notes) to determine if CELDT results were part of the IEP team consideration. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.324(a). |  |  |  |  |
| 10-2-4 | Does the IEP of students identified as English learners include a determination of whether CELDT will be administered with or without modifications or accommodations, or whether English proficiency will be measured using an alternate assessment? | The IEP must include a determination of whether the CELDT is administered with or without modifications, accommodations or through an alternate means. | Review district policies and procedures. Review the child's IEP (including IEP notes) to determine if the IEP team determined how the CELDT would be administered. Interview administrators, staff and parents about the IEP team process. | 34CFR 300.320, 5 CCR 11516. |  |  |  |  |
| 10-2-5 | Does the IEP of students identified as English learners include activities which lead to the development of English language proficiency. | The IEP must include linguistically appropriate goals, objectives, programs and services including English language development activities. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development in IEPs. | 34CFR 300.320, 5 CCR 3001. |  |  |  |  |
| 10-2-6 | Does the IEP of students identified as English learners include instructional systems which meet the language development needs of the student and ensure access to the general education curriculum? | The IEP must include linguistically appropriate goals, objectives, programs and services including instructional systems which meet the language development needs of the student. | Review the students IEP. Interview staff and administrators to determine how IEP teams assess and address English language development and instruction in the general curriculum for English learners with disabilities. Review the IEP for language of instruction and instructional delivery systems. | 34CFR 300.320, 6 CCR 3001. |  |  |  |  |

Monitoring Priority: Effective General Supervision Part B / Child Find

Indicator 11:  Percent of children with parental consent to evaluate, who were evaluated within 60 days (or State established timeline). (20 U.S.C. 1416(a)(3)(B))

Measurement: Measurement: - # of children for whom parental consent to evaluate was received. - # determined not eligible whose evaluations were completed within 60 days (or State established timeline). - # determined eligible whose evaluations were completed within 60 days (or State established timeline). Account for children included in a but not included in b or c. Indicate the range of days beyond the timeline when the evaluation was completed and any reasons for the delays. Percent = [(b + c) divided by (a)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | Eligibility determinations will be completed within 60 days for 100 percent of children for who parental consent to evaluate was received. |

Actual Target Data for (FFY 2006):

Table 11a summarizes the target data for FFY 2006 (2006-07)

## Table 11a

Actual Target Data for Initial Evaluation

| Measurement Item | Target Data |
| --- | --- |
| Number of children for whom parental consent to evaluate was received. | 124,097 |
| - Number determined not eligible whose evaluations were completed within 60 days (or State established timeline). | 11,915 |
| - Number determined eligible whose evaluations were completed within 60 days (or State established timeline). | 78,613 |
| Percent of children with parental consent to evaluate, who were evaluated within 60 days. Percent = [(b + c) divided by (a)] times 100. | 72.95% |

# These data were calculated using new CASEMIS data fields related to Referral Date, Parent Consent Date, and Initial Evaluation Date. Determination of eligibility was made using the Plan Type field which includes the type of plan a student has (IEP, IFSP, ISP) if the student is eligible or no plan if the student is determined ineligible.

## Table 11b

Excerpt from CASEMIS Table A - CASEMIS Data Fields for Indicator 11

| No. | Field | Type | Length | Verified | New |
| --- | --- | --- | --- | --- | --- |
| A-22 | REFR_DATE | Date | 8 | Yes | Yes |
| A-24 | PRNT_CSNT | Date | 8 | Yes | Yes |
| A-25 | INIT_EVAL | Date | 8 | Yes | Yes |
| A-26 | PLAN_TYPE | Character | 2 | Yes | No |

# When data were missing or unclear using Init_Eval date, the Last_IEP date was used instead (as it is the IEP team that determines eligibility).

Table 11c

Range of Days Beyond 60 days

| Date Range | Number | % of All Consents |
| --- | --- | --- |
| 1 to 30 days | 22,718 | 18.31% |
| 31 to 60 days | 6,474 | 5.22% |
| 61 to 90 days | 2,518 | 2.03% |
| 91 to 120 days | 939 | 0.76% |
| 121 to 150 days | 382 | 0.31% |
| Over 150 days | 412 | 0.33% |
| No Dates Provided | 11 | 0.01% |
| Before Consent Date | 115 | 0.09% |

Table 11c depicts the range of days beyond 60 days that evaluations were completed. The bulk of the late evaluations were completed within 30 days of the deadline. There were also some data anomalies – records with consent dates, but no evaluation date; evaluation dates before the consent date.

Failure to meet the 60 day timeline calculations may be due to several things – noncompliance, inaccurate data entry, or the inability to determine students whose timelines were affected by a break between regular school sessions. Under California Education Code (30 EC 56043(f)(1)):

(f) (1) An individualized education program required as a result of an assessment of a pupil shall be developed within a total time not to exceed 60 calendar days, not counting days between the pupil's regular school sessions, terms, or days of school vacation in excess of five schooldays, from the date of receipt of the parent's or guardian's written consent for assessment, unless the parent or guardian agrees, in writing, to an extension, pursuant to Section 56344.

This affects students who are referred for initial evaluation in June, just before the summer break and those who go “off track” in year round programs. While the calculations used for this APR took into account Parent Consent dates in June as a part of the calculation of timely evaluation, the number of students who were “late” due to being “off track” in year round programs could not be determined using the current data set. As a result, the number of students not evaluated in a timely way is inflated to some extent.

Analysis of LEA level findings Of the 1,020 districts reporting referrals of students for evaluation, 519 were of sufficient size (N>19) to calculate a percentage of students with parent consent who were evaluated within 60 days. The highest reported percentage was 100% (6 LEAs) and lowest was 20% (1 LEA).  The median percentage was 76.93%. Analysis of values by district size and geography indicated that there were no differences attributable to size or geography.

### Monitoring Data

All Verification and Special Education Self Reviews include the following item:

| Item No. | Compliance Test |
| --- | --- |
| 3-1-1.1 | Is there an IEP developed and implemented for each student (including students placed by the LEA in a private school or facility), within 60 days of obtaining written parental consent to the assessment plan? |

Noncompliance findings reported in 2006-07 There were 220 districts that had findings reported in 2006-07. Of those 220 districts, there were 36 districts reported to have systemic noncompliance related to the initial evaluation timeline. At the student level, there were 720 findings of noncompliance reported in 149 districts. There were a total of 2535 students reviewed in 2006-07 related to their initial evaluations. 71.6% of students whose records were reviewed met the 60-day timeline.

Correction of noncompliance identified in 2005-06. In the FFY 2005 Annual Performance Report, it was reported that there were 214 districts and 6,702 student records reviewed. These figures were based on the year that the review was initiated, not on the year when the findings were reported to the district. As a result, the figures for 2005-06 need to be amended. There were a total of 254 districts that had findings reported in 2005-06. Of those there were 43 districts with systemic findings of noncompliance related to the timeline for initial evaluation. At the student level, there were 471 findings of noncompliance in 99 districts. There were a total of 2804 students reviewed in 2006-07 related to their initial evaluations. 83.2% of students whose records were reviewed met the 60-day timeline. Of the 471 student level findings, there most were not correctible (the timeline was exceeded but the evaluation was completed). Of those requiring correction, all have been corrected, though ten exceeded the one year timeline.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Development and Implementation of new CASEMIS fields, including software development, statewide training and ongoing technical assistance. | 2005-2007 | CDE staff |

As noted above, only 72.95% of students with parental consent to evaluate were evaluated within 60 days. This is confirmed by the monitoring data (71.6% on time). While some of the students identified as late may have been due to data entry errors/misunderstandings (these are first time fields), others may have been due to breaks between regular school sessions for those students in year round school programs. Nonetheless, the percentage is significantly lower than the compliance target of 100%.

Based on monitoring data, there is a decrease in the percent of students identified in a timely way (82.2 in 2005-06 to 76.1 percent in 2006-07). Base on the LEA data analysis, the concern is a statewide concern and cannot be attributed to changes in policy, funding, or data collection. Personnel shortages, on the other hand, could be one source of delay. The California Speech and Hearing Association and the Directors of SELPAs have supported legislation to address shortages in speech therapists, occupational and physical therapists, and other related services personnel. To some extent, initial evaluations could be due to high caseloads for assessment personnel who are short supply.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Explore Web based applications for all components of the monitoring system including 60-day evaluation timeline. | 2005-2010 | CDE staff Type: Monitoring, Training and Technical Assistance |
| Examine and analyze data from compliance complaints and all monitoring activities. Determine areas of need for possible technical assistance in addition to correction of noncompliance. | 2005-2010 | CDE staff Type: Monitoring and Technical Assistance, enforcement as needed |

Three types of activities are proposed to bring California into compliance with this indicator: 1) improve data collection and analysis and 2) increased compliance awareness and technical assistance and 3) support to fill personnel shortages. New activities related to this indicator are listed below:

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activity | Timeline | Resources |
| Prepare and install initial evaluation compliance reports into the CASEMIS software to enable districts and SELPAs to self-monitor. | June 2008 | CDE Staff |
| Prepare and send noncompliance-finding letters based on CASEMIS data to augment Verification and Self Review monitoring findings. | March 2008 | CDE Staff |
| Prepare analysis of existing patterns of recording date information and emphasize in SELPA Director meetings and biannual CASEMIS training. | March 2008 | CDE Staff and contractors |
| Prepare and send statewide letter regarding the requirements related to initial evaluation. Post initial evaluation policy and technical assistance information on CDE website. | March 2008 | CDE Staff and contractors |
| Meet with the California Speech and Hearing Association, California School Psychologist Association, SELPA Directors, and other related service organizations to explore personnel shortages and develop a coordinated action plan to increase the availability of personnel. | March 2008 to June 2008 | CDE Staff and contractors. |

Monitoring Priority: Effective General Supervision Part B / Effective Transition

Indicator 12:  Percent of children referred by Part C prior to age 3, who are found eligible for Part B, and who have an IEP developed and implemented by their third birthdays.

(20 U.S.C. 1416(a)(3)(B))

Measurement: - # of children who have been served in Part C and referred to Part B for eligibility determination. - # of those referred determined to be NOT eligible and whose eligibilities were determined prior to their third birthdays. - # of those found eligible who have an IEP developed and implemented by their third birthdays. - # of children for whom parent refusal to provide consent caused delays in evaluation or initial services. Account for children included in a but not included in b, c or d. Indicate the range of days beyond the third birthday when eligibility was determined and the IEP developed and the reasons for the delays. Percent = [(c) divided by (a – b – d)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | 100 percent of children referred by IDEA Part C prior to age three and who are found eligible for IDEA Part B will have an IEP developed and implemented by their third birthdays |

Actual Target Data for (2006-07):

Overall 75.62% percent of Children referred by Part C prior to age 3, who are found eligible for Part B, and who have an IEP developed and implemented by their third birthdays. (6,536 children) This data is collected through CASEMIS data and data exchanged from the Department of Developmental Services. The total Number of children who have been served in Part C and referred to Part B for eligibility determination was 10,868.

Table 12a summarizes the target data for FFY 2006 (2006-07)

Table 12a

Target Data for FFY 2006 (2006-07)

| Measurement Item | Target Data |
| --- | --- |
| - Number of children who have been served in Part C and referred to Part B for eligibility determination | 10,868 |
| - Number of those referred determined to be NOT eligible and whose eligibilities were determined prior to their third birthdays | 494 |
| - Number of those found eligible who have an IEP developed and implemented by their third birthdays | 6,536 |
| - Number of children for whom parent refusal to provide consent caused delays in evaluation or initial services. | 1,731 |
| Percent of Children referred by Part C prior to age 3, who are found eligible for Part B, and who have an IEP developed and implemented by their third birthdays. (Calculation: 6,536 / (10,868 – 494 – 1,731) = 75.62%) | 75.62% |

# Calculation methodology Timelines for this indicator were generated using new CASEMIS fields for REFER_DATE, EVAL_DATE, LAST_IEP and PLAN_TYPE. A child was considered to be referred if the child appeared in both the CASEMIS data set and the PART C data set from the Department of Developmental Services. The child was considered to be within the timeline if the EVAL_DATE, INIT_EVAL or LAST_IEP occurred within a 90 day period prior to the child’s third birthday. Children were considered eligible if the PLAN_TYPE field indicated that they were eligible and had an IEP developed. Children were considered ineligible if the PLAN_TYPE field indicated that they were not eligible and had no plan. Children were included in the parent refusal category if the parent consent date was after the third birthday.

Range of days beyond third birthday Table 12b depicts the range of days beyond the third birthday when children were found eligible and had their IEP developed and implemented.

Table 12b

Range of Days Beyond the Third Birthday

| Days from Third Birthday | No. of Children | %of All Referrals |
| --- | --- | --- |
| 1 to 14 After | 832 | 7.66% |
| 15 to 30 After | 478 | 4.40% |
| 31 to 60 After | 391 | 3.60% |
| 61 to 90 After | 134 | 1.23% |
| 91 to 180 After | 82 | 0.75% |
| Greater Than 180 After | 24 | 0.22% |
| 91 to 120 Before | 28 | 0.26% |
| 121 to 180 Before | 27 | 0.25% |
| Greater Than 180 Before | 33 | 0.30% |
| On the 3rd Birthday | 78 | 0.72% |

Table 12b indicates that the bulk of the children who were assessed and had an IEP developed after their third birthday had their process completed within 14 to 30 days. Some children were reported to have their assessments and IEPs completed 3 to 6 month early. Some were completed more than 6 months after. Seventy-eight children had their IEPs completed on their third birthday.

It should be noted that data for this indicator are collected by two different agencies in the State of California. Information regarding children served under IDEA Part C is collected by the Department of Developmental Services (DDS), which is the lead agency for IDEA Part C. Data regarding children served in IDEA Part B is maintained by the CDE through the CASEMIS. The exchange of child find information with IDEA Part C was a major break through in the ability of both agencies to assess the effectiveness of transition to IDEA Part B.

Referral and evaluation dates for all students were added to the CASEMIS data set in December of 2005 and were collected for the first time in December 2006. This enabled CDE to determine which children in the Part C database were referred to Part B. Referral date information is still difficult to discern, as children referred to CDE’s infant toddler programs appear in both data sets (Part B and Part C) at age three but have a referral date from their first referral to CDE (e.g., at 18 months of age), not necessarily the referral to Part B at age three. While knowing the referral date does not alter the calculations, per se, if a referral is made late (less than sixty days before the child’s third birthday), it is possible that the LEA could complete the evaluation and assessment within statutory timelines and not complete the required assessments and IEP before the child’s third birthday. LEAs indicate that this occurs in a number of cases. In order to clarify these timeline issues, CDE is adding separate referral and evaluation information for Part B and Part C into the CASEMIS database. This will capture the referral and evaluation data for individual children for CDE’s birth to three programs and for Part B of IDEA. Collection of this data will begin on December 2, 2007 and will be reported to CDE for the first time in December 2008. Even with modifications to CASEMIS, CDE will rely on the Department of Developmental Services (DDS), the Part C lead agency, to determine referrals from Part C for FFY 2007 (2007-08).

## Monitoring Data

All Verification and Special Education Self Reviews include the following item:

| Item Number | Compliance Test |
| --- | --- |
| 7-4-1 | Did all students transitioning from early intervention services under Part C have an IEP developed and implemented by the student’s third birthday? |

CDE has adjusted all of its monitoring data from an initiation year basis (e.g., Verification Reviews initiated in 2006-07) to a reporting year basis (e.g., the ABC school district review findings were reported in 2005-06). For the purpose of this and other indicators, compliance findings are reported in the year in which they were reported to the district. “On time” calculations are based on a span of one year from the date that the noncompliance finding was reported. As a result, noncompliance findings made in 2005-06 should be corrected within one year in 2006-07. For this reason, some of the finding totals cited in prior APRs may not match with this APR because they were reported by initiation date rather than reporting date.

2006-07 findings of noncompliance In 2006-07 there were a total of 105 findings of noncompliance reported to districts. All of those findings were made in reviews initiated in 2005-06. Of the 105 findings, 73 were student level findings and 26 were systemic at the district level. Though districts would have one year from the date of reporting the finding to complete correction, 19 of the 26 districts corrected their systemic noncompliance in 2006-07.

2005-06 correction of noncompliance In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

The State also reported that of 214 districts monitored through Verification Reviews or Special Education Self Reviews, 25 were found systemically noncompliant with transition from Part C to Part B and that these districts have corrective actions due in 2006-07. The state did not demonstrate compliance and did not report on the correction of the noncompliance identified in the FFY 2004 SPP.

“The State must review its improvement activities and revise them, if appropriate, to ensure they will enable the State to include data in the FFY 2006 APR, due February 1, 2008, that demonstrate full compliance with the requirements in 34 CFR §300.124, including correction of noncompliance identified in FFY 2005…”

In 2005-06 there were a total of 77 findings of noncompliance reported to districts. Findings were made in monitoring reviews initiated in 2004-05 and 2005-06. Of the 77 findings, 53 were student level findings and 24 were systemic at the district level. Student level findings were not correctible, as they were late, rather than not completed. All systemic findings were corrected within one year, except for one finding, corrected 90 days beyond the one-year timeline.

2004-05 correction of noncompliance In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

OSEP’s …FFY 2004 SPP response letter also required the State to include in the February 1, 2007 APR data demonstrating compliance with the requirement at 34 CFR §300.132(b) (now 34 CFR §300.124(b)).

and

The State must review its improvement activities and revise them, if appropriate, to ensure they will enable the State to include data in the FFY 2006 APR, due February 1, 2008, that demonstrate full compliance with the requirements in 34 CFR §300.124, including correction of noncompliance identified in FFY 2005 and any remaining noncompliance identified in the FFY 2004 SPP.

Reporting dates are not consistently included in our compliance monitoring data bases prior to 2005-06. As a result, some of the findings recorded in 2004-05 are duplicative of those reported in 2005-06, above. In addition to those reported in 2005-06, there were 7 additional districts with systemic findings of noncompliance related to this indicator. Six of the seven findings were completed within 1 year and 1 was completed 27 days after the one year time frame.

All 2003-04 noncompliance findings related to timely transition of children from Part C to Part B have been corrected.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

In 2005-06, 69.19 percent of the three year olds entering Part B had an IEP developed before their third birthday (4,448 out of 6,429 that could be matched to Part C). Referral date information to determine the extent to which these three year olds were referred in a timely fashion was unavailable. In 2006-07 there was an increase from 69.19% to 75.62%. Once again, without a clear indication of the date a child was referred to Part B, it is difficult to determine the extent to which noncompliance is due to LEA policies, procedures or practices.

During 2006-07, CDE and DDS staff met on several occasions to review transition data. One result is that both agencies are adding data fields to clarify the extent of timely referral. As noted above, CDE is adding separate referral and evaluation information to CASEMIS and DDS is adding a Part B referral date to their required data set. In this way, correction of noncompliance can be targeted more appropriately (and more effectively). While improved information and targeted compliance activities should aid in understanding the problem, the issue is larger than figuring out who may be at fault. As a result, during 2006-07, CDE and DDS committed to participating in National Early Childhood Transition Initiative through the Western Regional Resource Center, in order to improve transition outcomes in California.

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Improvement Activity | Timeline | Resources and Type |
| Notify SELPAs, LEAs, and/or Regional Centers of the status, policies, procedures, and resources related to Part C to Part B transition that are available. | By March 1, 2007 | Part B and C staff and resources Type: Monitoring and Enforcement. Stakeholder/Agency Collaboration |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

| CONTINUING ACTIVITIES |  |  |  |
| --- | --- | --- | --- |
| Improvement Activity | Timeline | Resources and Type |  |
| Meet annually with SELPA, LEA, and Regional Centers to review data and plan for corrective action plans and technical assistance activities related to transition from Part C to Part B, based on Annual Performance Report data. | 2006-2010 | Part B and C staff and resources Type: Monitoring and Enforcement. Stakeholder/Agency Collaboration |  |
| Convene Improving Special Education Services (ISES) stakeholder group to obtain input on aspects of Part C to Part B transition; e.g., moving from family focus to child focus. | 2005-2010 | CDE staff, contractor Type: Stakeholder Group and Monitoring -Technical Assistance Project aligned to SPP Indicators |  |
| ADDED ACTIVITIES |  |  |  |
| Improvement Activity | Timeline |  | Resources and Type |
| Revise CASEMIS to include separate referral and evaluation dates for Part B and Part C | 2007-2008 |  | CDE staff, contractor |
| Participate in National Early Childhood Transition Initiative | 2007-2009? Yes-possibly 2010 |  | Part B and C staff and resources Western Regional Resource Center (WRRC) |

Monitoring Priority: Effective General Supervision Part B / Effective Transition

Indicator 13:  Percent of youth aged 16 and above with an IEP that includes coordinated, measurable, annual IEP goals and transition services that will reasonably enable the student to meet the post-secondary goals.

(20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = [(# of youth with disabilities aged 16 and above with an IEP that includes coordinated, measurable, annual IEP goals and transition services that will reasonably enable the student to meet the post-secondary goals) divided by the (# of youth with an IEP age 16 and above)] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | One hundred percent of youth aged 16 and above with an IEP will have annual IEP goals and transition services that will reasonably enable the student to meet the postsecondary goals. |

Actual Target Data for (FFY 2006):

Data Collection. 91% of youth aged 16 and above have postsecondary goals and services (transition, special education, or both) to support the annual goals in their IEP. There were 146,467 youth aged 16 and above reported in CASEMIS in June 2007. Of those, 133,176 youth aged 16 and above had postsecondary goals and services to support the annual goals in their IEPs.

Calculation:	(133,176 / 146,467) *100 = 91%

It should be noted that of the 13,291 youth aged 16 and above who were not reported to have postsecondary goals, 5,142 were reported to have transition services supporting the annual goals in their IEPs. However, because of the lack of postsecondary goals, these students were not included in the calculation above.

Monitoring A total of 220 districts were reviewed in 2006-07 through Verification or Special Education Self Review processes. Of those districts 109 were high school or unified districts serving youth aged 16 and above. A total of 2,088 students aged 16 or above were included in the 2006-07 monitoring reviews. Of those 1,568 records for students aged 16 or above were reviewed using specific compliance items for Postsecondary Transition.

Table 13a depicts the number of noncompliant findings found at the student and district levels for individual compliance tests in 2006-07.

Table 13a

Transition-Related Noncompliance Findings 2006-07

| Item No. | Compliance Test | No. of Student Level NC Findings Statewide | No. of LEAs with Student Level Findings | No. of Systemic Findings | No. of LEAs with Systemic Findings |
| --- | --- | --- | --- | --- | --- |
| 202 | For students at age 16, or younger if appropriate, does the IEP describe needed transition services? | 122 | 40 | 15 | 14 |
| 203 | For students at age 16, or younger if appropriate, are transition services designed using an outcome and results oriented process? | 37 | 11 | 3 | 2 |
| 204 | Is the first IEP that addresses transition, when the student turns 16 years old or younger, if appropriate, reviewed annually? | 29 | 10 | 1 | 1 |
| 206 | Does the first IEP that addresses transition, when the student turns 16 years old, or younger if appropriate, contain transition services that are based on the individual student’s needs, taking into account the student’s preferences and interests? | 42 | 10 | 0 | 0 |
| 877 | Does the first IEP that addresses transition, when the student turns 16 years old or younger, if appropriate, contain measurable post secondary goals? | 21 | 3 | 2 | 2 |
| 878 | Does the first IEP that addresses transition, when the student turns 16 years old or younger, if appropriate, contain measurable post secondary goals based on age appropriate transition assessments related to training, education, employment, and, where appropriate, independent living skills? | 14 | 3 | 1 | 1 |
| * Note: Systemic findings of noncompliance are not based on student record reviews alone. They can be based on a review of student record reviews, interviews, policies and procedure reviews or a combination of these information sources. |  |  |  |  |  |

Overall tables 13b, 13c and 13d depict the statewide summary of noncompliance findings in 2006-07:

Table 13b

Number and Percent of LEAs with Systemic Findings

| LEAs with Systemics | 15 |
| --- | --- |
| LEAs Reviewed with Students 16+ | 109 |
| Percent of LEAs Reviewed with Systemic Findings | 14% |

Table 13c

Number and Percent of LEAs with Student Level Findings

| LEAs with Student NC Findings | 46 |
| --- | --- |
| LEAs Reviewed with Students 16+ | 109 |
| Percent of LEAs with NC Student Findings | 42% |

Table 13c

Number and Percent of Students with NC Findings

| Students 16+ with findings | 169 |
| --- | --- |
| Students 16+ reviewed for Transition | 1570 |
| Percent of students 16+ with NC findings | 11% |

The percent of students with compliant IEPs (100%-11% = 89%), closely parallels the findings from the CASEMIS data system of 91%.

Correction of Noncompliance Identified in 2005-06. In 2005-06 there were 13 findings of systemic noncompliance reported to 10 LEAs. All of those findings have been corrected. At the student level, there were 109 findings of noncompliance reported to LEAs. All of these findings have been corrected.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Improvement Activities | Timelines | Resources and Type |
| Transition to Adult Living: A Guide for Secondary Education: Guide revised to IDEA final regulations. This comprehensive handbook is written for students, parents, and teachers. It offers practical guidance and resources in support of transition efforts for students with disabilities as they move from their junior high and high school years into the world of adulthood and/or independent living. | 2005-2007 | CDE staff, field staff Type: Development of training and technical assistance, information dissemination, general supervision for compliance with IDEA 2004 http://www.cde.ca.gov/sp/se/ac/trnstntrng.asp |

In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

The baseline data that the State provided for this indicator are the percent of students whose IEPs include “transition services language.” The measurement for this indicator requires that the State report the percent of students whose IEPs include coordinated, measurable, annual IEP goals and transition services that will reasonably enable the student to meet the post-secondary goals. Therefore, it appears that the State did not use the correct measurement for this indicator. The State reported that it is revising its data system (CASEMIS) to collect additional secondary transition data. In the FFY 2006 APR, due February 1, 2008, the State must either clarify why the reported FFY 2005 data are consistent with the required measurement for this indicator, or provide data that are consistent with the measurement.

In 2005-06, CASEMIS required LEAs to report on two transition specific fields and to report on all of the services provided to the student contained in their IEP.

| # A-36 | # TRAN_SERV | # Character | # 2 | For students 15 years and older (younger if appropriate), The primary transition service program in which the student is participating or has participated during the school year. If the student is or has participated in more than one transition service s program, use the primary transition service program. |
| --- | --- | --- | --- | --- |
| # A-37 | # TRAN_LANG | # Character | # 1 | Language contained in student’s IEP designed to prepare student for post school activities. This includes language pertaining to type of instruction, related services, community experience, and employment or adult living. |

Calculations for the Annual Performance Report in 2005-06 were based on the age of the student, and affirmative data submission to these two data fields. Also, in 2005-06 it was recognized that these field may not have been sufficiently precise to capture annual goals and services related to post secondary goals. For this reason, CASEMIS added four fields for Post Secondary Goals. These fields were used to capture information about post-secondary transition service goal(s) in which the student was participating or had participated during the school year. The Service Code list was also revised to include a series of transition specific services, e.g., college awareness, vocational services, career awareness, work experience education, mentoring, agency linkages, travel training, etc. These fields and services have been used to generate the data for this indicator in 2006-07.

While the basis for the calculations have changed from 2005-06, the statewide indicator has dropped from 98% in 2005-06 to 91% in 2006-07. A portion of this drop may be due the change to a new data system, though the monitoring findings seem to validate the information from the data system. In 2006-07, CDE updated its Transition to Adult Living: A Guide for Secondary Education and will sponsor seven training sessions statewide in 2007-08. It is anticipated that this training, along with revised monitoring an data collection instruments will support better outcomes in this indicator.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

| CONTINUING ACTIVITIES |  |  |  |  |
| --- | --- | --- | --- | --- |
| Improvement Activities | Timelines |  |  | Resources and Type |
| Use transition data in the state-funded Workability I grant procedures to ensure programs include the provision of transition services. |  | December 30, 2007 | CDE staff, SELPA, LEAs |  |
| Provide CASEMIS training for SELPAS and ongoing technical assistance to ensure reliable and accurate submission of data. |  | 2005-2010 Ongoing and twice a year trainings | CDE staff, SELPA, LEAs |  |

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Improvement Activities | Timelines | Resources and Type |
| Develop and implement multiple activities regarding Secondary Transition including training to build local capacity, technical assistance, Community of Practice, materials dissemination with emphasis on compliance and guidance based upon exemplary researched based practices and stakeholder input. | July 2007 to June 2008 | CDE staff, Workability I staff, field trainers |
| Provide regionalized training and technical assistance regarding transition services language in the IEP. | July 2007 to November 2007 | CDE staff, Workability I staff, field trainers Type: Training and technical assistance |
| Use statewide community of practice for collaborative efforts related to transition services across multiple agencies (DOR, EDD, SILC, parents and consumers). | 2005-2011 | CDE staff, Workability I Staff, NASDSE facilitation for COP Type: Stakeholder group; Technical Assistance |

Part B State Annual Performance Report (APR) for FFY 2006 (2006-07)

Overview of the Annual Performance Report Development:

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 15: General supervision system (including monitoring, complaints, hearings, etc.) identifies and corrects noncompliance as soon as possible but in no case later than one year from identification.

(20 U.S.C. 1416 (a)(3)(B))

Measurement: Percent of noncompliance corrected within one year of identification: - # of findings of noncompliance. - # of corrections completed as soon as possible but in no case later than one year from identification. Percent = [(b) divided by (a)] times 100. For any noncompliance not corrected within one year of identification, describe what actions, including technical assistance and enforcement actions that the State has taken.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | 100 percent of noncompliance will be corrected within one year of identification |

Actual Target Data for (FFY 2006):

In 2006-07 83.4% percent of noncompliance was corrected within one year of identification. Table 15a. summarizes the data and calculation.

15a

Percent of Noncompliance Corrected within One Year of Identification

| Item | Number |
| --- | --- |
| a. Number of findings of noncompliance | 24,437 |
| b. Number of corrections completed as soon as possible but in no case later than one year from identification | 20,380 |
| Percent = [(b) divided by (a)] times 100. ( 20,380 / 24,437 * 100 | 83.4% |

This year, CDE has adjusted all of its monitoring data from an initiation year basis (e.g., Verification Reviews initiated in 2006-07) to a reporting year basis (e.g., the ABC school district review findings were reported in 2005-06). For the purpose of this and other indicators, compliance findings are reported in the year in which they were reported to the district. “On time” calculations are based on a span of one year (365 days) from the date that the noncompliance finding was reported. For this reason, some of the finding totals cited in prior APRs may not match with this APR because they were reported by initiation date rather than reporting date.

Findings for this indicator are based on findings reported by CDE to districts in 2005-06 and include noncompliance identified through onsite monitoring (Verification and Nonpublic School Reviews), Special Education Self Reviews, Complaints and Due Process Hearings as well as ongoing data collection, local plan reviews, annual maintenance of effort reviews, and audits related to state and federal special education funds.

General procedures for monitoring and correction As noted in Indicator 15 in the SPP, the CDE has uses multiple methods to carry out its monitoring responsibilities. These monitoring activities are part of an overall Quality Assurance Process (QAP) designed to ensure that procedural guarantees of the law are followed and that programs and services result in educational benefits. The CDE uses all of its QAP activities to monitor for procedural compliance and educational benefit. Formal noncompliance may be identified and corrective action plans develop for through a wide variety of means including, data collection and analysis, investigation of compliance complaints and due process hearings, and reviewing policies and procedures in local plans. For example, the CDE uses data collected through the California Special Education Management Information System (CASEMIS) to identify districts that are not completing annual reviews of individualized educational programs (IEPs) in a timely way. These result in formal findings of noncompliance citing specific state and federal regulations and require that a corrective action plan be completed

In addition to these components of the QAP, there are four types of traditional monitoring review processes: Facilitated Reviews, Verification Reviews, Special Education Self Reviews, and Nonpublic School Reviews (both onsite and self reviews). Each of the formal review processes results in findings of noncompliance at the student and district level. District level findings are made based on a combination o factors including student record reviews, staff and parent interviews, reviews of policies and procedures. All findings require correction. At the student level the district must provide specified evidence of correction within a 45-day time period. It should be noted that some findings are not correctible at the student level (e.g., missed timelines) though student level findings are a significant contributor to findings at the district level. At the district level, the district must provide updated policies and procedures, evidence that the new policies and procedures have been disseminated and, in a six-month follow-up review, the district must demonstrate that no new instances of noncompliance in that area have occurred. CDE has a variety of sanctions available to use in situations in which noncompliance goes uncorrected (e.g., special grant conditions, withholding of funds, and court action).

Agencies Monitored. Findings from monitoring sources were reported to 281 school districts, county offices of education and nonpublic schools and agencies. Noncompliant findings related to dispute resolutions were reported to 281 districts and agencies.

Percentage of 2005-06 findings by Indicator or other topic area In its California’s Part B FFY 2005 SPP/APR Response Table, OSEP indicated that:

In its response to Indicator 15 in the FFY 2006 APR due February 1, 2008, the State must disaggregate by APR indicator the status of timely correction of the noncompliance findings identified by the State during FFY 2005.

Table 15b (Timely Correction of Noncompliance Findings Disaggregated by APR Indicator depicts the number of noncompliance findings identified for each cluster of APR indicators. Indicators are clustered based on the clusterings contained in the Part B SPP/APR Related Requirements document. This document identifies those federal regulations that are associated with each of the SPP/APR indicators. The CDE utilized the Part B SPP/APR Related Requirements document to categorize noncompliance findings from monitoring reviews and from dispute resolutions processes into the appropriate APR indicators. Not all of the noncompliance findings fit into the APR indicators. As a result, Table 15b has an “other” category. Table 15c depicts the general topics associated with the “other” compliance findings.

Table 15b includes information about the general supervision component used to identify the noncompliance and also summarizes the number of districts and nonpublic schools/agencies monitored using that method. For each indicator the table summarizes the total number of noncompliance findings, the number of those findings corrected within one year of the date they were reported to the public, and the number of findings corrected in more than one year.

Table 15b

Timely Correction of Noncompliance Findings Disaggregated by APR Indicator

| Monitoring Priorities and Indicators | General Supervision Component | No. of Programs Monitored | Total Findings | Timely | Not Timely |
| --- | --- | --- | --- | --- | --- |
| 1. Percent of youth with individualized education programs (IEPs) graduating from high school with a regular diploma compared to percent of all youth in the State graduating with a regular diploma .[20 U.S.C. 1416 (a)(3)(A)] | Monitoring | 251 | 9,668 | 8,403 | 1,565 |
| 2. Percent of youth with IEPs dropping out of high school compared to the percent of all youth in the State dropping out of high school. [20 U.S.C. 1416 (a)(3)(A)] |  |  |  |  |  |
| 13. Percent of youth aged 16 and above with an IEP that includes coordinated, measurable, annual IEP goals and transition services that will reasonably enable the child to meet the post-secondary goals. [20 U.S.C. 1416(a)(3)(B)] | Dispute Resolution | 208 | 75 | 70 | 5 |
| 14. Percent of youth who had IEPs, are no longer in secondary school and who have been competitively employed, enrolled in some type of postsecondary school, or both, within one year of leaving high school.[20 U.S.C. 1416(a)(3)(B)] |  |  |  |  |  |
| - Participation and performance of children with disabilities on statewide assessments: A. Percent of districts meeting the State’s Adequate Yearly Progress (AYP) objectives for progress for disability subgroups. B. Participation rate for children with IEPs in a regular assessment with no accommodations; regular assessment with accommodations; alternate assessment against grade level standards; alternate assessment against alternate achievement standards. C. Proficiency rate for children with IEPs against grade level standards and alternate achievement standards. [20 U.S.C. 1416 (a)(3)(A)] | Monitoring | 251 | 480 | 350 | 130 |
| 7 Percent of preschool children with IEPs who demonstrate improved: A. Positive social-emotional skills (including social relationships); B. Acquisition and use of knowledge and skills (including early language/ communication and early literacy); and C. Use of appropriate behaviors to meet their needs. [20 U.S.C. 1416(a)(3)(A)] | Dispute Resolution | 208 | 3 | 1 | 2 |
| 5 Percent of children with IEPs aged 6 through 21 A. Removed from regular class less than 21% of the day; B. Removed from regular class greater than 60% of the day; or C. Served in public or private separate schools, residential placements, or homebound or hospital placements. [20 U.S.C. 1416(a)(3)(A)] | Monitoring | 251 | 5,965 | 5,590 | 374 |
| 6. Percent of preschool children with IEPs who received special education and related services in settings with typically developing peers (e.g., early childhood settings, home, and part-time early childhood/part-time early childhood special education settings). [20 U.S.C. 1416(a)(3)(A)] | Dispute Resolution | 208 | 114 | 92 | 22 |
| 8 Percent of parents with a child receiving special education services who report that schools facilitated parent involvement as a means of improving services and results for children with disabilities. [20 U.S.C. 1416(a)(3)(A)] | Monitoring | 251 | 211 | 184 | 27 |
|  | Dispute Resolution | 208 | 68 | 60 | 8 |
| 9 Percent of districts with disproportionate representation of racial and ethnic groups in special education and related services that is the result of inappropriate identification. [20 U.S.C. 1416(a)(3)(C)] | Monitoring | 251 | 1,248 | 808 | 440 |
| 10. Percent of districts with disproportionate representation of racial and ethnic groups in specific disability categories that is the result of inappropriate identification.[20 U.S.C. 1416(a)(3)(C)] | Dispute Resolution | 208 | 85 | 75 | 10 |
| 11. Percent of children with parental consent to evaluate who were evaluated and eligibility determined within 60 days (or State established timeframe).[20 U.S.C. 1416(a)(3)(B)] | Monitoring | 251 | 3,342 | 2,558 | 794 |
|  | Dispute Resolution | 208 | 141 | 117 | 24 |
| 12. Percent of children referred by Part C prior to age 3 and who are found eligible for Part B who have an IEP developed and implemented by their third birthdays.[20 U.S.C. 1416(a)(3)(B)] | Monitoring | 251 | 211 | 134 | 77 |
|  | Dispute Resolution | 208 |  |  |  |
| 4. Rates of suspension and expulsion A. Percent of districts identified by the State as having a significant discrepancy in the rates of suspensions and expulsions of children with disabilities for greater than 10 days in a school year; and: B. Percent of districts identified by the State as having a significant discrepancy in the rates of suspensions and expulsions of greater than 10 days in a school year of children with disabilities by race and ethnicity. [20 U.S.C. 1416(a)(3)(A); 1412(a)(22)] | Monitoring | 251 | 105 | 79 | 26 |
|  | Dispute Resolution | 208 | - | - | - |
| 15.General supervision system (including monitoring, complaints, hearings, etc.) identifies and corrects noncompliance as soon as possible but in no case later than one year from identification.[20 U.S.C. 1416(a)(3)(B)] | Monitoring | 251 | 1,488 | 1,116 | 372 |
|  | Dispute Resolution | 208 | 923 | 807 | 116 |
| TOTAL |  |  | 24,437 | 20,380 | 4,057 |

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

The overall percentage of noncompliance findings corrected within one year of identification dropped from 97% in 2005-06 to 83% 2006-07. There was a dramatic increase in the number of findings from 9,372 in 2005-06 to 24,437 in 2006-07. In part, this is due to the change in method of reporting findings. In part is due to more complete electronic submission of findings and correction from the Los Angeles Unified School District (LAUSD). In prior years, findings from LAUSD have been submitted in paper form and summarized at the district level. For findings reported in 2005-06 a complete set of findings has been submitted electronically increasing the number of findings by about 11,000.

There were 28 districts with findings that were corrected more than one year after the date the finding was reported to the district. All districts had regular contacts from CDE staff during the period of correction. In addition, all of the districts were contacted by phone and email to formally indicate that the district had exceeded the one year timeline for correction. Twenty-five of the districts had onsite visits to provide technical assistance. Two districts were placed on special conditions.

The CDE has place particular emphasis on providing in-service to staff related to changes in federal law and the alignment of state law to changes in the IDEA. There have been no administrative or organizational changes that would account for the slippage. There has been persistent difficulty hiring and maintaining professional staff in the Special Education Division. All of the monitoring units have vacancies on a consistent basis and it is difficult to attract candidates from local programs, due to the differences in salary and benefit structures.

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Provide targeted training on implementing the IDEA 2004 including court cases and legal interpretations for CDE staff | November 2007 | Perry Zirkel, Esq., nationally known expert in IDEA. Type: Training and Technical Assistance for SEA |
| Pursue the development of an integrated database to pro-actively identify upcoming corrective actions across all components of the monitoring system. | June 30, 2006 | Outside Contractor subject to approval by the Department of Finance, CDE staff Type: Special Project, Monitoring and Enforcement |
| Explore Web based applications for all components of the monitoring system. | June 30, 2006 | Outside Contractor subject to approval by the Department of Finance, CDE staff |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

| COMPLETED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| IDEA Final Regulation Training web case promoted during fall 2006. Web cast archived and DVD widely distributed. | Ongoing through 2011 | Art Cernosia, Esq., nationally known expert in the IDEA. Free to the public and funded through IDEA funds. Type: Training and Technical Assistance to SEA http://www.ideatraining.org/ |
| Conduct analysis and prepare plans for Annual Performance Reports (APR) on all general supervision indicator requirements | July 1, 2007-June 30, 2011 | CDE Staff Type: Monitoring and Enforcement |
| Develop & maintain IDEA 2004 information Web page with links to important references and resources on the Reauthorization of the IDEA | December 2004; ongoing update | CDE/SED staff; Web capability of CDE Web page: http://www.cde.ca.gov/sp/se/lr/ideareathztn.asp Type: Public Reporting/Data Awareness/Data Utilized to Reflect Upon Practice and legal requirements of IDEA 2004 |
| Provide staff training for corrective actions, timelines, and sanctions. Incorporate notice of potential sanctions in monitoring correspondence | 2005-2011 Ongoing through 2011 | CDE Staff Type: Monitoring and Enforcement as part of general supervision |

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Recruit candidates and hold civil service examinations. Fill unfilled vacancies with staff, retired annuitants, or visiting educators | Ongoing to 2011 | CDE staff |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 16:  Percent of signed written complaints with reports issued that were resolved within 60-day timeline or a timeline extended for exceptional circumstances with respect to a particular complaint.

(20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = [(1.1(b) + 1.1(c)) divided by 1.1] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | 100 percent of written complaints resolved within 60-day timeline, including a timeline extended for exceptional circumstances with respect to a particular complaint. |

Actual Target Data for (FFY 2006):

Table 7 of the required 618 Data Collection is attached. Section A regarding signed, written complaints is reproduced below.

| SECTION A: Signed, written complaints |  |
| --- | --- |
| (1) Signed, written complaints total | 1117 |
| (1.1) Complaints with reports issued | 914 |
| (a) Reports with findings | 508 |
| (b) Reports within timeline | 791 |
| (c) Reports within extended timelines | 58 |
| (1.2) Complaints withdrawn or dismissed | 203 |
| (1.3) Complaints pending | 0 |
| (a) Complaint pending a due process hearing | 0 |

The table indicates that the CDE resolved 93 percent of written complaints within the 60-day timeline and extended timelines for exceptional circumstances with respect to a particular complaint.

Calculation:  (791 + 58) / 914 = 93 %

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

The CDE continued to improve its percentage written complaints resolved within the 60-day timeline and extended timelines. Achieving a 93 percent timely completion rate, demonstrates continuous improvement from the two previous reporting periods (i.e., 84 percent in 2005-2006, and 52 percent in 2004-2005). The complaints unit resolved the large backlog of reconsiderations that barred a completed investigation of written complaints within the 60-day timeline and extended timelines. To decrease the number of vacancies in the complaints investigation unit, the CDE requested and received a waiver to fill investigator positions by deviating from the state-mandated hiring process. At the end of the reporting period, the complaints unit was 100% staffed. The map below identifies the distribution of complaints by California County:

The more populated counties had more complaint filings than that of counties with fewer people (i.e., Los Angeles, Orange). However, when a proportion was calculated as number of complaints divided by the number of students in special education, some rural counties had proportionately more complaints than more populated counties (e.g., Trinity).The chart below identifies both the number of complaints by county and the ratio

| County | Special Education Students | Total School Population | No. of Complaints | No. of Complaints Per 1,000 Special Education Students |
| --- | --- | --- | --- | --- |
| Alameda | 22,668 | 213,497 | 48 | 2.11 |
| Alpine | 38 | 138 | 0 | 0 |
| Amador | 669 | 5,201 | 0 | 0 |
| Butte | 4045 | 32,827 | 2 | .49 |
| Calaveras | 696 | 6,828 | 0 | 0 |
| Colusa | 596 | 4,578 | 0 | 0 |
| Contra Costa | 19780 | 166,102 | 38 | 1.92 |
| Del Norte | 537 | 4,642 | 0 | 0 |
| El Dorado | 3437 | 29,417 | 2 | .58 |
| Fresno | 18461 | 193,544 | 11 | .59 |
| Glenn | 640 | 6,907 | 2 | 3.1 |
| Humboldt | 2692 | 19,230 | 1 | 3.7 |
| Imperial | 3051 | 36,293 | 3 | .98 |
| Inyo | 378 | 3,047 | 0 | 0 |
| Kern | 16418 | 171,585 | 27 | 1.6 |
| Kings | 2759 | 27984 | 7 | 2.5 |
| Lake | 1223 | 10091 | 3 | 2.5 |
| Lassen | 714 | 5225 | 0 | 0 |
| Los Angeles | 182545 | 1673257 | 430 | 2.4 |
| Madera | 3068 | 29071 | 1 | .32 |
| Marin | 3814 | 29081 | 11 | 2.88 |
| Mariposa | 356 | 2374 | 1 | 2.8 |
| Mendocino | 1746 | 13688 | 0 | 0 |
| Merced | 5704 | 56743 | 1 | .18 |
| Modoc | 158 | 2148 | 0 | 0 |
| Mono | 335 | 2517 | 0 | 0 |
| Monterey | 6694 | 69851 | 5 | .74 |
| Napa | 2690 | 20087 | 3 | 1.1 |
| Nevada | 1350 | 14243 | 3 | 2.2 |
| Orange | 51131 | 503955 | 80 | 1.6 |
| Placer | 6886 | 64401 | 2 | .3 |
| Plumas | 296 | 2755 | 0 | 0 |
| Riverside | 42515 | 413069 | 50 | 1.2 |
| Sacramento | 26520 | 238233 | 27 | 1 |
| San Benito | 1258 | 11578 | 2 | 1.6 |
| San Bernardino | 45519 | 427583 | 39 | .86 |
| San Diego | 58745 | 493699 | 63 | 1 |
| San Francisco | 6502 | 57347 | 29 | 4.5 |
| San Joaquin | 13529 | 136739 | 25 | 1.8 |
| San Luis Obispo | 4177 | 36618 | 4 | .9 |
| San Mateo | 10046 | 88479 | 29 | 2.9 |
| Santa Barbara | 7134 | 66501 | 5 | .7 |
| Santa Clara | 26619 | 255722 | 84 | 3.1 |
| Santa Cruz | 4708 | 38062 | 6 | 1.3 |
| Shasta | 3150 | 28908 | 3 | .95 |
| Sierra | 68 | 532 | 0 | 0 |
| Siskiyou | 759 | 6357 | 0 | 0 |
| Solano | 7937 | 69048 | 10 | 1.3 |
| Sonoma | 928 | 71412 | 14 | 15 |
| Stanislaus | 13097 | 106984 | 14 | 1 |
| Sutter | 2154 | 19137 | 2 | .9 |
| Tehama | 1071 | 11212 | 0 | 0 |
| Trinity | 221 | 1936 | 1 | 4.5 |
| Tulare | 7399 | 94407 | 5 | .68 |
| Tuolumne | 893 | 7535 | 0 | 0 |
| Ventura | 15359 | 142488 | 18 | 1.2 |
| Yolo | 3220 | 29493 | 6 | 1.9 |
| Yuba | 1957 | 14559 | 0 | 0 |

The allegations most often filed in a state complaint were failure to implement the student’s individualized education program (IEP), failure to provide student records within state timelines, and failure to meet assessment plan timelines. Although the majority of complaints were investigated, alternative means resolving the allegations met with success, including complainant withdrawal, local resolution, and state mediation or facilitated solutions. The table below provides the number of complaints, categories, and resolution:

| COMPLETED ACTIVITES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| The Legal Division continues to meet biweekly with the Complaints Management and Mediation Unit and Special Education Division staff to provide special education legal updates and ongoing training with regard to the complaints investigation process. | July 1, 2006 through June 30, 2007 | CDE Legal Division Attorneys |
| Art Cernosia, renowned special education attorney, provided a two day training regarding IDEA regulations. | January 30-31, 2007 | Art Cernosia |
| The Unit continued and developed ongoing collaboration with CDE legal and other entities such as Parent Training Information Centers, Family Empowerment Centers, LEAs, and advocates in conjunction with PSRS. | June 30, 2006 | CDE legal staff, Art Cernosia |
| Representatives of the complaints unit attended the 2007 LRP Special Education Law training and updated fellow unit members on the content. | April 21-26, 2007 | CDE staff |
| The Complaints Management and Mediation Unit attended USDOE regulations training. | June 2006 | CDE staff |

| NUMBER OF COMPLAINTS | CATEGORY | Resolution of Complaints |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Compliant | Non-Compliant | Dropped | Allegation Withdrawn | Case Withdrawn | Facilitated Solution | Local Resolution | Not Determined | Set Aside |
| 634 | IEP Implementation | 177 | 309 | 11 | 1 | 79 | 6 | 34 | 1 | 16 |
| 168 | Pupil Records | 43 | 95 | 3 | 0 | 12 | 2 | 10 | 0 | 3 |
| 158 | Assessment Plan Timeline | 31 | 84 | 3 | 0 | 17 | 6 | 12 | 1 | 4 |
| 122 | Assessment | 46 | 37 | 5 | 0 | 18 | 0 | 8 | 0 | 8 |
| 122 | IEP Content | 65 | 27 | 9 | 0 | 14 | 0 | 2 | 0 | 5 |
| 87 | IEP Meeting | 47 | 23 | 4 | 0 | 6 | 0 | 4 | 1 | 2 |
| 83 | Assessment and IEP Development Timeline | 11 | 50 | 2 | 0 | 10 | 0 | 5 | 0 | 4 |
| 76 | IEP Parent Request | 19 | 37 | 5 | 0 | 10 | 0 | 4 | 0 | 1 |
| 74 | Parent Participation | 46 | 16 | 1 | 0 | 5 | 0 | 1 | 0 | 5 |
| 61 | Prior Notice | 17 | 22 | 5 | 0 | 8 | 0 | 2 | 1 | 6 |
| 54 | Parent Rights | 25 | 16 | 2 | 0 | 3 | 0 | 1 | 1 | 6 |
| 49 | IEP Team Membership | 16 | 23 | 3 | 1 | 3 | 0 | 1 | 0 | 2 |
| 40 | IEP Annual Timeline | 12 | 19 | 3 | 0 | 3 | 0 | 2 | 0 | 1 |
| 40 | Placement | 13 | 21 | 0 | 0 | 1 | 0 | 3 | 0 | 2 |
| 33 | Child Find | 13 | 12 | 3 | 0 | 0 | 0 | 2 | 0 | 3 |
| 27 | Assessment in All Areas | 14 | 6 | 1 | 0 | 4 | 0 | 2 | 0 | 0 |
| 24 | IEP Teacher Knowledge | 10 | 8 | 1 | 0 | 3 | 0 | 1 | 0 | 1 |
| 24 | LRE | 9 | 7 | 3 | 0 | 2 | 0 | 2 | 0 | 1 |
| 23 | IEP Team Meeting | 17 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 1 |
| 22 | Behavior Intervention | 12 | 2 | 1 | 0 | 6 | 0 | 1 | 0 | 0 |

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

## Alternative Dispute Resolution

CDE reduced the number of complaint requests through Alternative Dispute Resolution (ADR) grants. ADR grants support positive interaction and collaboration between parents and educators, and promote assisting parents and education agencies in the implementation of the use of conflict resolution throughout the state, while attempting to reduce the number of compliance complaints. ADR strategies may include: solutions panels, IEP facilitation, resource parents, early case review, IEP coaches, local mediation, technical assistance/expert teams, independent child advocates, and placement specialists. CDE awards grants to regional consortia that include LEAs and county offices. Selected LEAs train and implement an ADR process in responding to and resolving local complaints and concerns regarding the implementation of the IDEA, Part B and relevant state laws. Results indicate that SELPAs involved ADR grant activities have a lower rate of compliance complaints. SELPAs with ADR grants had an average of 1.65 complaints per 1,000 special education students, while other SELPAs had an average of 1.83 complaints per 1,000 special education students.

## Collaboration

A three year analysis of data collected and state interventions reveals a thirty-three percent (33%) reduction in the number of complaints filed against school districts located in Orange County. Review of the 2004-05, 2005-06 and 2006-07 data indicates that the number of complaints decreased from 120, 93 and to 80 during that three year period of time. Strategies used in achieving the reduction involved interactive communication and collaboration between the Compliance, Management & Mediation (CMM), Procedural Safeguards Referral Service (PSRS), Focused Monitoring & Technical Assistance (FMTA) Units and the Department’s Legal Office. Dialogue with PSRS included meeting with PSRS staff to discuss citations and allegations before a case was opened, Discussions with Districts entailed interviews and the sharing of state level compliance data. Collaboration with FMTA involved having discussions and meeting with the FMTA Consultant assigned to Orange County. And, interaction with the Legal Office included collaboration on high profile cases.

## Staffing

In the past, the Complaints Management and Mediation Unit (CMM), the unit that completes compliance investigations, was understaffed by as much as twenty-five percent. To ensure that compliance complaint reports were completed in a timely manner, the director of the Special Education Division set a priority to fully staff the unit. Various strategies were employed to ensure full staffing by the ending of the 2006-07 fiscal year, including obtaining a waiver of state hiring practices.

| CONTINUING ACTIVITES |  |  |
| --- | --- | --- |
| Activity | Timelines | Resources |
| Develop an integrated database to proactively identify upcoming corrective actions across all components of the monitoring system. | Ongoing | CDE Staff Type: Monitoring |
| Continue to cross-unit train for complaint investigations and other monitoring activities to focus on inter-rater reliability and consistency. | Ongoing | CDE Staff Type: Monitoring |

| ADDED ACTIVITES |  |  |
| --- | --- | --- |
| Activity | Timelines | Resources |
| Reorganized complaint investigation unit to meet requirements and assist the field. | December 2007-2008 | CDE Staff Type: Monitoring |
| Continue to cross-unit train for complaint investigations and other monitoring activities to focus on inter-rater reliability and consistency. | Ongoing | CDE Staff Type: Monitoring |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 17:  Percent of fully adjudicated due process hearing requests that were fully adjudicated within the 45-day timeline or a timeline that is properly extended by the hearing officer at the request of either party. (20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = [(3.2(a) + 3.2(b)) divided by 3.2] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | One hundred percent of due process hearing requests will be fully adjudicated within the 45-day timeline or a timeline that is properly extended by the hearing officer at the request of either party |

Actual Target Data for 2006 (2006-07):

Table 7 of the required 618 Data Collection is attached. Section C regarding hearing requests are reproduced below:

| SECTION C: Hearing requests |  |
| --- | --- |
| (3) Hearing requests total | 2516 |
| (3.1) Resolution sessions | 818 |
| (a) Settlement agreements | 478 |
| (3.2) Hearings (fully adjudicated) | 74 |
| (a) Decisions within timeline | 14 |
| (b) Decisions within extended timeline | 60 |
| (3.3) Resolved without a hearing | 1735 |

100 percent of due process hearing requests were fully adjudicated within the 45-day timeline or a timeline that was properly extended by the hearing officer at the request of either party.

Calculation:  [(14 + 60) / 74] *100 = 100%

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

Compliance with the target increased from 33 percent in 2005-06, to 100 percent for 2006-07. This progress resulted from a combination of:

- Continued implementation of improvement activities identified in the 2005-06 APR, and

- The resolution of complications arising out of the transition from one contractor, the McGeorge School of Law, to the successor contractor, the Office of Administrative Hearings (OAH). These complications were reported in the 2005-06 APR and included, among others, an unanticipated addition of more than 1,000 cases to OAH’s workload.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07):

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | ### Timelines | Resources |
| Hearing officers will receive training regarding IDEA, Education Code Section 56000 and related regulations. Trainings will be designed to ensure that all hearing officers meet the minimum training standards specified by law. | 2005-2011 | CDE staff, Outside contractors Type: Monitoring |
| Hearing officers will receive global skills training. | Annually 2005-2011 | Outside contractors |
| It will be determined when hearing officers have a working knowledge of the laws and regulations governing services to students who qualify for services under IDEA and related California laws and regulations, and the programmatic aspects of special education, services, and supports. | 2005-2011 | Office of Administrative Hearing (OAH) staff |
| Only hearing officers who have the level of expertise specified in the proposed regulations will be assigned mediation and hearing duties. Such monitoring activities will be provided on an ongoing basis by knowledgeable senior staff. | 2005-2011 | OAH senior staff |
| Data will be gathered pertaining to due process hearings to ensure that all due process hearing requests are fully adjudicated within the 45-day timeline or a timeline that is properly extended by the hearing officer at the request of either party. Such data will include the following items: 1) number of hearing requests total; 2) number of resolution sessions conducted; 3) number of settlement agreements; 4) number of hearings held (fully adjudicated); 5) Number of decisions within timeline; 6) number of decisions within extended timeline; 7) number of decisions issued after timelines and extension expired;8) number of hearings pending; 9) number of expedited hearings; and 10) number of hearing request cases resolved without a hearing. Regarding expedited hearing requests (related to disciplinary decision), the following data will be collected: 1) number of expedited hearing requests total; 2) number of resolution sessions; number of settlement agreements; number of expedited hearings (fully adjudicated); and number of change of placement ordered. | 2005-2011 | OAH and CDE staff |
| A new case management system will track decision due dates and be updated regularly. A tickler system will allow immediate access to decision timeline information on any given case. | 2005-2011 | OAH staff and external contractors |
| Administrative law judges will meet with their presiding judge to discuss decision timelines. At that time, due dates will be established for submission of a decision draft, usually within five days, and allowance will be made for additional time for decision review, feedback and revisions prior to preparation and issuance of the final decision draft. | 2005-2011 | OAH staff |
| The OAH management has communicated to all administrative law judges how absolutely critical it is that decisions be timely. It is an individual administrative law judge performance measure that is closely tracked. | 2005-2011 | OAH staff |
| The OAH has provided and will continue to offer training on decision writing, portions of which will include efficient decision writing skills. | 2005-2011 | OAH senior staff and outside consultants |

The following improvement activities are being added to address both the number of filings and the process and strategies encompassing alternative dispute resolution. It is intended that OAH consult with its advisory group to identify 1) issues needing improvement and 2) identify potential strategies for addressing those issues. The advisory group will, in collaboration with OAH, be in the best position (and have the greatest vested interest) to analyze conditions, identify needs, and develop strategies to meet those needs.

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Improvement Activities | ### Timelines | Resources |
| OAH’s advisory group will recommend training materials to be developed, by OAH, for use by parents and interested others. | To occur during 2007-08 | OAH staff and its advisory group |
| OAH will, in consultation with its advisory group, develop and submit to CDE for review and approval, recommendations for system improvement. | To occur during 2007-08 | OAH staff and its advisory group |
| OAH will, in consultation with its advisory group, conduct or cause to be conducted, a workshop on alternative resolutions for resolving differences in a non-adversarial atmosphere, and with the goal of providing a free appropriate public education. | To occur during 2007-08 | OAH staff and its advisory group |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 18:  Percent of hearing requests that went to resolution sessions that were resolved through resolution session settlement agreements.  (20 U.S.C. 1416(a)(3(B))

Measurement: Percent = (3.1(a) divided by 3.1) times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | 62 percent of hearing requests that went to resolution sessions were resolved through resolution session settlement agreements. |

Actual Target Data for 2006 (2006-2007):

Table 7 of the required 618 Data Collection is attached. Section C regarding hearing requests is reproduced below:

| SECTION C: Hearing requests |  |
| --- | --- |
| (3) Hearing requests total | 2516 |
| (3.1) Resolution sessions | 818 |
| (a) Settlement agreements | 478 |
| (3.2) Hearings (fully adjudicated) | 74 |
| (a) Decisions within timeline | 14 |
| (b) Decisions within extended timeline | 60 |
| (3.3) Resolved without a hearing | 1735 |

59 percent of hearing requests that went to resolution sessions were resolved through resolution session settlement agreements.

Calculation:  (419 / 714) * 100 = 59%

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

The target for 2006-07 was 62 percent, while actual achievement was 59 percent. This difference is likely due to having limited initial information upon which to establish accurate subsequent annual targets, rather than to slippage. More specifically, annual targets were set during the transition from one contractor to another and reflect predictions based on a relatively new activity that had generated only six months of data.

In 2006-07, data regarding resolution sessions and settlement agreements deriving solely from those sessions was solicited by CDE directly from school districts with due process filings between July 1, 2006 and June 30, 2007. Districts reported in aggregate data the number of resolution sessions that were held and the number of those sessions that resulted in a settlement agreement. Because of the complexities of amending contracts, it was determined that soliciting data directly from districts would be a more timely and effective strategy for obtaining needed information than amending the contractor’s form for requesting a due process hearing (which was the stated improvement activity in the 2005-06 SPP and APR).

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07):

Revisions to proposed targets and timelines are required. Revisions are justified based on the availability of more complete data, as noted in the above section, upon which to make accurate projections.

(Note: CDE is permitted to consider ranges of values for these targets and may switch before December 15th submission)

| FFY | Measurable and Rigorous Targets |
| --- | --- |
| 2007-08 | 61 percent of hearing requests that go to resolution sessions will be resolved through resolution session settlement agreements. |
| 2008-09 | 64 percent of hearing requests that go to resolution sessions will be resolved through resolution session settlement agreements. |
| 2009-10 | 67 percent of hearing requests that go to resolution sessions will be resolved through resolution session settlement agreements. |
| 2010-11 | 71 percent of hearing requests that go to resolution sessions will be resolved through resolution session settlement agreements. |

The following improvement activities replace those reported during the previous year:

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Obtain data, on resolution sessions and settlement agreements deriving solely from those sessions, directly from school districts with due process filings during 2007-08. | Ongoing | CDE staff and OAH/contractor staff |
| OAH/contractor will conduct or cause to be conducted, a workshop on strategies for resolving differences in a non-adversarial atmosphere, and with the goal of providing a free appropriate public education. | To occur during 2007-08 | OAH/contractor staff |
| OAH’s advisory group will recommend training materials to be developed, by OAH, for use by parents and interested others. | To occur during 2007-08 | OAH staff and its advisory group |
| OAH will, in consultation with its advisory group, develop and submit to CDE for review and approval, recommendations for system improvement. | To occur during 2007-08 | OAH staff and its advisory group |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 19:  Percent of mediations held that resulted in mediation agreements.  (20 U.S.C. 1416(a)(3)(B))

Measurement: Percent = [(2.1(a)(i) + 2.1(b)(i)) divided by 2.1] times 100.

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | At least 57 percent of mediation conferences will result in mediation agreements. |

Actual Target Data for 2006 (2006-07):

Table 7 of the required 618 Data Collection is attached.  Section B regarding mediation requests is reproduced below:

| SECTION B: Mediation requests |  |
| --- | --- |
| (2) Mediation requests total | 2747 |
| (2.1) Mediations |  |
| (a) Mediations related to due process | 1393 |
| (i) Mediation agreements | 570 |
| (b) Mediations not related to due process | 231 |
| (i) Mediation agreements | 122 |
| (2.2) Mediations not held (including pending) | 1123 |

43 percent of mediation conferences resulted in mediation agreements.

Calculation:  [(570+122) / 1,624] * 100 = 43%

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

The target for 2006-07 was 57 percent, while actual measured achievement was 43 percent. Similar to the discrepancy described for Indicator 18, this difference is likely attributable to the limited availability of data upon which to establish accurate annual targets, rather than to slippage. Again, annual targets were established during the transition from one contractor to another and reflect predictions based on significantly limited data/knowledge.

The contractor’s new case/data management system became operational during the second half of 2006-07. Through combined use of the predecessor and new case management systems, the contractor was able to report mediation-related data for 2006-07.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07):

The following proposed targets are being added. The original target of 57 percent has been revised downward to reflect the recent availability of more accurate data.

(NOTE: CDE is permitted to revise these targets into ranges and may consider changing these targets before the December 15th submission)

| FFY | Measurable and Rigorous Targets |
| --- | --- |
| 2007-08 | At least 46 percent of mediation conferences will result in mediation agreements. |
| 2008-09 | At least 49 percent of mediation conferences will result in mediation agreements. |
| 2009-10 | At least 52 percent of mediation conferences will result in mediation agreements. |
| 2010-11 | At least 56 percent of mediation conferences will result in mediation agreements. |

The following improvement activities are being added to 1) increase the probability of disputes being resolved under circumstances more informal than through mediation and 2) accentuate the contractor’s ability to facilitate successful mediations when such become necessary:

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Activities | Timelines | Resources |
| Implement standards for the training of OAH/contractor staff functioning as mediators. | Ongoing | CDE staff and OAH/contractor staff |
| Implement standards for the qualifications of OAH/contractor staff functioning as mediators. | Ongoing | CDE staff and OAH/contractor staff |
| Implement standards for the supervision of OAH/contractor staff functioning as mediators. | Ongoing | CDE staff and OAH/contractor staff |
| Develop and distribute a parent manual that provides guidance regarding mediations and due process hearings. | Manual to be completed during 2007-08. | OAH/contractor staff |
| OAH’s advisory group will recommend training materials to be developed, by OAH, for use by parents and interested others. | To occur during 2007-08 | OAH staff and its advisory group |
| OAH will, in consultation with its advisory group, develop and submit to CDE for review and approval, recommendations for system improvement. | To occur during 2007-08 | OAH staff and its advisory group |
| OAH will, in consultation with its advisory group, conduct or cause to be conducted, a workshop on alternative resolutions for resolving differences in a non-adversarial atmosphere, and with the goal of providing a free appropriate public education. | To occur during 2007-08 | OAH staff and its advisory group |

Monitoring Priority: Effective General Supervision Part B / General Supervision

Indicator 20: State reported data (618 and State Performance Plan and Annual Performance Report) are timely and accurate. (20 U.S.C. 1416(a)(3)(B))

Measurement: State reported data, including 618 data and annual performance reports, are: - Submitted on or before due dates (February 1 for child count, including race and ethnicity; placement; November 1 for exiting, discipline, personnel; and February 1 for Annual Performance Reports); and - Accurate (describe mechanisms for ensuring error free, consistent, valid and reliable data and evidence that these standards are met).

| FFY | Measurable and Rigorous Target |
| --- | --- |
| 2006 (2006-07) | 20a. One hundred percent of state-reported data, including 618 data and Annual Performance Reports (APR) are submitted on time and are accurate 20b. One hundred percent of the SELPAs will submit accurate data to CDE in a timely manner. |

Actual Target Data for (FFY 2006 - 2006-07):

# State Data Submission

Timeliness CDE submitted required 618 data through EDEN and through DANS two data reports were submitted late due to late data submissions from 10 ten SELPA. Table 20a depicts due dates and submission dates for each of the federal data tables.

Table 20a

Submission Dates for 2006-07 618 Data Reports

|  | Due Date | Submission Date | On Time |
| --- | --- | --- | --- |
| Table 1 | February 1, 2007 | March 27, 2007 | No |
| Table 2 | November 1, 2007 | November 1,2007 | Yes |
| Table 3 | February 1, 2007 | March 27, 2007 | No |
| Table 4 | November 1, 2007 | October 17, 2007 | Yes |
| Table 5 | November 1, 2007 | November 1,2007 | Yes |
| Table 6 | February 1, 2008 | February 1, 2008 | Yes |
| Table 7 | November 1, 2007 | November 1,2007 | Yes |

In response to the late submissions the CDE immediately sent notices to affected County Superintendents and SELPA Directors advising the LEAs of the State’s intent to impose sanctions for delinquent data reports. These proposed sanctions included findings of non-compliance and superintendent salary sanctions. All data were received within 3 weeks of the due date.

Data Accuracy The data collection software for the State, CASEMIS, includes data edits and logical checks in the verification process to ensure data accuracy. In addition the CASEMIS program provides reports during the verification process that identify further potential discrepancies that cannot be detected using logical data edits and checks.

CDE staff collected and review potential anomaly data from SELPAs. CDE Staff also reviewed and evaluated data submitted in any modified CASEMIS data fields. No data needed to be resubmitted to OSEP or EDEN due to inaccurate data.

# Local Data Submission

Timeliness For the December 1, 2006 Statewide Pupil Count 113 out of 123 or 92% of the SELPAs submitted timely data. The State was late reporting Data Table 1 and Data Table 3 due to late reporting by ten SELPAs;

| Pasadena Unified SELPA | Santa Clara Area 2 SELPA |
| --- | --- |
| Riverside County SELPA | Santa Clara Area 3 SELPA |
| San Francisco Unified SELPA | Santa Clara Area 4 SELPA |
| San Mateo County SELPA | Santa Clara Area 7 SELPA |
| Santa Clara Area 1 SELPA | CA State Special Schools |

For the June 30, 2007 End-of-Year Report 111 out of 123 or 90% of the SELPAs submitted timely data.

As noted above, the CDE immediately sent notices to affected County Superintendents and SELPA Directors advising the LEAs of the State’s intent to impose sanctions for delinquent data reports. These proposed sanctions included findings of non-compliance and superintendent salary sanctions. All data were received within 3 weeks of the due date.

Data Accuracy The data collection software for the State, CASEMIS, includes data edits and logical checks in the verification process to ensure data accuracy. In addition the CASEMIS program provides reports during the verification process that identify further potential discrepancies that cannot be detected using logical data edits and checks.

One SELPA (Vallejo Unified SELPA) did not submit a discipline data table.

The following 10 SELPAs did not submit a post secondary follow-up data table.

| Antelope Valley | Long Beach Unified |
| --- | --- |
| Santa Ana Unified | Plumas County |
| Santa Clara Area I-IV, VII | Pajaro Valley Joint Unified |
| Sierra County | Vallejo City Unified |
| Stanislaus County | Modesto City Schools |

The State sent notices to affected County Superintendents and SELPA Directors advising the LEAs of the States intent to impose sanctions for delinquent data reports. These proposed sanctions included findings of non-compliance and superintendent salary sanctions.

Discussion of Improvement Activities Completed and Explanation of Progress or Slippage that occurred for 2006 (2006-07):

Ongoing consultation and development of the CASEMIS data system.  CDE regularly reviews the CASEMIS data system with SELPA administrators and LEA data managers. CDE provides monthly presentations at SELPA Director meetings and at regional CASEMIS trainings twice a year. Two meetings are held each spring and fall, one in the northern region and one in the southern region of the state. SPP/APR data collection requirements are discussed at each event.

Timely submission of data The importance of timely submission and the consequences of late submission were addressed at every training and technical assistance event in 2006-07.  CDE reviewed the need to alter the December 1 count date with SELPA Administrators.  For 2007-08, December 1 will continue to be the count date.

Indicator 12 - C to B Transition CDE implemented data collection changes in 2006-07. These enabled the preparation of the calculations required by Indicator 12: the number of children who have been served in Part C and referred to Part B for eligibility determination; the number of those referred determined to be NOT eligible and whose eligibilities were determined prior to their third birthdays; the number of those found eligible who have an IEP developed and implemented by their third birthdays; and the number of children for whom parent refusal to provide consent caused delays in evaluation or initial services. Additional data changes will be implemented in the December 2008 data collection that will facilitate distinguishing between Part B and Part C referrals and identification.

Indicator 13 – Secondary Transition Data changes were implemented in December 2006 that enabled CDE to make the required calculations for Indicator 13: percent of youth aged 16 and above with an IEP that includes coordinated, measurable, annual IEP goals and transition services that will reasonably enable the student to meet the post-secondary goals.

Indicator 19 – Mediation CDE worked with the contractor to collect data that would enable calculation of percent of mediations held that resulted in mediation agreements.

Graduation Data CDE added two codes to the Exit Reason field in CASEMIS – one to identify students who graduate with a diploma with an exemption and one to identify students who graduate with a diploma with a waiver.  These data were collected in the June 2007 data collection, were removed from the Exit Data submitted November 1, 2007, and were removed from calculations for Indicator 1 – Graduation in the FFY 2006 APR.

Revisions, with Justification, to Proposed Targets / Improvement Activities / Timelines / Resources for 2006 (2006-07): [If applicable]

Review of CASEMIS submissions, particularly in relation to fields that were newly added in 2006-07 indicates that targeted technical assistance and training should be provided in completing data submissions. Particular attention will be paid to identifying SELPAs/LEAs in need of technical assistance in terms of reducing data entry errors relating to proper referral, assessment, entry, and IEP dates; data entry for transition services and post school outcomes. Submission timelines will also continue to be an issue. Analysis of revised data submission patterns may result in a change from the traditional December 1 collection date. CDE will be working with the SELPAs and LEAs to add data fields and medications that provide more precise information for calculating SPP indicators

| CONTINUING ACTIVITIES |  |  |
| --- | --- | --- |
| Improvement Activities | Timelines | Resources and Type |
| Modify validation codes and develop prototype reports. | 2005-2011 Ongoing as needed | CDE staff Type: General IDEA 2004 requirements |
| Provide statewide CASEMIS training for SELPAs | 2005-2011 Annually Fall and Spring as necessary | CDE staff, SELPA, LEAs Type: Training and Technical Assistance |
| Provide ongoing technical assistance to ensure reliable and accurate submission of data. | 2005-2011 Ongoing throughout the year | CDE staff Type: Training and Technical Assistance |

| ADDED ACTIVITIES |  |  |
| --- | --- | --- |
| Improvement Activities | Timelines | Resources and Type |
| Develop and pilot a CASEMIS generated Annual Service Plan (Part of SELPA local plan) for SELPA s to use locally in informing the public of the current services in their area and adoption of the criteria of those services. | Began 2006-07 Beginning operation 2007-08 | CDE staff Type: Monitoring and Public Reporting/Data Awareness/Data Used to Reflect Upon Practice and compliance |
| Participate in the California Commission on Teacher Credentialing (CTC) workgroup and work with CDE data unit(s) and others regarding trends. | Began 2006-07 continuing 2007-08 | CDE staff Type: Stakeholder, Public Reporting/Data Awareness/Data Used to Reflect Upon Practice and compliance http://www.ctc.ca.gov/ |
| Participation, development, implementation and monitoring of Highly Qualified Teachers under NCLB and IDEA 2004. | Began 2004 and continuing 2014 | CDE staff (Professional Development Division and Special Education Division) Type: Stakeholder, Public Reporting/Data Awareness/Data Used to Reflect Upon Practice and compliance http://www.cde.ca.gov/nclb/sr/tq/index.asp |
| Improve and expand anomaly analysis and reporting. | Began 2004 and continuing 2014 | CDE Staff |
| Provide increased technical assistance regarding data entry particularly for data fields concerning referral, assessment, IEP, and entry dates. | Ongoing throughout the year and continuing 2014 | CDE staff |
| Work with SELPAs/LEAs to ensure comprehensive use of valid school codes and unique student identifiers, Statewide Student Identifiers (SSID) | Ongoing and provided throughout the year | CDE staff and contractors |

Attachment 1: Table 7, Report of Dispute Resolution Under Part B, of the Individuals With Disabilities Education Act 2006-07

| SECTION A: Written, signed complaints |  |
| --- | --- |
| (1) Written, signed complaints total | 1117 |
| (1.1) Complaints with reports issued | 914 |
| (a) Reports with findings | 508 |
| (b) Reports within timeline | 791 |
| (c) Reports within extended timelines | 58 |
| (1.2) Complaints withdrawn or dismissed | 203 |
| (1.3) Complaints pending | 0 |
| (a) Complaint pending a due process hearing | 0 |

| SECTION B: Mediation requests |  |
| --- | --- |
| (2) Mediation requests total | 2747 |
| (2.1) Mediations |  |
| (a) Mediations related to due process | 1393 |
| (i) Mediation agreements | 570 |
| (b) Mediations not related to due process | 231 |
| (i) Mediation agreements | 122 |
| (2.2) Mediations not held (including pending) | 1123 |

| SECTION C: Hearing requests |  |
| --- | --- |
| (3) Hearing requests total | 2516 |
| (3.1) Resolution sessions | 818 |
| (a) Settlement agreements | 478 |
| (3.2) Hearings (fully adjudicated) | 74 |
| (a) Decisions within timeline | 14 |
| (b) Decisions within extended timeline | 60 |
| (3.3) Resolved without a hearing | 1735 |

| SECTION D: Expedited hearing requests (related to disciplinary decision) |  |
| --- | --- |
| (4) Expedited hearing requests total | 45 |
| (4.1) Resolution sessions | 34 |
| (a) Settlement agreements | 23 |
| (4.2) Expedited hearings (fully adjudicated) | 2 |
| (a) Change of placement ordered | 1 |